## Sheet1
Bid Invitation List
Wood Residence
Scope | Company Name | Recipient | Bid Invite Sent | Reminder Sent | Intent to Bid | Submission Status
Demo | Peitzmeier | Evan Dwyer | 2025-11-20 |  | Yes
Foundation | - | - | - | - | - | -
Concrete Flatwork | - | - | - | - | - | -
Masonry & Precast | - | - | - | - | - | -
Structural Steel | - | - | - | - | - | -
Framing Materials | unit rates
Framer | Klassen Construction | Chris Klassen |  |  | came to walk thru
Cabinetry | CKF | Tricia Gaillard | 2025-12-03 |  | Yes | Received
| Eurowood | Steve Baker | 2025-12-03 |  | Yes | Received
Countertops | CKF | Tricia Gaillard | 2025-12-03 |  | Yes | Received
| DeMarco | Gregg Narduzzo | 2025-12-03 |  | Yes | Received
Trim | unit rates
Insulation | unit rates
Roofing / Gutters | Rooferees | Trent | 2025-12-03 |  | Yes | Received
Interior Doors | Christensen Lumber | Phil Berkowitz | 2025-12-03 |  | Yes | Received
Front Door | SE Smith | Andrew Tabor | 2025-12-02 |  | Yes
| Midwest Iron | Dan Cullinane | 2025-12-02 |  | Yes | Received
Mirrors / Shower Doors | Gatsby Glass | Bob Denniston | 2025-12-03 |  | Yes | Received
| Elite Glass | Kerrie Tesmer | 2025-12-03 |  | Yes | Received
Drywall | Freedom | Randy Tufly | 2025-11-20 |  | Yes
Flooring | Timberland | Theresa | 2025-12-03 |  | Yes | Received
| Carpetland | Kevin Cupps | 2025-12-03 |  | Yes | Received
Paint | Omaha Decoration | Jon McClellan | 2025-12-03
Fireplaces | Fireplace Stone & Patio | Brad Nicholson | 2025-12-03 | 2025-12-15
Closets | SCI | Becky Maltby | 2025-11-24 |  |  | Received
| Your Custom Closet | Josh Erikson | 2025-11-24 |  |  | Received
Appliances | Ferguson |  |  |  | Yes | Received
Plumbing | unit rates
Plumbing Fixtures | Briggs | Carrie Geihs |  |  | Yes | Received
Water Filtration
HVAC | D&K | Kyle Kula | 2025-11-20 |  | Yes | Received
Electrical | Custom Electric | Jeremy Franson | 2025-11-20 |  | Yes | Received
Lighting Control / AV | Simplifi | Doug Dushan | 2025-11-20 |  | Yes
Security