## PROJECT SUMMARY
PROJECT COST SUMMARY
Wood - Bath 3
LOWER LEVEL
PROJECT | McNeil Company | [7 empty] | MAIN LEVEL
MANAGER | [8 empty] | UPPER LEVEL | 98
LOCATION | 3435 N 140th Circle, Omaha, NE | [7 empty] | TOTAL FINISHED SQUARE FEET | 98
DATE | December 2025 | [7 empty] | COVERED PORCH
LOT | [8 empty] | GARAGE
ZONING | [8 empty] | LOWER UNFINISHED
[9 empty] | TOTAL SF UNDER ROOF (including porch) | 98
PHASE | DESCRIPTION |  | ALLOW. | LABOR | MATERIAL | OTHER | SUBCONT. |  | DIVISION | FINISHED COST/SF | UNDER ROOF
1 | GENERAL REQUIREMENTS | [5 empty] | TOTAL |  | 1616 | 16.4898 | 16.4898
01.120 | Superintendent |  | 0 | 680 | 0 | 0 | 0 |  | 680 | 6.9388 | 6.9388
01.170 | Transportation - Pickup/Deliveries |  | 0 | 50 | 0 | 0 | 0 |  | 50 | 0.5102 | 0.5102
01.205 | MUD Fees |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
01.214 | Bldg. Permit/Parks/Trail/Tech Fees |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
01.230 | Builders Risk |  | 0 | 0 | 0 | 18 | 0 |  | 18 | 0.18367 | 0.18367
01.235 | General Liability |  | 0 | 0 | 0 | 33 | 0 |  | 33 | 0.33673 | 0.33673
01.253 | Safety Supplies |  | 0 |  | 20 | 0 | 0 |  | 20 | 0.20408 | 0.20408
01.452 | Testing/Inspections |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
01.501 | Temporary Utilities |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
01.531 | Technology |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
01.540 | Equipment |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
01.560 | Temporary Barriers/Enclosures/Protection |  | 0 | 120 | 150 | 0 | 0 |  | 270 | 2.7551 | 2.7551
01.740 | Cleaning & Waste Management (Dumpsters) |  | 0 | 180 | 0 | 100 | 60 |  | 340 | 3.4694 | 3.4694
01.810 | Warranties |  | 0 | 0 | 0 | 80 | 0 |  | 80 | 0.81633 | 0.81633
01.830 | Small Tools/Supply/Rent |  | 0 |  | 25 | 0 | 0 |  | 25 | 0.2551 | 0.2551
01.840 | Punchlist |  | 0 | 100 | 0 | 0 | 0 |  | 100 | 1.0204 | 1.0204
2 | EXISTING CONDITIONS | [5 empty] | TOTAL |  | 240 | 2.449 | 2.449
02.010 | Demolition |  | 0 | 0 | 0 | 0 | 240 |  | 240 | 2.449 | 2.449
6 | CARPENTRY | [5 empty] | TOTAL |  | 2708 | 27.6327 | 27.6327
06.380 | Cabinetry |  | option | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
06.460 | Wood Interior Trim |  | existing | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
06.612 | Countertop Allowance |  | 2708 | 0 | 0 | 0 | 0 |  | 2708 | 27.6327 | 27.6327
7 | MOISTURE/THERMAL PROT. | [5 empty] | TOTAL |  | 0 | 0 | 0
07.210 | Insulation |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
8 | DOORS & WINDOWS | [5 empty] | TOTAL |  | 681 | 6.949 | 6.949
08.140 | Interior Wood Doors |  | existing | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
08.817 | Mirrors/Glass Inserts/Shower Doors |  | 681 | 0 | 0 | 0 | 0 |  | 681 | 6.949 | 6.949
9 | FINISHES | [5 empty] | TOTAL |  | 2513 | 25.6429 | 25.6429
09.200 | Drywall |  | 0 | 0 | 0 | 0 | 260 |  | 260 | 2.6531 | 2.6531
09.300 | Tile
| Floor Tile |  | 1003 | 0 | 0 | 0 | 0 |  | 1003 | 10.2347 | 10.2347
| Shower/Tub Tile |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
09.720 | Wall Coverings/Faux Finishing |  | by owner | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
09.910 | Painting |  | 0 | 0 | 0 | 0 | 1250 |  | 1250 | 12.7551 | 12.7551
10 | SPECIALTIES | [5 empty] | TOTAL |  | 516 | 5.2653 | 5.2653
10.050 | Finish Hardware Allowance |  | 366 | 150 | 0 | 0 | 0 |  | 516 | 5.2653 | 5.2653
10.572 | Closets |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
12 | FURNISHINGS | [5 empty] | TOTAL |  | 0 | 0 | 0
12.170 | Art Glass |  | by owner | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
12.200 | Window Treatments |  | by owner | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
12.250 | Motorized Shades |  | by owner | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
22-23 | PLUMBING/HVAC SYSTEMS | [5 empty] | TOTAL |  | 1705 | 17.398 | 17.398
22.050 | Plumbing |  | 0 | 0 | 0 | 0 | 300 |  | 300 | 3.0612 | 3.0612
22.322 | Water Filtration System |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
22.400 | Plumbing Fixtures |  | 1355 | 0 | 0 | 0 | 0 |  | 1355 | 13.8265 | 13.8265
23.050 | HVAC |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
23.400 | Duct Cleaning |  | 0 | 0 | 0 | 0 | 50 |  | 50 | 0.5102 | 0.5102
26-28 | ELECTRICAL & LOW VOLTAGE | [5 empty] | TOTAL |  | 340 | 3.4694 | 3.4694
26.050 | Electrical |  | 0 | 0 | 0 | 0 | 340 |  | 340 | 3.4694 | 3.4694
26.505 | Light Fixtures (lit mirror, phase 8) |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
26.570 | Lighting Control System |  | option | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
27.410 | Audio-Visual Systems/Structured Wire |  | option | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
28.070 | Security System/Fire Protection |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
50 | CONTIGENCY | [5 empty] | TOTAL |  | 600 | 6.1224 | 6.1224
50.050 | Contigency | 5% | 600 | [5 empty] | 600 | 6.1224 | 6.1224
50.070 | Arch/Engr Fees (Separate Agreement) | [7 empty] | 0 | 0 | 0
| TOTAL |  | 6713 | 1280 | 195 | 231 | 2500 |  | 12884.42 | 131.4737 | 131.4737
McNeil Company Builders
PROJECT COST SUMMARY---MARKUP ANALYSIS
Project: | Wood - Bath 3 | [7 empty] | LOWER LEVEL | 0
Location: | 3435 N 140th Circle, Omaha, NE | [7 empty] | MAIN LEVEL | 0
Date: | December 2025 | [7 empty] | UPPER LEVEL | 98
Lot: | 0 | [7 empty] | TOTAL FINISHED SQUARE FEET | 98
[9 empty] | COVERED PORCH | 0
[9 empty] | TOTAL SF UNDER ROOF (including porch) | 98
[9 empty] | GARAGE | 0
[9 empty] | LOWER UNFINISHED | 0
MARKUP ADJUSTMENTS
|  |  | DIR. COST | MARKUP | TOTAL |  | ACTUAL COST |  |  | FACTOR | ADJ TOT.
| Allowances |  | 6713 | 0 | 0 |  | Allowance |  | 6713 | 0 | 0
| Labor |  | 1280 | 0 | 0 |  | Labor |  | 1280 | 0 | 0
| Material |  | 195 | 0 | 0 |  | Material |  | 195 | 0 | 0
| Other |  | 231 | 0 | 0 |  | Other |  | 231 | 0 | 0
| Subcontractor |  | 2500 | 0 | 0 |  | Subcont. |  | 2500 | 0 | 0
| Sales Tax 7% (Material Only) |  | 0 |  | 0 |  | Sale Tax Matl. |  | 0 | 0 | 0
|  |  |  | TOTAL | 0 | NO MARK-UP TOTAL |  |  | 10919 |  | 0
[10 empty] | BID | 12884.42
TOTAL BID COMPUTATION
| LOT MARKUP DEDUCTED |  |  |  |  | LOT MARKUP INCLUDED
| Total Direct Costs |  | 10919 |  |  | Total Direct Costs |  |  |  | 10919
| Indirect Cost Markup |  |  |  |  | Indirect Cost Markup |  |  |  | 0
18% | General & Admin Markup |  | 1965.42 |  |  | General & Administrative Markup |  |  |  | 1965.42
|  |  | SUBTOT. | 12884.42 | [5 empty] | SUBTOT. | 12884.42
0% |  |  | Profit | 0 | [5 empty] | Profit | 0
Deduct of Lot Markup
|  |  | TOTAL | 12884.42 | [5 empty] | TOTAL | 12884.42
0% |  | Marketing Fee-With Lot | 0 | 12884.42 |  |  |  |  | Marketing Fee-With Lot | 0 | 12884.42
|  | Marketing Fee-Without Lot | #REF! | #REF! |  |  |  |  | Marketing Fee-Without Lot | #REF! | #REF!
|  | Marketing Fee Markup With Lot | 0 | 12884.42 |  |  |  |  | Marketing Fee Markup With Lot | 0 | 12884.42
|  | Marketing Fee Markup-Without Lot | #REF! | #REF! |  |  |  |  | Marketing Fee Markup-Without Lot | #REF! | #REF!

## DIV 1 GC
| GENERAL CONDITIONS | TYPE | METHOD LS DETAILED | CLASSIFICATION MT.SUB.EQUIP.LABOR.OTHER | RESOURCE | QTY | COST | UNIT | ESTIMATE | TOTAL
1.12 | Superintendent
| Senior Supervisor |  | DETAILED | LABOR |  | 1 | 85 | HRS | 85 | 85
1.165 | Site Security | TYPE | METHOD | CLASSIFICATION | RESOURCE | QTY | COST | UNIT | SUBTOTAL | TOTAL
1.205 | MUD Fees | TYPE | METHOD | CLASSIFICATION | RESOURCE | QTY | COST | UNIT | SUBTOTAL | TOTAL
| 1" Capital Facilities Charge |  |  |  |  | 0 | 2246 |  | 0 | 346
| 1" Meter |  |  |  |  | 0 | 346 |  | 346
1.214 | Bldg. Permit/Parks/Trails/Tech Fees | TYPE | METHOD | CLASSIFICATION | RESOURCE | QTY | COST | UNIT | SUBTOTAL | TOTAL
| City of Omaha |  |  |  |  | 0 | 1878.57 |  | 0 | 0
1.216 | OPPD Fees | TYPE | METHOD | CLASSIFICATION | RESOURCE | QTY | COST | UNIT | SUBTOTAL | TOTAL
| Connect Fee |  |  |  |  | 0 | 150 |  | 0 | 0
1.23 | Builders Risk | TYPE | METHOD | CLASSIFICATION | RESOURCE | QTY | COST | UNIT | SUBTOTAL | TOTAL
| Builders Risk (0.144/100 cost) |  |  |  |  | 120 | 0.144 |  | 17.28 | 17.28
| Misc. |  |  |  |  | 0 |  |  | 0
1.235 | General Liability | TYPE | METHOD | CLASSIFICATION | RESOURCE | QTY | COST | UNIT | SUBTOTAL | TOTAL
| Liability (2.77/1000 cost) |  |  |  |  | 12 | 2.77 |  | 33.24
| Bond |  |  |  |  | 0 |  |  | 0
| Misc. |  |  |  |  | 0 |  |  | 0
1.452 | Testing/Inspections | TYPE | METHOD | CLASSIFICATION | RESOURCE | QTY | COST | UNIT | SUBTOTAL | TOTAL
| Soil Testing |  |  |  |  | 0 | 1500 |  | 0 | 0
| Call back after excavation for visual inspection |  |  |  |  | 0 | 200 |  | 0
1.501 | Temporary Utilities | TYPE | METHOD | CLASSIFICATION | RESOURCE | QTY | COST | UNIT | SUBTOTAL | TOTAL
[9 empty] | TOTAL | 0
| Temp Power Service |  |  |  |  | 0 | 150 | /MONTH | 0 | 0
| Temp Water Service |  |  |  |  | 0 | 50 | /MONTH | 0 | 0
[6 empty] | 0 | 0 |  |  | 0
| Temp Heat for Interior |  |  |  |  | 0 | 200 |  | 0 | 0
| Temp Heat for Exterior |  |  |  |  | 0 | 200 |  | 0 | 0
| Portable |  |  | Monthly Charge |  | 0 | 90 | /MONTH | 0 | 0
|  |  |  | Delivery & Pickup |  | 0 | 75 | /MONTH | 0 | 0
1.56 | Temporary Barries/Enclosures | TYPE | METHOD | CLASSIFICATION | RESOURCE | QTY | COST | UNIT | SUBTOTAL | TOTAL
|  |  |  | Material |  | 1 | 150 | EA | 150 | 270
|  |  |  | Labor |  | 2 | 60 | HRS | 120
|  |  |  | Subcontract |  | 0 | 4500 |  | 0
1.74 | Cleaning & Waste Management | TYPE | METHOD | CLASSIFICATION | RESOURCE | QTY | COST | UNIT | SUBTOTAL | TOTAL
[9 empty] | TOTAL | 213.75
Interim Cleaning
|  |  |  | Labor |  | 1 | 60 |  | 60 | 60
Final Clean
|  |  |  | Subcontract |  | 0 | 0.8 | /SF | 0 | 0
|  |  |  | Labor |  | 1 | 60 |  | 60 | 60
Dumpsters
| Excludes drywall in phase |  |  | Other | U Fill It | 0.25 | 375 |  | 93.75 | 93.75
1.81 | Warranties | TYPE | METHOD | CLASSIFICATION | RESOURCE | QTY | COST | UNIT | SUBTOTAL | TOTAL
| Warranty Historical |  |  | Own | McNeil | 12000 | 0.006 | /TOTAL/COST | 72 | 72
1.83 | Small Tools/Supply/Rent | TYPE | METHOD | CLASSIFICATION | RESOURCE | QTY | COST | UNIT | SUBTOTAL | TOTAL
| Supplies |  |  |  |  | 0 | 500 | /JOB | 0 | 0
| Rental Equipment |  |  | Equipment |  |  |  | /WEEK | 0
Miscellaneous
1.84 | Punchlist | TYPE | METHOD | CLASSIFICATION | RESOURCE | QTY | COST | UNIT | SUBTOTAL | TOTAL
[9 empty] | TOTAL | 60
|  |  |  | Labor |  | 1 | 60 |  | 60 | 60

## DIV 21 FIRE SUPPRESSION (hidden)
PHASE | DESCRIPTION | ALLOW. | LABOR | MATERIAL | OTHER | SUBCONT. | DIVISION | COST/SF | COST/UN
FIRE SUPPRESSION | [5 empty] | TOTAL | 0
21.05 | Fire Suppression (Sprinklers) | [5 empty] | 0
PHASE | FIRE SUPPRESSION
21.05 | Fire Suppression (Sprinklers)