## PROJECT SUMMARY
PROJECT COST SUMMARY
Wood - Final Scope
PROJECT | McNeil Company
MANAGER
LOCATION | 3435 N Circle, Omaha, NE
DATE | December 2025
LOT | Existing Home Renovation | [5 empty] | MAIN LEVEL | 2507
ZONING | [6 empty] | TOTAL FINISHED SQUARE FEET | 2507
[7 empty] | TOTAL SF UNDER ROOF | 2507
PHASE | DESCRIPTION | ALLOW. | LABOR | MATERIAL | OTHER | SUBCONT. | DIVISION | FINISHED COST/SF | UNDER ROOF
1 | GENERAL REQUIREMENTS |  |  |  |  | TOTAL | 103728 | 41.3753 | 41.3753
01.120 | Superintendent | 0 | 53056 | 0 | 0 | 0 | 53056 | 21.1631 | 21.1631
01.170 | Transportation - Pickup/Deliveries | 0 | 1690 | 0 | 0 | 0 | 1690 | 0.67411 | 0.67411
01.205 | MUD Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
01.214 | Bldg. Permit/Parks/Trail/Tech Fees | 0 |  | 0 | 2400 | 0 | 2400 | 0.95732 | 0.95732
01.230 | Builders Risk | 0 | 0 | 0 | 1443 | 0 | 1443 | 0.57559 | 0.57559
01.235 | General Liability | 0 | 0 | 0 | 2806 | 0 | 2806 | 1.1193 | 1.1193
01.253 | Safety Supplies | 0 | 0 | 0 | 430 | 0 | 430 | 0.17152 | 0.17152
01.452 | Testing/Inspections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
01.501 | Temporary Utilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
01.531 | Technology | 0 | 0 | 0 | 1275 | 0 | 1275 | 0.50858 | 0.50858
01.540 | Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
01.560 | Temporary Barriers/Enclosures/Protection | 0 | 4180 | 2570 | 0 | 0 | 6750 | 2.6925 | 2.6925
01.740 | Cleaning & Waste Management (Dumpsters) | 0 | 11060 | 0 | 5388 | 4199 | 20647 | 8.2357 | 8.2357
01.810 | Warranties | 0 | 0 | 0 | 6471 | 0 | 6471 | 2.5812 | 2.5812
01.830 | Small Tools/Supply/Rent | 0 | 0 | 0 | 2060 | 0 | 2060 | 0.8217 | 0.8217
01.840 | Punchlist | 0 | 4700 | 0 | 0 | 0 | 4700 | 1.8748 | 1.8748
2 | EXISTING CONDITIONS |  |  |  |  | TOTAL | 19030 | 7.5907 | 7.5907
02.010 | Demolition | 0 | 0 | 0 | 1200 | 17830 | 19030 | 7.5907 | 7.5907
4 | MASONRY |  |  |  |  | TOTAL | 900 | 0.35899 | 0.35899
04.210 | Brick (repair) | 0 | 0 | 0 | 0 | 900 | 900 | 0.35899 | 0.35899
5 | METAL |  |  |  |  | TOTAL | 0 | 0 | 0
05.120 | Structural Steel Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | CARPENTRY |  |  |  |  | TOTAL | 306157 | 122.1209 | 122.1209
06.110 | Wood Framing | 0 | 0 | 8200 | 0 | 26800 | 35000 | 13.9609 | 13.9609
06.380 | Cabinetry Allowance | 154190 | 0 | 0 | 0 | 0 | 154190 | 61.5038 | 61.5038
06.460 | Wood Interior Trim | 0 | 0 | 20855 | 0 | 35240 | 56095 | 22.3753 | 22.3753
06.612 | Countertop Allowance | 60801 | 0 | 71 | 0 | 0 | 60872 | 24.2808 | 24.2808
7 | MOISTURE/THERMAL PROT. |  |  |  |  | TOTAL | 8825 | 3.5201 | 3.5201
07.130 | Waterproofing/Passive Radon | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
07.210 | Insulation | 0 | 0 | 0 | 0 | 8825 | 8825 | 3.5201 | 3.5201
8 | DOORS & WINDOWS |  |  |  |  | TOTAL | 53370 | 21.2884 | 21.2884
08.140 | Interior Wood Doors Allowance | 11003 | 0 | 0 | 0 | 0 | 11003 | 4.3889 | 4.3889
08.178 | Front Door Allowance | 22248 | 1680 | 0 | 750 | 0 | 24678 | 9.8436 | 9.8436
08.500 | Windows - existing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
08.817 | Mirrors/Glass Inserts/Shower Doors Allowance | 17689 | 0 | 0 | 0 | 0 | 17689 | 7.0558 | 7.0558
9 | FINISHES |  |  |  |  | TOTAL | 307999 | 122.8556 | 122.8556
09.200 | Drywall | 0 | 0 | 0 | 0 | 21099 | 21099 | 8.416 | 8.416
09.300 | Tile Allowances
| Floor Tile | 44349 | 0 | 0 | 0 | 0 | 44349 | 17.6901 | 17.6901
| Tile Backsplash | 5589 | 0 | 0 | 0 | 0 | 5589 | 2.2294 | 2.2294
| Wall Tile/Columns | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Shower/Tub Tile | 30137 | 0 | 0 | 0 | 0 | 30137 | 12.0211 | 12.0211
09.640 | Wood Flooring Allowance | 10942 | 0 | 0 | 0 | 0 | 10942 | 4.3646 | 4.3646
09.672 | Epoxy Flooring Allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
09.680 | Carpet Allowance | 60538 | 0 | 0 | 0 | 0 | 60538 | 24.1476 | 24.1476
09.720 | Wall Coverings/Faux Finishing | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
09.910 | Painting | 0 | 0 | 0 | 0 | 135345 | 135345 | 53.9868 | 53.9868
10 | SPECIALTIES |  |  |  |  | TOTAL | 76085 | 30.349 | 30.349
10.050 | Finish Hardware Allowance | 17933 | 6525 | 0 | 0 | 0 | 24458 | 9.7559 | 9.7559
10.310 | Fireplaces (door replacement only) | 0 | 0 | 0 | 0 | 12155 | 12155 | 4.8484 | 4.8484
10.314 | Fireplace Facings Allowance | 6185 | 180 | 0 | 0 | 975 | 7340 | 2.9278 | 2.9278
10.572 | Storage Shelving | 0 | 1110 | 2584 | 0 | 0 | 3694 | 1.4735 | 1.4735
10.572 | Closets Allowance | 28438 | 0 | 0 | 0 | 0 | 28438 | 11.3434 | 11.3434
11 | EQUIPMENT |  |  |  |  | TOTAL | 52991 | 21.1372 | 21.1372
11.302 | Residential Appliance Allowance | 48777 | 920 | 0 | 0 | 0 | 49697 | 19.8233 | 19.8233
11.52 | TV's Allowance | 3294 | 0 | 0 | 0 | 0 | 3294 | 1.3139 | 1.3139
12 | FURNISHINGS |  |  |  |  | TOTAL | 0 | 0 | 0
12.170 | Art Glass | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.200 | Window Treatments | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.250 | Motorized Shades | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | SPECIAL CONSTRUCTION |  |  |  |  | TOTAL | 9291 | 3.706 | 3.706
13.174 | Sauna | 8121 | 1170 | 0 | 0 | 0 | 9291 | 3.706 | 3.706
22-23 | PLUMBING/HVAC SYSTEMS |  |  |  |  | TOTAL | 70456 | 28.1037 | 28.1037
22.050 | Plumbing | 0 | 0 | 0 | 0 | 23770 | 23770 | 9.4815 | 9.4815
22.322 | Water Filtration System | option | 0 | 0 | 0 | 0 | 0 | 0 | 0
22.400 | Plumbing Fixtures Allowance | 25834 | 0 | 0 | 0 | 0 | 25834 | 10.3047 | 10.3047
23.050 | HVAC | 0 | 360 | 642 | 0 | 15400 | 16402 | 6.5425 | 6.5425
23.400 | Duct Cleaning | 0 | 0 | 0 | 0 | 4450 | 4450 | 1.775 | 1.775
26-28 | ELECTRICAL & LOW VOLTAGE |  |  |  |  | TOTAL | 173703 | 69.2872 | 69.2872
26.050 | Electrical (includes electrical demo) | 0 | 0 | 0 | 0 | 47805 | 47805 | 19.0686 | 19.0686
26.505 | Light Fixtures Allowance | 67119 | 0 | 0 | 0 | 0 | 67119 | 26.7726 | 26.7726
26.570 | Lighting Control System Allowance | option | 0 | 0 | 0 | 0 | 0 | 0 | 0
27.410 | Audio-Visual Systems/Structured Wire Allow. | 56029 | 0 | 0 | 0 | 0 | 56029 | 22.349 | 22.349
28.070 | Security System/Fire Protection Allowance | 2750 | 0 | 0 | 0 | 0 | 2750 | 1.0969 | 1.0969
50 | CONTIGENCY |  |  |  |  | TOTAL | 54688 | 21.8141 | 21.8141
50.050 | Contigency | 54188 |  |  |  |  | 54188 | 21.6147 | 21.6147
50.070 | Arch/Engr Fees (Separate Agreement) | 500 |  |  |  |  | 500 | 0.19944 | 0.19944
| TOTAL | 736654 | 86631 | 34922 | 24223 | 354793 | 1459923.14 | 582.3387 | 582.3387
McNeil Company Builders
PROJECT COST SUMMARY---MARKUP ANALYSIS
Project: | Wood - Final Scope | [5 empty] | MAIN LEVEL | 2507
Location: | 3435 N Circle, Omaha, NE | [5 empty] | TOTAL FINISHED SQUARE FEET | 2507
Date: | December 2025 | [5 empty] | TOTAL SF UNDER ROOF | 2507
Lot: | Existing Home Renovation
MARKUP ADJUSTMENTS
|  | DIR. COST | MARKUP | TOTAL |  | ACTUAL COST |  | FACTOR | ADJ TOT.
| Allowances | 736654 | 0 | 0 |  | Allowance | 736654 | 0 | 0
| Labor | 86631 | 0 | 0 |  | Labor | 86631 | 0 | 0
| Material | 34922 | 0 | 0 |  | Material | 34922 | 0 | 0
| Other | 24223 | 0 | 0 |  | Other | 24223 | 0 | 0
| Subcontractor | 354793 | 0 | 0 |  | Subcont. | 354793 | 0 | 0
| Sales Tax 7% (Material Only) | 0 |  | 0 |  | Sale Tax Matl. | 0 | 0 | 0
|  |  | TOTAL | 0 | NO MARK-UP TOTAL |  | 1237223 |  | 0
[8 empty] | BID | 1459923.14
TOTAL BID COMPUTATION
| LOT MARKUP DEDUCTED |  |  |  | LOT MARKUP INCLUDED
| Total Direct Costs | 1237223 |  |  | Total Direct Costs |  |  | 1237223
| Indirect Cost Markup |  |  |  | Indirect Cost Markup |  |  | 0
18% | General & Admin Markup | 222700.14 |  |  | General & Administrative Markup |  |  | 222700.14
|  | SUBTOT. | 1459923.14 |  |  |  |  | SUBTOT. | 1459923.14
0% |  | Profit | 0 |  |  |  |  | Profit | 0
Deduct of Lot Markup
|  | TOTAL | 1459923.14 |  |  |  |  | TOTAL | 1459923.14
[7 empty] | Marketing Fee-With Lot | 0 | 1459923.14

## PROJECT BREAKDOWN
PROJECT COST BREAKDOWN
Wood - Final Scope (Breakdown)
PROJECT | McNeil Company
MANAGER
LOCATION | 3435 N Circle, Omaha, NE
DATE | December 2025
LOT
ZONING
PHASE | DESCRIPTION |  | Kitchen Wing | Primary Suite | Sauna | Bath 2 Shower | Bath 2 | Bath 2 - New Cab | Bath 3 Shower | Bath 3 | Bath 3 - New Cab | Front Door | Decorative Muntins - TBD | Change Tub Selection | Heated Floor - Primary Bath | Pantry to be painted | New cabs in Hearth Room - TBD | New carpet at curved stairs - up | New carpet at curved stairs - down | New wall mouldings - Foyer | New wall mouldings - Great Room | New flooring Great Room - carpet | Reframe steps to Great Room | New Foyer Chandelier | Balcony Sconces | Balcony wall mouldings | Paint Upper Level (GR, Foyer, Balcony) | Re-finish stair parts - TBD | New carpet at UL | Paint Lower Level | New carpet at LL | Storage Shelving in LL Mech/Stor. | New Hardware at LL & UL | AV Systems | TV's | Lighting Control - TBD | TOTAL
1 | GENERAL REQUIREMENTS
01.120 | Superintendent |  | 23750 | 25268 | 1020 | 425 | 680 | 0 | 425 | 680 | 0 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 85 | 0 | 0 | 43 | 85 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53056 | 103728
01.170 | Transportation - Pickup/Deliveries |  | 500 | 750 | 180 | 50 | 50 | 0 | 50 | 50 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1690
01.205 | MUD Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
01.214 | Bldg. Permit/Parks/Trail/Tech Fees |  | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400
01.230 | Builders Risk |  | 661 | 620 | 36 | 20 | 16 | 0 | 20 | 18 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1443
01.235 | General Liability |  | 1307 | 1191 | 69 | 38 | 31 | 0 | 38 | 33 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2806
01.253 | Safety Supplies |  | 150 | 150 | 25 | 20 | 20 | 0 | 20 | 20 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430
01.452 | Testing/Inspections |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
01.501 | Temporary Utilities |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | matches summary
01.531 | Technology |  | 500 | 725 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1275
01.540 | Equipment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
01.560 | Temporary Barriers/Enclosures/Protection |  | 1850 | 3000 | 440 | 270 | 270 | 0 | 270 | 270 | 0 | 380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6750
01.740 | Cleaning & Waste Management (Dumpsters) |  | 9500 | 9459 | 340 | 334 | 340 | 0 | 334 | 340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20647
01.810 | Warranties |  | 2832 | 2951 | 153 | 81 | 80 | 0 | 81 | 80 | 0 | 213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6471
01.830 | Small Tools/Supply/Rent |  | 750 | 1000 | 100 | 25 | 25 | 0 | 25 | 25 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2060
01.840 | Punchlist |  | 2000 | 2000 | 200 | 100 | 100 | 0 | 100 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4700
2 | EXISTING CONDITIONS
02.010 | Demolition |  | 9045 | 7085 | 360 | 240 | 240 |  | 240 | 240 |  | 980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19030 | 19030 | matches summary
4 | MASONRY
04.210 | Brick (repair) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 900 | matches summary
5 | METAL
05.120 | Structural Steel Material |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | matches summary
6 | CARPENTRY
06.110 | Wood Framing |  | 14300 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 306157
06.380 | Cabinetry Allowance |  | 111393 | 33746 | 0 | 0 | 0 | 3559 | 0 | 0 | 3559 | 0 | 0 | 0 | 0 | 1933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154190
06.460 | Wood Interior Trim |  | 22850 | 18961 | 1460 | 0 | 0 | 0 | 0 | 0 | 0 | 1899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4711 | 4824 | 0 | 0 | 0 | 0 | 1390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56095 |  | matches summary
06.612 | Countertop Allowance |  | 30633 | 23798 | 0 | 400 | 2933 | 0 | 400 | 2708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60872
7 | MOISTURE/THERMAL PROT.
07.130 | Waterproofing/Passive Radon |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8825
07.210 | Insulation |  | 3000 | 5825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8825 |  | matches summary
8 | DOORS & WINDOWS
08.140 | Interior Wood Doors |  | 3262 | 7013 | 728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11003 | 53370
08.178 | Front Door Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24678
08.500 | Windows |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | matches summary
08.817 | Mirrors/Glass Inserts/Shower Doors |  | 1786 | 8202 | 325 | 2935 | 681 | 0 | 3079 | 681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17689
9 | FINISHES
09.200 | Drywall |  | 5581 | 12013 | 1820 | 260 | 260 | 0 | 260 | 260 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21099 | 307999
09.300 | Tile | [35 empty] | 0
| Floor Tile |  | 8531 | 26932 | 2143 | 0 | 1960 | 0 | 0 | 1003 | 0 | 0 | 0 | 0 | 3780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44349
| Shower/Tub Tile |  | 0 | 17139 | 0 | 6080 | 0 | 0 | 6918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30137
| Tile Backsplash |  | 5589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5589
| Wall Tile/Columns |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
09.640 | Wood Flooring |  | 10942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10942 |  | matches summary
09.672 | Epoxy Flooring |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
09.680 | Carpet |  | 0 | 11652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4620 | 4620 | 0 | 0 | 5748 | 0 | 0 | 0 | 0 | 0 | 0 | 10593 | 0 | 23305 | 0 | 0 | 0 | 0 | 0 | 60538
09.720 | Wall Coverings/Faux Finishing |  | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner
09.910 | Painting |  | 33680 | 24620 | 1250 | 250 | 1250 |  | 250 | 1250 |  | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350 | 1875 | 0 | 0 | 0 | 475 | 550 | 25423 | 0 | 0 | 42372 | 0 | 0 | 0 | 0 | 0 | 0 | 135345
10 | SPECIALTIES
10.050 | Finish Hardware Allowance |  | 10136 | 7748 | 300 | 0 | 516 | 0 | 0 | 516 | 0 | 1352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3890 | 0 | 0 | 0 | 24458 | 76085
10.310 | Fireplaces (door replacement only) |  | 5936 | 6219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12155
10.314 | Fireplace Facings |  | 4737 | 2603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7340 |  | matches summary
10.562 | Storage Shelving |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3694 | 0 | 0 | 0 | 0 | 3694
10.572 | Closets |  | 1055 | 27383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28438
11 | EQUIPMENT
11.302 | Residential Appliance |  | 47280 | 2417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49697 | 52991
11.52 | TV's |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3294 | 0 | 3294 |  | matches summary
12 | FURNISHINGS
12.170 | Art Glass |  | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner
12.200 | Window Treatments |  | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner
12.250 | Motorized Shades |  | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner | by owner
13 | SPECIAL CONSTRUCTION
13.174 | Sauna |  | 0 | 0 | 9291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9291 | 9291 | matches summary
22-23 | PLUMBING/HVAC SYSTEMS
22.050 | Plumbing |  | 4675 | 17595 | 0 | 450 | 300 | 0 | 450 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23770 | 70456
22.322 | Water Filtration System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22.400 | Plumbing Fixtures |  | 8709 | 14047 | 0 | 654 | 1355 | 0 | 654 | 1355 | 0 | 0 | 0 | -940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25834 |  | matches summary
23.050 | HVAC |  | 8384 | 7118 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16402
23.400 | Duct Cleaning |  | 0 | 4300 | 50 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4450
26-28 | ELECTRICAL & LOW VOLTAGE
26.050 | Electrical (includes electrical demo) |  | 22155 | 22065 | 855 | 0 | 360 | 0 | 0 | 340 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 840 | 840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47805 | 173703
26.505 | Light Fixtures Allowance |  | 25199 | 18083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21650 | 2187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67119
26.570 | Lighting Control System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | matches summary
27.410 | Audio-Visual Systems/Structured Wire |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56029 | 0 | 0 | 56029
28.070 | Security System/Fire Protection |  | 1750 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750
50 | CONTIGENCY
50.050 | Contigency | 5% | 26500 | 22500 | 1250 | 750 | 600 |  | 750 | 600 |  | 1000 | [5 empty] | 231 | 7 | [17 empty] | 54188 | 54688 | matches summary, adjusted contingency
50.070 | Arch/Engr Fees (Separate Agreement) | [10 empty] | 500 | [24 empty] | 500
| TOTAL |  | 472108 | 418178 | 23345 | 13382 | 12117 | 3559 | 14364 | 10919 | 3559 | 33898 | 0 | -940 | 4130 | 1933 | 0 | 4851 | 4627 | 6146 | 6784 | 6148 | 1100 | 22533 | 3857 | 2025 | 25423 | 0 | 10593 | 42372 | 23305 | 3694 | 3890 | 56029 | 3294 | 0 | 1237223 | matches summary, adjusted to match book
|  |  | matches estimate | matches BOOK | matches estimate | matches estimate | matches estimate | matches estimate | matches estimate | matches estimate | matches estimate | *matches estimate | matches estimate | matches estimate | matches estimate | matches estimate | matches estimate | matches estimate | *matches estimate | matches estimate | matches estimate | matches estimate | matches estimate | matches estimate | matches estimate | matches estimate | matches estimate | matches estimate | matches estimate | matches estimate | matches estimate | matches estimate | matches estimate | matches estimate | matches estimate | matches estimate | matches # below
McNeil Company Builders | [18 empty] | adjusted cont.
PROJECT COST SUMMARY---MARKUP ANALYSIS
Project: | Wood Residence - Final Scope
Location: | 3435 N Circle, Omaha, NE
Date: | December 2025
MARKUP ADJUSTMENTS
|  |  | DIR. COST | MARKUP | FEE TOTAL | COST +FEE
| Kitchen Wing |  | 472108 | 18% | 84979.44 | 557087.44 | matches estimate / book
| Primary Suite |  | 418178 | 18% | 75272.04 | 493450.04 | matches book |  | excel estimate does NOT match the book ($1158 less in the book) - $494,608
| Sauna |  | 23345 | 18% | 4202.1 | 27547.1 | matches estimate / book
| Bath 2 Shower |  | 13382 | 18% | 2408.76 | 15790.76 | matches estimate / book
| Bath 2 |  | 12117 | 18% | 2181.06 | 14298.06 | matches estimate / book
| Bath 2 - New Cabinet |  | 3559 | 18% | 640.62 | 4199.62 | matches estimate / book
| Bath 3 Shower |  | 14364 | 18% | 2585.52 | 16949.52 | matches estimate / book
| Bath 3 |  | 10919 | 18% | 1965.42 | 12884.42 | matches estimate / book
| Bath 3 - New Cabinet |  | 3559 | 18% | 640.62 | 4199.62 | matches estimate / book
| Front Door |  | 33898 | 18% | 6101.64 | 39999.64 | matches estimate / book
| Decorative Muntins - TBD |  | 0 | 18% | 0 | 0 | matches estimate / book
| Change Tub Selection |  | -940 | 18% | -169.2 | -1109.2 | matches estimate / book
| Heated Floor - Primary Bath |  | 4130 | 18% | 743.4 | 4873.4 | matches estimate / book |  | auto math off by $1, $4874
| Pantry to be Painted |  | 1933 | 18% | 347.94 | 2280.94 | matches estimate / book
| New Cabinets at Hearth Room - TBD |  | 0 | 18% | 0 | 0 | matches estimate / book
| New Carpet at Curved Stairs - Up |  | 4851 | 18% | 873.18 | 5724.18 | matches estimate / book |  | auto math off by $1, $5725
| New Carpet at Curved Stairs - Down |  | 4627 | 18% | 832.86 | 5459.86 | matches estimate / book |  | auto math off by $1, $5725
| New Wall Mouldings - Foyer |  | 6146 | 18% | 1106.28 | 7252.28 | matches estimate / book |  | auto math off by $1, $7253
| New Wall Mouldings - Great Room |  | 6784 | 18% | 1221.12 | 8005.12 | matches estimate / book |  | auto math off by $1, $8006
| New Flooring in Great Room - Carpet |  | 6148 | 18% | 1106.64 | 7254.64 | matches estimate / book
| Reframe Steps to Great Room |  | 1100 | 18% | 198 | 1298 | matches estimate / book
| New Foyer Chandelier |  | 22533 | 18% | 4055.94 | 26588.94 | matches estimate / book
| New Balcony Sconces |  | 3857 | 18% | 694.26 | 4551.26 | matches estimate / book |  | auto math off by $1, $4552
| Balcony Wall Mouldings |  | 2025 | 18% | 364.5 | 2389.5 | matches estimate / book
| Paint Upper Level (GR, Foyer, Balcony) |  | 25423 | 18% | 4576.14 | 29999.14 | matches estimate / book |  | auto math off by $1, $30,000
| Refinish Stair Parts - TBD |  | 0 | 18% | 0 | 0 | matches estimate / book
| New carpet UL |  | 10593 | 18% | 1906.74 | 12499.74 | matches estimate / book
| Paint LL |  | 42372 | 18% | 7626.96 | 49998.96 | matches estimate / book |  | auto math off by $1, $50,000
| New carpet at LL |  | 23305 | 18% | 4194.9 | 27499.9 | matches estimate / book
| Storage Shelving in LL Mech/Storage |  | 3694 | 18% | 664.92 | 4358.92 | *matches estimate / book
| New Hardware at UL & LL |  | 3890 | 18% | 700.2 | 4590.2 | matches estimate / book
| AV Systems |  | 56029 | 18% | 10085.22 | 66114.22 | matches estimate / book |  | auto math off by $1, $66,115
| TV's |  | 3294 | 18% | 592.92 | 3886.92 | matches estimate - fee not applied, deducted in payapp
| Lighting Control - TBD |  | 0 | 18% | 0 | 0 | matches estimate / book
| TOTALS |  | 1237223 |  | 222700.14 | 1459923.14 | matches summary / book

## DIV 21 FIRE SUPPRESSION (hidden)
PHASE | DESCRIPTION | ALLOW. | LABOR | MATERIAL | OTHER | SUBCONT. | DIVISION | COST/SF | COST/UN
FIRE SUPPRESSION | [5 empty] | TOTAL | 0
21.05 | Fire Suppression (Sprinklers) | [5 empty] | 0
PHASE | FIRE SUPPRESSION
21.05 | Fire Suppression (Sprinklers)