

2/16/26
Crockett Residence – preliminary cash flow projection

Design Deposit (already paid $20,000)	paid
Design Draw 2	$20,000.00	4/1/2026
Design Draw 3	$30,000.00	5/1/2026	
Design Draw 4 (pending final billable hours*)	$40,000.00*	6/1/2026

LOT PURCHASE	 $345,000.00	4/30/2026

upon beginning of surcharge	$50,000.00	5/10/2026
upon signed agreement – CONSTRUCTION DEPOSIT	$200,000.00	5/30/2026
upon completion of pouring foundation	$200,000.00	7/10/2026
upon beginning of framing	$300,000.00	8/10/2026
upon completion of window installation	$300,000.00	10/20/2026
upon beginning of electrical rough in	$300,000.00	12/1/2026
upon beginning of drywall 	$300,000.00	2/12/2027
upon beginning of the cabinetry installation 	$300,000.00	3/23/2027
upon beginning of retaining walls	$150,000.00	4/5/2027
upon completion of pool rough-in	$100,000.00	5/1/2027
upon completion of driveway concrete	$100,000.00	5/20/2027
upon beginning of painting 	$300,000.00	6/15/2027
upon substantial completion of sitework 	$75,000.00	9/15/2027
upon substantial completion (plus allowance changes**)	$75,000.00**	11/15/2027

