## A
CONTRACTOR'S APPLICATION FOR PAYMENT
TO (OWNER): |  | Phil & Michelle Wood |  |  |  |  | APPLICATION NO.: | 1
PROJECT: |  | Wood Residence |  |  |  |  | APPLICATION DATE: | 2026-03-10
FROM (CONTRACTOR): |  | McNeil Company |  |  |  |  | PAYMENT DUE DATE: | 2026-03-17
CONTRACT FOR: |  | Phil & Michelle Wood
CHANGE ORDER SUMMARY
|  |  |  | CHANGES APPROVED PREVIOUS | CHANGES APPROVED THIS PERIOD | Application is made for Payment, as shown below, in connection with the Contract Continuation Sheet, B, is attached.
Number | Description |  |  | Value | Value
1 | Renovate LL bathrooms (Powder & #4) |  |  |  | 50903.24 | ORIGINAL CONTRACT SUM |  |  | 1459923.14
2 | [5 empty] | NET CHANGE BY CHANGE ORDERS |  |  | 50903.24
3 | [5 empty] | CONTRACT SUM TO DATE |  |  | 1510826.38
4 | [5 empty] | TOTAL BILLED TO DATE |  |  | 0
5
6 | [5 empty] | CURRENT PAYMENT DUE |  |  | 82582.9333
7
8 | [5 empty] | BALANCE TO FINISH, INCLUDING FEE |  |  | 1428243.4467
9
10
11
12
13
14
15
16
17
|  |  | TOTAL | 0 | 50903.24
|  |  |  | NET CHANGE BY CHANGE ORDERS | 50903.24

## B
CONTRACT CONTINUATION SHEET B
[5 empty] | APPLICATION NUMBER: |  |  |  | 1
[5 empty] | APPLICATION DATE: |  |  |  | 2026-03-10
[5 empty] | PAYMENT DUE DATE: |  |  |  | 2026-03-17
A | B | C | D | MCNEIL | E | MCNEIL TEAM |  |  | F | G | MCNEIL TEAM | [11 empty] | H
ITEM | DESCRIPTION OF WORK | ORIGINAL | CHANGE | CHANGE | CURRENT | TOTAL | ACCRUAL | ACCRUAL | TOTAL | TOTAL | Pay App #12 | Pay App #11 | Pay App #10 | Pay App #9 | Pay App #8 | Pay App #7 | Pay App #6 | Pay App #5 | Pay App #4 | Pay App #3 | Pay App #2 | Pay App #1 | BALANCE
NO |  | SCHEDULED | ORDER | ORDER | SCHEDULED | INVOICED | AMOUNT | DESCRIPTION | COMPLETED | PREVIOUS | [12 empty] | TO FINISH
|  | VALUE | VALUE | DESCRIPTION | VALUE | THIS PERIOD | THIS PERIOD |  | THIS PERIOD | COST
01-000 | General Requirements
01-120 | Superintendent | 53056 | 1360 | CO1 $1360 | 54416 | 5010.75 |  |  | 5010.75 | 0 | [12 empty] | 49405.25
01-170 | Travel/Pickup/Delivery | 1690 | 150 | CO1 $150 | 1840 | 891.6 |  |  | 891.6 | 0 | [12 empty] | 948.4
01-205 | MUD Fees | 0 | 0 |  | 0 |  |  |  | 0 | 0 | [12 empty] | 0
01-214 | Permits | 2400 | 0 |  | 2400 | 1378.76 |  |  | 1378.76 | 0 | [12 empty] | 1021.24
01-230 | Builder's Risk | 1443 | 64 | CO1 $64 | 1507 | 125.5833 |  |  | 125.5833 | 0 | [12 empty] | 1381.4167
01-235 | General Liability | 2806 | 123 | CO1 $123 | 2929 | 244.0833 |  |  | 244.0833 | 0 | [12 empty] | 2684.9167
01-253 | Safety Supplies | 430 | 60 | CO1 $60 | 490 |  |  |  | 0 | 0 | [12 empty] | 490
01-501 | Temporary Utilities & Toilets | 0 | 0 |  | 0 |  |  |  | 0 | 0 | [12 empty] | 0
01-531 | Technology | 1275 | 0 |  | 1275 | 106.25 |  |  | 106.25 | 0 | [12 empty] | 1168.75
01-560 | Temporary Barries/Enclosures | 6750 | 810 | CO1 $810 | 7560 | 5600.7 |  |  | 5600.7 | 0 | [12 empty] | 1959.3
01-740 | Cleaning & Waste Management | 20647 | 963 | CO1 $963 | 21610 | 1379.61 |  |  | 1379.61 | 0 | [12 empty] | 20230.39
01-810 | Warranties | 6471 | 264 | CO1 $264 | 6735 | 561.25 |  |  | 561.25 | 0 | [12 empty] | 6173.75
01-830 | Small Tools/Supplies/Rental | 2060 | 75 | CO1 $75 | 2135 | 215.45 |  |  | 215.45 | 0 | [12 empty] | 1919.55
01-840 | Punchlist | 4700 | 300 | CO1 $300 | 5000 |  |  |  | 0 | 0 | [12 empty] | 5000
02-000 | Existing Conditions
02-010 | Demolition | 19030 | 730 | CO1 $730 | 19760 | 4744.88 | 15000 | accrue for Peitzmeier invoice | 19744.88 | 0 | [12 empty] | 15.12
04-000 | Masonry
04-210 | Brick Masonry (repair) | 900 | 0 |  | 900 |  |  |  | 0 | 0 | [12 empty] | 900
05-000 | Metal
05-120 | Structural Steel - Material | 0 | 0 |  | 0 |  |  |  | 0 | 0 | [12 empty] | 0
06-000 | Carpentry
06-110 | Wood Framing | 35000 | 0 |  | 35000 | 2166.03 | 3000 | accrue for 1 week for Klassen @ $75/hr | 5166.03 | 0 | [12 empty] | 29833.97
06-380 | Cabinetry Allowance | 154190 | 5048 | CO1 $5048 | 159238 | 16304 |  |  | 16304 | 0 | [12 empty] | 142934
06-460 | Wood Interior Trim | 56095 | 0 |  | 56095 |  |  |  | 0 | 0 | [12 empty] | 56095
06-612 | Countertop Allowance | 60872 | 4963 |  | 65835 |  |  |  | 0 | 0 | [12 empty] | 65835
07-000 | Moisture/Thermal Protection
07-130 | Waterproofing | 0 | 0 |  | 0 |  |  |  | 0 | 0 | [12 empty] | 0
07-210 | Insulation | 8825 | 0 |  | 8825 |  |  |  | 0 | 0 | [12 empty] | 8825
08-000 | Doors/Windows/Glazing
08-140 | Interior Wood Doors | 11003 | 0 |  | 11003 |  |  |  | 0 | 0 | [12 empty] | 11003
08-178 | Front Door | 24678 | 0 |  | 24678 |  |  |  | 0 | 0 | [12 empty] | 24678
08-500 | Windows - existing | 0 | 0 |  | 0 |  |  |  | 0 | 0 | [12 empty] | 0
08-817 | Mirrors/Glass Inserts | 17689 | 3616 | CO1 $3616 | 21305 |  |  |  | 0 | 0 | [12 empty] | 21305
09-000 | Finishes
09-200 | Drywall | 21099 | 780 | CO1 $780 | 21879 |  |  |  | 0 | 0 | [12 empty] | 21879
09-300 | Tile
| Floor Tile | 44349 | 2200 | CO1 $2200 | 46549 |  |  |  | 0 | 0 | [12 empty] | 46549
| Tile Backsplash | 5589 | 0 |  | 5589 |  |  |  | 0 | 0 | [12 empty] | 5589
| Wall Tile/Columns | 0 | 0 |  | 0 |  |  |  | 0 | 0 | [12 empty] | 0
| Shower/Tub Tile | 30137 | 6560 | CO1 $6560 | 36697 |  |  |  | 0 | 0 | [12 empty] | 36697
09-640 | Wood Flooring | 10942 | 0 |  | 10942 |  |  |  | 0 | 0 | [12 empty] | 10942
09-672 | Epoxy Flooring | 0 | 0 |  | 0 |  |  |  | 0 | 0 | [12 empty] | 0
09-680 | Carpeting | 60538 | 0 |  | 60538 |  |  |  | 0 | 0 | [12 empty] | 60538
09-720 | Wall Coverings/Faux Finishing | 0 | 0 |  | 0 |  |  |  | 0 | 0 | [12 empty] | 0
09-910 | Painting | 135345 | 3000 | CO1 $3000 | 138345 |  |  |  | 0 | 0 | [12 empty] | 138345
10-000 | Specialties
10-050 | Finish Hardware Allowance | 24458 | 1479.34 | CO1 $1479 | 25937.34 |  |  |  | 0 | 0 | [12 empty] | 25937.34
10-310 | Fireplaces | 12155 | 0 |  | 12155 |  |  |  | 0 | 0 | [12 empty] | 12155
10-314 | Fireplace Facings Allowance | 7340 | 0 |  | 7340 |  |  |  | 0 | 0 | [12 empty] | 7340
10-562 | Storage Shelving | 3694 | 0 |  | 3694 |  |  |  | 0 | 0 | [12 empty] | 3694
10-572 | Closet Allowance | 28438 | 0 |  | 28438 |  |  |  | 0 | 0 | [12 empty] | 28438
11-000 | Architectural Equipment
11-302 | Residential Appliance Allowance | 49697 | 0 |  | 49697 |  |  |  | 0 | 0 | [12 empty] | 49697
11-520 | TV's | 3294 | 0 |  | 3294 |  |  |  | 0 | 0 | [12 empty] | 3294
12-000 | Furnishings
12-250 | Motorized Shades | 0 | 0 |  | 0 |  |  |  | 0 | 0 | [12 empty] | 0
13-000 | Special Construction
13-174 | Sauna | 9291 | 0 |  | 9291 |  |  |  | 0 | 0 | [12 empty] | 9291
14-000 | Conveying Systems
22-000 | Plumbing
22-050 | Plumbing | 23770 | 1050 | CO1 $1050 | 24820 |  |  |  | 0 | 0 | [12 empty] | 24820
22-322 | Water Filtration System | 0 | 0 |  | 0 |  |  |  | 0 | 0 | [12 empty] | 0
22-400 | Plumbing Fixtures | 25834 | 3364 | CO1 $3364 | 29198 |  |  |  | 0 | 0 | [12 empty] | 29198
23-000 | HVAC
23-050 | HVAC | 16402 | 0 |  | 16402 | 212.59 |  |  | 212.59 | 0 | [12 empty] | 16189.41
23-400 | Duct Cleaning | 4450 | 100 | CO1 $100 | 4550 |  |  |  | 0 | 0 | [12 empty] | 4550
26-000 | Electrical
26-050 | Electrical | 47805 | 940 | CO1 $940 | 48745 | 2610 |  |  | 2610 | 0 | [12 empty] | 46135
26-505 | Light Fixtures Allowance | 67119 | 2889 | CO1 $2889 | 70008 |  |  |  | 0 | 0 | [12 empty] | 70008
26-570 | Lighting Control System | 0 | 0 |  | 0 |  |  |  | 0 | 0 | [12 empty] | 0
27-000 | Communications
27-410 | AV Systems/Structured Wire Allow. | 56029 | 0 |  | 56029 | 10434 |  |  | 10434 | 0 | [12 empty] | 45595
28-000 | Electronic Safety & Security
28-070 | Security System Allowance | 2750 | 0 |  | 2750 |  |  |  | 0 | 0 | [12 empty] | 2750
50-050 | Contingency | 54188 | 2250 | CO1 $2250 | 56438 |  |  |  | 0 | 0 | [12 empty] | 56438
| Arch/Engr Fees (Separate Agreement) | 500 | 0 |  | 500 |  |  |  | 0 | 0
| Contractor's Fee | 222700.14 | 7764.9012 | CO1 $7765 | 230465.0412 |  |  |  | 12597.3966 | 0 | [12 empty] | 217867.6446
| TOTALS | 1459923.14 | 50903.2412 |  | 1510826.3812 | 51985.5367 | 18000 | 0 | 82582.9333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1427743.4479

## LABOR JTD 3.7.2026
Wood Residence
2-2513
JTD Labor | 2026-03-07
Cost Code | Description | JTD Total Labor Hours | Billable Hours | Billing Rate | Total Billable Cost | Job Cost Report Total | Billing Difference
01-000 | GENERAL REQUIREMENTS
01-117 | Project Engineer Intern | 0 | 0 | 0 | 0 |  | 0
01-120 | Superintendent | 58.95 | 58.95 | 85 | 5010.75 | 4043.93 | 966.82
01-125 | Assistant Superintendent | 0 | 0 | 0 | 0 | 0 | 0
01-130 | Project Manager | 49 | 0 | 0 | 0 | 2943.25 | -2943.25
01-140 | Estimator | 116 | 0 | 0 | 0 | 6732.54 | -6732.54
01-170 | Travel/Pickup/Deliveries | 12 | 12 | 60 | 804 | 366.09 | 437.91
| from 18-030 | 7 | 7
01-560 | Temp Barriers/Enclosures | 59.43 | 59.43 | 60 | 4278.96 | 2010.58 | 2268.38
| from 18-030 | 12 | 12
01-740 | Cleaning & Waste Management | 6.94 | 6.94 | 60 | 527.44 | 117.98 | 409.46
| from 18-030 | 16 | 16
|  | 337.32 | 172.32 |  | 10621.15 | 16214.37
02-0000 | EXISTING CONDITIONS
02-010 | Demolition | 69.54 | 69.54 | 60 | 4698.8178 | 2104.69 | 2594.1278
| from 18-030 | 7.57 | 7.57
|  | 69.54 | 69.54 |  | 4698.8178 | 2104.69
00-0000 | PHASE
|  |  |  | 0 | 0 |  | 0
|  | 0 | 0 |  | 0 | 0
00-0000 | PHASE
|  |  |  | 0 | 0 |  | 0
|  | 0 | 0 |  | 0 | 0
00-0000 | PHASE
|  |  |  | 0 | 0 |  | 0
|  | 0 | 0 |  | 0 | 0