## FOR CONTRACT MATH
Updated Quote Comparison - Per Shop Drawing Review |  |  |  | FOR CONTRACT MATH
Wood Residence
2026-09-11
Budget | 168738 | cabinetry
| 28438 | closets
197176
|  | Subcontract/Original Budget | Updated Pricing | variance | WHY?
Kitchen |  | 57955 | 71315 | 13360 | air hinges at glass front cabinet doors, decorative moulding doors at fridge panels, maple dovetail drawer boxes, hardrock maple melamine interiors
Laundry |  | 21419 | 21993 | 574 | hardrock maple melamine interiors, dog bowl area details
Hearth Room/Dining |  | 18693 | 22209 | 3516 | upgraded to air hinges at see-thru, hardrock maple melamine interiors
Pantry |  | 5951 | 12297 | 6346 | upgraded to paint in lieu of melamine, hardrock maple melamine interiors, took uppers to the ceiling
Den |  | 15147 | 21925 | 6778 | hardrock maple melamine interiors, knee-space hidden cord storage
Primary Bath |  | 16819 | 19745 | 2926 | hardrock maple melamine interiors, maple dovetail drawer boxes
Hearth Room |  | 0 | 7620 | 7620 | hardrock maple interiors
ML Powder Bath |  | prefab | by owner, custom | 0
Bath 2 |  | 0 | 4779 | 4779 | hardrock maple melamine interiors
Bath 3 |  | 0 | 3053 | 3053 | hardrock maple melamine interiors
LL Powder Bath |  | prefab | resuse exist | 0
Bath 4 |  | prefab | prefab, by owner | 0
|  | 135984 | 184936 | 48952 | variance to contract
|  |  | 16198 | variance to budget
Primary Wardrobe |  | 24379 | 55479 | 31100 | upgraded design, changed to colored melamine color in lieu of standard white, dovetail drawer boxes
Coats Closet |  | 1055 | 1055 | 0
Guest Coats |  | 1619 | 1619 | 0
|  | 27053 | 58153 | 31100 | variance to contract
|  |  | 29715 | variance to budget
|  | 163037 | 243089 | 80052 | variance to contract
|  |  | 45913 | variance to budget
Original Quote (based on Subcontract)
| 179593 | Original Quote (what subcontract is based on)
| -1356 | less Bath 2
| -1321 | less Bath 3
| -1234 | less Bath 4
| -12645 | less Dining Buffet
| 163037 | SUBCONTRACT TOTAL
| 48952 | "final" cabinet shop dwg changes - per quote dated 8/6/2026
| 31100 | "final" primary wardrobe shop dwg changes - per quote dated 8/6/2026
| 243089 | SUBTOTAL
| -1619 | delete Guest Coats Closet
| -1055 | delete Coats Closet
| 240415 | CURRENT TOTAL
| 240415 | FINAL QUOTE TOTAL

## 8.5.2026
Updated Quote Comparison - Per Shop Drawing Review
Wood Residence
2026-08-05
Budget | 168738 | cabinetry
| 28438 | closets
197176
|  | Subcontract/Original Budget | Updated Pricing | variance | WHY?
Kitchen |  | 57955 | 71315 | 13360 | air hinges at glass front cabinet doors, decorative moulding doors at fridge panels, maple dovetail drawer boxes, hardrock maple melamine interiors
Laundry |  | 21419 | 21993 | 574 | hardrock maple melamine interiors, dog bowl area details
Hearth Room/Dining |  | 18693 | 23555 | 4862 | upgraded to air hinges at see-thru, hardrock maple melamine interiors
Pantry |  | 5951 | 12297 | 6346 | upgraded to paint in lieu of melamine, hardrock maple melamine interiors, took uppers to the ceiling
Den |  | 15147 | 21925 | 6778 | hardrock maple melamine interiors, knee-space hidden cord storage
Primary Bath |  | 16819 | 19745 | 2926 | hardrock maple melamine interiors, maple dovetail drawer boxes
Hearth Room |  | 9000 | 7620 | -1380 | hardrock maple interiors
ML Powder Bath |  | prefab | by owner, custom | 0
Bath 2 |  | 0 | 4779 | 4779 | hardrock maple melamine interiors
Bath 3 |  | 0 | 3053 | 3053 | hardrock maple melamine interiors
LL Powder Bath |  | prefab | resuse exist | 0
Bath 4 |  | prefab | prefab, by owner | 0
|  | 144984 | 186282 | 41298 | variance to contract
|  |  | 17544 | variance to budget
Primary Wardrobe |  | 24379 | 55479 | 31100 | upgraded design, changed to colored melamine color in lieu of standard white, dovetail drawer boxes
Coats Closet |  | 1055 | 1055 | 0
Guest Coats |  | 1619 | 1619 | 0
|  | 27053 | 58153 | 31100 | variance to contract
|  |  | 29715 | variance to budget
|  | 172037 | 244435 | 72398 | variance to contract
|  |  | 47259 | variance to budget

## 7.2.2026
Updated Quote Comparison - Per Shop Drawing Review
Wood Residence
2026-07-02
Budget | 168738 | cabinetry
| 28438 | closets
197176
|  | Subcontract | Updated Pricing | variance | WHY?
Kitchen |  | 57955 | 63591 | 5636 | air hinges - qty ?, decorative moulding doors at fridge panels
Laundry |  | 21419 | 21223 | -196
Hearth Room/Dining |  | 18693 | 20813 | 2120 | upgraded to air hinges at see-thru
Pantry |  | 5951 | 11933 | 5982 | changed to paint grade in lieu of originally melamine
Den |  | 15147 | 19651 | 4504 | ???????
Primary Bath |  | 16819 | 17157 | 338
Hearth Room |  | 0 | 7345 | 7345
ML Powder Bath |  | prefab | 1730 | 0
Bath 2 |  | 0 | 3929 | 3929
Bath 3 |  | 0 | 2815 | 2815
LL Powder Bath |  | prefab | resuse exist | 0
Bath 4 |  | prefab | prefab, by owner | 0
|  | 135984 | 170187 | 34203 | variance to contract
|  |  | 1449 | variance to budget
Primary Wardrobe |  | 24379 | 48447 | 24068 | changed to different design and material
Coats Closet |  | 1055 | 1055 | 0
Guest Coats |  | 1619 | 1619 | 0
|  | 27053 | 51121 | 24068 | variance to contract
|  |  | 22683 | variance to budget
|  | 163037 | 221308 | 58271 | variance to contract
|  |  | 24132 | variance to budget

## 8.5.2026+
Updated Quote Comparison - Per Shop Drawing Review
Wood Residence
2026-08-05
Budget | 168738 | cabinetry
| 28438 | closets
197176
|  | Subcontract | Updated Pricing 7/30 | variance | WHY?
Kitchen |  | 57955 | 71315 | 13360 | air hinges at glass front cabinet doors, decorative moulding doors at fridge panels, maple dovetail drawer boxes, hardrock maple melamine interiors
Laundry |  | 21419 | 21993 | 574 | hardrock maple melamine interiors, dog bowl area details
Hearth Room/Dining |  | 18693 | 23555 | 4862 | upgraded to air hinges at see-thru, hardrock maple melamine interiors
Pantry |  | 5951 | 12297 | 6346 | upgraded to paint in lieu of melamine, hardrock maple melamine interiors, took uppers to the ceiling
Den |  | 15147 | 21925 | 6778 | hardrock maple melamine interiors, knee-space hidden cord storage
Primary Bath |  | 16819 | 19745 | 2926 | hardrock maple melamine interiors, maple dovetail drawer boxes
Hearth Room |  | option | 7620 | 7620 | hardrock maple interiors
ML Powder Bath |  | prefab | by owner | 0
Bath 2 |  | option | 4779 | 4779 | hardrock maple melamine interiors
Bath 3 |  | option | 3053 | 3053 | hardrock maple melamine interiors
LL Powder Bath |  | prefab | existing | 0
Bath 4 |  | prefab | by owner | 0
|  | 135984 | 186282 | 50298 | variance to contract
Primary Wardrobe |  | 24379 | 55479 | 31100 | upgraded design, changed to colored melamine color in lieu of standard white, dovetail drawer boxes
Coats Closet |  | 1055 | 1055 | 0
Guest Coats |  | 1619 | 1619 | 0
|  | 27053 | 58153 | 31100 | variance to contract
|  | 163037 | 244435 | 81398 | variance to contract
|  |  | 47259 | variance to budget

## 7.2.2026+
Updated Quote Comparison - Per Shop Drawing Review
Wood Residence
2026-07-02
Budget | 168738 | cabinetry
| 28438 | closets
197176
|  | Subcontract | Updated Pricing 7/1 | variance | WHY?
Kitchen |  | 57955 | 63591 | 5636 | air hinges - qty ?, decorative moulding doors at fridge panels
Laundry |  | 21419 | 21223 | -196
Hearth Room/Dining |  | 18693 | 20813 | 2120 | upgraded to air hinges at see-thru
Pantry |  | 5951 | 11933 | 5982 | changed to paint grade in lieu of originally melamine
Den |  | 15147 | 19651 | 4504 | ???????
Primary Bath |  | 16819 | 17157 | 338
Hearth Room |  | 0 | 7345 | 7345
ML Powder Bath |  | prefab | by owner | 0
Bath 2 |  | option | 3929 | 3929
Bath 3 |  | option | 2815 | 2815
LL Powder Bath |  | prefab | existing | 0
Bath 4 |  | prefab | by owner | 0
|  | 135984 | 168457
Primary Wardrobe |  | 24379 | 48447 | 24068 | changed to different design and material
Coats Closet |  | 1055 | 1055 | 0
Guest Coats |  | 1619 | 1619 | 0
|  | 27053 | 51121
|  | 163037 | 219578 | 56541 | variance to contract
|  |  | 22402 | variance to budget