## PROJECT SUMMARY
PROJECT COST SUMMARY - PROJECTION
PROJECT | Hogan Residence
PROJECT MANAGER | [7 empty] | LOWER LEVEL | 2072
LOCATION | 811 N 143rd Plaza, Omaha, NE 68154 | [6 empty] | MAIN LEVEL | 2867
DATE | July 2026 | [6 empty] | TOTAL FINISHED SF | 4939
LOT # | 21 | [6 empty] | GARAGE | 756
ZONING | [7 empty] | LOWER UNFINISHED | 1567
[8 empty] | COVERED DECK | 362
[8 empty] | TOTAL SF UNDER ROOF | 7624
PHASE | DESCRIPTION | ALLOW. | LABOR | MATERIAL | OTHER | SUBCONT. | DIVISION | FINISHED COST/SF | UNDER ROOF
1 | GENERAL REQUIREMENTS |  |  |  |  | TOTAL | 154268 | 31.2347 | 20.2345
01.120 | Superintendent | 0 | 70125 | 0 | 0 | 0 | 70125 | 14.1982 | 9.1979
01.170 | Travel/Pickup/Deliveries | 0 | 0 | 0 | 3000 | 0 | 3000 | 0.60741 | 0.39349
01.205 | MUD Fees | 0 | 0 | 0 | 4350 | 0 | 4350 | 0.88075 | 0.57057
01.214 | Bldg. Permit | 0 | 0 | 0 | 6822 | 0 | 6822 | 1.3813 | 0.89481
01.230 | Builders Risk | 0 | 0 | 0 | 3096 | 0 | 3096 | 0.62685 | 0.40609
01.235 | General Liability | 0 | 0 | 0 | 5956 | 0 | 5956 | 1.2059 | 0.78122
01.452 | Testing/Inspections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
01.454 | Mockups | 0 | 1500 | 750 | 0 | 0 | 2250 | 0.45556 | 0.29512
01.501 | Temporary Utilities | 0 | 0 | 0 | 2719 | 5250 | 7969 | 1.6135 | 1.0453
01.538 | Technology | 0 | 0 | 0 | 1200 | 0 | 1200 | 0.24296 | 0.1574
01.540 | Equipment (Forklift/Skid Loader) | 0 | 0 | 0 | 1750 | 0 | 1750 | 0.35432 | 0.22954
01.560 | Temporary Barriers/Enclosures/Protection | 0 | 2400 | 750 | 0 | 0 | 3150 | 0.63778 | 0.41317
01.578 | Site Maintenance (Snow Removal/Mowing) | 0 | 900 | 0 | 0 | 0 | 900 | 0.18222 | 0.11805
01.740 | Cleaning & Waste Management (Dumpsters) | 0 | 10200 | 0 | 7125 | 4800 | 22125 | 4.4797 | 2.902
01.810 | Warranties | 0 | 0 | 0 | 12900 | 0 | 12900 | 2.6119 | 1.692
01.830 | Small Tools/Supply/Rentals | 0 | 0 | 0 | 2175 | 0 | 2175 | 0.44037 | 0.28528
01.840 | Punchlist | 0 | 6500 | 0 | 0 | 0 | 6500 | 1.3161 | 0.85257
2 | EXISTING CONDITIONS |  |  |  |  | TOTAL | 0 | 0 | 0
02.010 | Demolition | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CONCRETE |  |  |  |  | TOTAL | 120023 | 24.3011 | 15.7428
03.300 | Footings / Foundations | 0 | 0 | 0 | 450 | 92051 | 92501 | 18.7287 | 12.1329
03.320 | Interior Concrete Flatwork | 0 | 0 | 0 | 0 | 27522 | 27522 | 5.5724 | 3.6099
4 | MASONRY |  |  |  |  | TOTAL | 104892 | 21.2375 | 13.7581
04.210 | Brick Masonry / Precast Sills & Caps | 0 | 0 | 42942 | 0 | 59450 | 102392 | 20.7313 | 13.4302
04.220 | Concrete Unit Masonry (Blockwork) | 0 | 0 | 1150 | 0 | 1350 | 2500 | 0.50618 | 0.32791
04.430 | Stone Masonry / Precast Sills & Caps | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | METAL |  |  |  |  | TOTAL | 25311 | 5.1247 | 3.3199
05.120 | Structural Steel Material | 0 | 0 | 0 | 0 | 19581 | 19581 | 3.9646 | 2.5683
05.528 | Metal Interior Railing | 0 | 0 | 0 | 0 | 5250 | 5250 | 1.063 | 0.68861
05.530 | Exterior/Deck Railing | 0 | 0 | 0 | 0 | 480 | 480 | 0.097186 | 0.062959
05.700 | Decorative Metal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | CARPENTRY |  |  |  |  | TOTAL | 553429 | 112.0528 | 72.5904
06.110 | Wood Framing | 0 | 2850 | 89875 | 0 | 90000 | 182725 | 36.9964 | 23.9671
06.380 | Cabinetry Allowance | 210000 | 500 | 2800 | 0 | 0 | 213300 | 43.1869 | 27.9774
06.442 | Exterior Brackets/Timbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
06.460 | Wood Interior Trim / Stair Parts / Garage Step | 0 | 0 | 32404 | 0 | 65000 | 97404 | 19.7214 | 12.776
06.612 | Countertop Allowance | 60000 | 0 | 0 | 0 | 0 | 60000 | 12.1482 | 7.8699
7 | MOISTURE/THERMAL PROT. |  |  |  |  | TOTAL | 145661 | 29.492 | 19.1056
07.130 | Waterproofing/Passive Radon/Termite Treatment | 0 | 0 | 0 | 850 | 10420 | 11270 | 2.2818 | 1.4782
07.210 | Insulation | 0 | 0 | 0 | 0 | 20000 | 20000 | 4.0494 | 2.6233
07.250 | Stucco/EIFS System | 0 | 0 | 0 | 0 | 4800 | 4800 | 0.97186 | 0.62959
07.300 | Roofing | 0 | 0 | 0 | 0 | 83700 | 83700 | 16.9468 | 10.9785
07.455 | Siding | 0 | 0 | 2780 | 188 | 3440 | 6408 | 1.2974 | 0.8405
07.469 | Exterior Carsiding | 0 | 0 | 2883 | 0 | 2200 | 5083 | 1.0292 | 0.66671
07.600 | Flashing/Brick Ledge | 0 | 0 | 0 | 0 | 2050 | 2050 | 0.41506 | 0.26889
07.630 | Gutters/Downspouts | 0 | 0 | 0 | 0 | 6600 | 6600 | 1.3363 | 0.86569
07.920 | Joint Sealants | 0 | 0 | 0 | 0 | 5750 | 5750 | 1.1642 | 0.7542
8 | DOORS & WINDOWS |  |  |  |  | TOTAL | 99058 | 20.0563 | 12.9929
08.140 | Interior Wood Doors | 0 | 0 | 0 | 17938 | 0 | 17938 | 3.6319 | 2.3528
08.178 | Front Door | 18500 | 750 | 0 | 0 | 0 | 19250 | 3.8976 | 2.5249
08.385 | Garage Doors | 0 | 0 | 0 | 0 | 6800 | 6800 | 1.3768 | 0.89192
08.500 | Windows (Pella Lifestyle) | 0 | 0 | 0 | 750 | 40300 | 41050 | 8.3114 | 5.3843
08.600 | Roof Window/Skylights/Sun Tunnel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
08.817 | Mirrors/Glass Inserts/Shower Doors | 14020 | 0 | 0 | 0 | 0 | 14020 | 2.8386 | 1.8389
9 | FINISHES |  |  |  |  | TOTAL | 238603 | 48.31 | 31.2963
09.200 | Drywall | 0 | 0 | 0 | 1200 | 42613 | 43813 | 8.8708 | 5.7467
09.300 | Tile Allowance
| Floor Tile | 66517 | 0 | 0 | 0 | 0 | 66517 | 13.4677 | 8.7247
| Wall Tile/Columns | 2106 | 0 | 0 | 0 | 0 | 2106 | 0.4264 | 0.27623
| Tile Backsplash | 5320 | 0 | 0 | 0 | 0 | 5320 | 1.0771 | 0.6978
| Shower/Tub Tile | 22286 | 0 | 0 | 0 | 0 | 22286 | 4.5122 | 2.9231
09.640 | Wood/LVP/LVT Flooring Allowance | 3485 | 0 | 0 | 0 | 0 | 3485 | 0.70561 | 0.45711
09.657 | Fitness Room Carpet Tile | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
09.672 | Epoxy Flooring | option | 0 | 0 | 0 | 0 | 0 | 0 | 0
09.680 | Carpet Allowance | 25076 | 0 | 0 | 0 | 0 | 25076 | 5.0771 | 3.2891
09.720 | Wall Coverings/Faux Finishing | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
09.910 | Painting | 0 | 0 | 0 | 0 | 70000 | 70000 | 14.1729 | 9.1815
10 | SPECIALTIES |  |  |  |  | TOTAL | 99447 | 20.135 | 13.0439
10.050 | Finish Hardware Allowance | 15172 | 5200 | 0 | 0 | 0 | 20372 | 4.1247 | 2.6721
10.140 | Address Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.310 | Fireplaces / Chimney Pot | 0 | 400 | 5260 | 0 | 23957 | 29617 | 5.9966 | 3.8847
10.314 | Fireplace Facings Allowance | 16356 | 0 | 0 | 0 | 0 | 16356 | 3.3116 | 2.1453
10.552 | Mailbox | 850 | 0 | 0 | 0 | 0 | 850 | 0.1721 | 0.11149
10.562 | Storage Shelving | 0 | 240 | 300 | 0 | 0 | 540 | 0.10933 | 0.070829
10.572 | Closet Systems Allowance | 31712 | 0 | 0 | 0 | 0 | 31712 | 6.4207 | 4.1595
11 | EQUIPMENT |  |  |  |  | TOTAL | 66844 | 13.5339 | 8.7676
11.3 | Appliance Allowance | 66344 | 500 | 0 | 0 | 0 | 66844 | 13.5339 | 8.7676
11.52 | TV's Allowance | option | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | FURNISHINGS |  |  |  |  | TOTAL | 0 | 0 | 0
12.170 | Art Glass | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.200 | Window Treatments | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.250 | Motorized Shades | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | SPECIAL CONSTRUCTION |  |  |  |  | TOTAL | 3500 | 0.70865 | 0.45908
13.342 | Covered Patio Sunshade | 3500 | 0 | 0 | 0 | 0 | 3500 | 0.70865 | 0.45908
14 | CONVEYING SYSTEMS |  |  |  |  | TOTAL | 0 | 0 | 0
14.050 | Elevator (rough-in only, future) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22-23 | PLUMBING/HVAC SYSTEMS |  |  |  |  | TOTAL | 150700 | 30.5122 | 19.7665
22.050 | Plumbing | 0 | 0 | 0 | 0 | 55100 | 55100 | 11.1561 | 7.2272
22.322 | Water Filtration System Allowance | option | 0 | 0 | 0 | 0 | 0 | 0 | 0
22.400 | Plumbing Fixtures Allowance | 33900 | 0 | 0 | 0 | 0 | 33900 | 6.8637 | 4.4465
23.050 | HVAC | 0 | 0 | 0 | 4900 | 55300 | 60200 | 12.1887 | 7.8961
23.400 | Duct Cleaning | 0 | 0 | 0 | 0 | 1500 | 1500 | 0.30371 | 0.19675
26-28 | ELECTRICAL & LOW VOLTAGE |  |  |  |  | TOTAL | 188047 | 38.0739 | 24.6651
26.050 | Electrical Service & Wiring | 0 | 0 | 0 | 0 | 75000 | 75000 | 15.1853 | 9.8374
26.410 | Lightning Protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26.505 | Light Fixtures Allowance | 45047 | 0 | 0 | 0 | 0 | 45047 | 9.1207 | 5.9086
26.570 | Lighting Control System Allowance | option | 0 | 0 | 0 | 0 | 0 | 0 | 0
27.410 | AV Systems Pre-Wire/Sound System Allowance | 62500 | 0 | 0 | 0 | 0 | 62500 | 12.6544 | 8.1978
28.070 | Security System/Fire Protect./Video Surv. Allowance | 5500 | 0 | 0 | 0 | 0 | 5500 | 1.1136 | 0.72141
31-32 | EARTHWORK & EXTERIOR IMPROVEMENTS |  |  |  |  | TOTAL | 250583 | 50.7356 | 32.8677
31.128 | Site Demolition | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31.230 | Excavation/Fill/Grading/Silt Fence | 0 | 0 | 0 | 4500 | 22500 | 27000 | 5.4667 | 3.5414
31.260 | Surveying | 0 | 0 | 0 | 0 | 1500 | 1500 | 0.30371 | 0.19675
32.130 | Exterior Concrete Flatwork | 0 | 0 | 0 | 0 | 14680 | 14680 | 2.9723 | 1.9255
32.931 | Landscaping Allowance
| Plantings & Beds | 47500 | 0 | 0 | 0 | 0 | 47500 | 9.6173 | 6.2303
| Paver Allowance | 33827 | 0 | 0 | 0 | 0 | 33827 | 6.849 | 4.4369
| Retaining Walls Allowance | 50000 | 0 | 0 | 0 | 0 | 50000 | 10.1235 | 6.5582
| Landscape Lighting Allowance | 12000 | 0 | 0 | 0 | 0 | 12000 | 2.4296 | 1.574
| Irrigation Allowance | 6500 | 0 | 0 | 0 | 0 | 6500 | 1.3161 | 0.85257
| Seeding/Sod Allowance | 2062 | 0 | 0 | 0 | 0 | 2062 | 0.41749 | 0.27046
| Underground Buried Drainage Allowance | 35000 | 0 | 0 | 0 | 0 | 35000 | 7.0865 | 4.5908
32.310 | Fences/Gates | 0 | 0 | 0 | 0 | 20514 | 20514 | 4.1535 | 2.6907
33 | UTILITIES |  |  |  |  | TOTAL | 10000 | 2.0247 | 1.3116
33.020 | Water/Sewer Utilities | 0 | 0 | 0 | 0 | 10000 | 10000 | 2.0247 | 1.3116
50 | CONTIGENCY |  |  |  |  | TOTAL | 22000 | 4.4543 | 2.8856
50.050 | Contigency | 22000 | 0 | 0 | 0 | 0 | 22000 | 4.4543 | 2.8856
50.070 | Arch/Engr Fees (Separate Agreement) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 917080 | 102065 | 181894 | 81869 | 949458 | 2567220.9 | 519.7856 | 336.7289
McNeil Company Builders
PROJECT COST SUMMARY---MARKUP ANALYSIS
Project: | Hogan Residence
Location: | 811 N 143rd Plaza, Omaha, NE 68154 | [5 empty] | LOWER LEVEL | 2072
Date: | July 2026 | [5 empty] | MAIN LEVEL | 2867
Lot: | 21 | [5 empty] | TOTAL FINISHED SF | 4939
[7 empty] | GARAGE | 756
[7 empty] | LOWER UNFINISHED | 1567
[7 empty] | COVERED DECK | 362
[7 empty] | TOTAL SF UNDER ROOF | 7624
MARKUP ADJUSTMENTS
ACTUAL COST
[6 empty] | Allowances |  | 917080
[6 empty] | Labor |  | 102065
[6 empty] | Material |  | 181894
[6 empty] | Other |  | 81869
[6 empty] | Subcontractor |  | 949458
[6 empty] | NO MARKUP TOTAL |  | 2232366
[6 empty] | MARKUP PERCENTAGE |  | 15%
[6 empty] | MARKUP |  | 334854.9
[6 empty] | BID |  | 2567220.9

## DIV 1 GC
01.000 | GENERAL CONDITIONS
1.12 | Superintendent
|  |  | PROJECT DURATION - MONTHS | APPROX. HOURS/DAY | HOURS/WEEK | RATE/HOUR | COST/WEEK | PROJECT DURATION - WEEKS | TOTAL
|  | minimal supervision at start 3 wks | 16 | 3 | 15 | 85 | 1275 | 55 | 70125
1.17 | Travel/Pickup/Deliveries
| Rates updated March 2026 | [6 empty] | TOTAL | 3000
|  |  |  | Labor |  | 50 | 60 | HR | 3000
1.205 | MUD Fees
| Rates updated March 2026 (based on Schachne) |  |  |  | TOTAL | 4350
| 1" Capital Facilities Charge (Impact Fee) |  |  | 1 | 3200 | 3200
| 1" Meter Install |  |  | 1 | 500 | 500
| Water Tap |  |  | 1 | 650 | 650
1.214 | Bldg. Permit
| Rates updated March 2026 | [6 empty] | TOTAL | 0
City of Omaha
https://permits.cityofomaha.org/fees
| $1.00-$2,000 |  | 41 |  |  |  | 0 | 41 | 0
| $2,000-$25,000 |  | $41.00 for first $2,000, plus $9.53 for each additional $1,000 |  |  |  | 0 | 41 | 0
[7 empty] | 0 | 9.53 | 0
| $25,001-$50,000 |  | $260.19 for first $25,000, plus $6.44 for each additional $1,000 |  |  |  | 0 | 260.19 | 0
[7 empty] | 0 | 6.44 | 0
| $50,001-$100,000 |  | $421.19 for first $50,000, plus $3.19 for each additional $1,000 |  |  |  | 0 | 421.19 | 0
[7 empty] | 0 | 3.19 | 0
| $100,001-$500,000 |  | $580.69 for first $100,000, plus $2.78 for each additional $1,000 |  |  |  | 0 | 580.69 | 0
[7 empty] | 0 | 2.78 | 0
| $500,001-$1,000,000 |  | $1,692.69 for first $500,000, plus $2.37 for each additional $1,000 |  |  |  | 0 | 1692.69 | 0
[7 empty] | 0 | 2.37 | 0
| $1,000,001 and up |  | $2877.69 for first $1,000,000, plus $1.96 for each additional $1,000 |  |  |  | 0 | 1000000 | 0
[7 empty] | 0 | 1.96 | 0
City of Blair
https://www.blairne.gov/DocumentCenter/View/52/Building-Permit-and-Zoning-Fees-PDF
| Finished SF (not including finished basement) |  |  | 0 | * | 102 | 0
| Finished Basement SF |  |  | 0 | * | 62 | 0
| Unfinished Basement SF |  |  | 0 | * | 32 | 0
| Garage SF |  |  | 0 | * | 30 | 0
0
[6 empty] | Multiply by .006 | 0.006
[6 empty] | Total | 0
1.23 | Builders Risk
[8 empty] | TOTAL | 0
| Builders Risk (0.144/100 cost) |  |  |  |  | 0 | 0.144 |  | 0
| Misc. |  |  |  |  | 0 |  |  | 0
1.235 | General Liability
[8 empty] | TOTAL | 0
| Liability (2.77/1000 cost) |  |  |  |  | 0 | 2.77 |  | 0
| Bond |  |  |  |  | 0 |  |  | 0
| Misc. |  |  |  |  | 0 |  |  | 0
1.452 | Testing/Inspections
[8 empty] | TOTAL | 0
| Soil Testing |  |  |  |  | 0 | 1500 |  | 0
| Call back after excavation for visual inspection |  |  |  |  | 0 | 200 |  | 0
1.454 | Mockups
[8 empty] | TOTAL | 2250
|  |  |  | Labor |  | 25 | 60 | HR | 1500
|  |  |  | Materials |  | 1 | 500 | EA | 750
1.501 | Temporary Utilities
| Rates updated March 2026 | [6 empty] | TOTAL | 7968.8
| Temp Power Service |  | OPPD |  |  | 15 | 150 | /MONTH | 2250
| Temp Gas / Water Service |  | MUD |  |  | 12 | 250 | /MONTH | 3000
| Temp Heat for Interior |  | Labor / Material |  |  | 1 | 350 | ALLOWANCE | 350
| Temp Heat for Exterior |  | Labor / Material |  |  | 1 | 400 | ALLOWANCE | 400
| Portable Toilet |  | Eagle Services |  | Monthly Charge (includes tax) | 15 | 128.4 | /MONTH | 1926
[5 empty] | Delivery & Pickup (inlcudes tax) | 2 | 21.4 | /MONTH | 42.8
1.538 | Technology
| Rates updated March 2026 | [6 empty] | TOTAL | 1200
[5 empty] | Equipment | 1 | 1200 | /JOB | 1200
1.54 | Equipment (Forklift/Skid Loader)
| Rates updated March 2026 | [6 empty] | TOTAL | 1750
[5 empty] | Equipment | 1 | 1750 | /JOB | 1750
1.56 | Temporary Barries/Enclosures
| Rates updated March 2026 | [6 empty] | TOTAL | 3150
|  |  |  | Material |  | 1 | 750 | EA | 750
|  |  |  | Labor | (2 guys at $60/hr) | 20 | 120 | HR | 2400
|  |  |  | Subcontract |  | 0 | 4500 | EA | 0
1.578 | Site Maintenance
| Rates updated March 2026 | [6 empty] | TOTAL | 900
| Snow Removal |  |  | Labor |  | 5 | 60 | HR | 300
| Mowing/Spraying/Weedeating |  |  | Labor |  | 10 | 60 | HR | 600
1.74 | Cleaning & Waste Management
| Rates updated March 2026 | [6 empty] | TOTAL | 22125
|  |  | Interim Clean | Labor | 3 hrs/week | 170 | 60 | HR | 10200
|  |  | Final Clean | Labor |  | 0 | 60 | HR | 0
|  |  | Final Clean | Subcontract |  | 1 | 4800 | EA | 4800
|  |  | Window Clean | Subcontract | 2-story | 0 | 1200 | EA | 0
|  |  | Window Clean | Subcontract | Ranch | 0 | 750 | EA | 0
|  |  | Dumpsters | Other | S2 | 19 | 375 | /MONTH | 7125
Excludes drywall in phase
1.81 | Warranties
| Warranty Historical |  |  | Own | McNeil | 0 | 0.006 | /TOTAL/COST | 0
1.83 | Small Tools/Supply/Rent
| Rates updated March 2026 | [6 empty] | TOTAL | 2175
[5 empty] | Tools/Supplies | 1 | 2000 | /JOB | 2000
[5 empty] | Floor Sander | 1 | 175 | /JOB | 175
[5 empty] | Other Equipment | 0 | 250 | /JOB | 0
1.84 | Punchlist
| Rates updated March 2026 | [6 empty] | TOTAL | 2250
[5 empty] | Labor | 1 | 2250 | /JOB | 2250

## DIV 2 EXIST. COND.
02.000 | EXISTING CONDITIONS
2.01 | Demolition
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 3 CONCRETE
03.000 | CONCRETE
3.3 | Footings/Foundations
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
3.32 | Interior Concrete Flatwork
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
Unit Rate Estimate - rates updated March of 2026
Lower Level Slab |  | 0 | sf
Garage Slab |  | 0 | sf
|  | 0 | sf
MATERIAL
Poly (LL & GARAGE SLAB SF x 1.15 = sf) |  |  |  | 0 | 0.075 | SF | 0
Lower Level Slab Granular (LL SF x .33ft x 1.25 / 18 = tons) |  |  |  | 0 | 22 | TON | 0
Garage Slab Granular (GARAGE SF x .33ft x 1.25 / 18 = tons) |  |  |  | 0 | 22 | TON | 0
Additive (Xypex for water impermeable) |  |  |  | 0 | 131.85 | BOX | 0
Expansion Joints at Walls |  |  | ls | 0 | 125 | EA | 0
SUBCONTRACTOR
Lower Level Slab |  |  |  | 0 | 6.75 | SF | 0
Poly install |  |  |  | 0 | 0.35 | SF | 0
Step Down (form charge) |  |  |  | 0 | 10 | LF | 0
Garage Slab |  |  |  | 0 | 6.75 | SF | 0
Saw Cut slabs |  |  |  | 0 | 0.05 | SF | 0
Grading |  |  |  | 0 | 0.25 | SF | 0
Pump charge |  |  |  | 0 | 1700 | EA | 0
Cure & Seal |  |  |  | 0 | 0.12 | SF | 0
[6 empty] | TOTAL | 0

## DIV 4 MASONRY
04.000 | MASONRY
4.21 | Brick / Precast Sills & Caps
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
Unit Rate Estimate - rates updated March of 2026
Brick (Modular) |  | 0 | SF | 7 | 0 | brick ea
Soldiers/Rowblocks |  | 0 | LF | 3.5 | 0 | brick ea
Approx. per 292lf |  |  |  | RAW QTY BRICK | 0 | brick ea
|  |  |  | 12% WASTE FACTOR | 0 | brick ea
|  |  |  | TOTAL | 0 | brick ea
*adjust brick/cube quantity based on brick size |  |  |  | Qty of Full Cubes | 525 | brick/cube
|  |  |  | TOTAL | 0 | total cubes
Per Laura at Watkins:
125 brick/bag of masonry for this product
premix mortar - 35-40 brick/bag on modular / 30-32 brick per bag oversize
MATERIAL
Brick (modular) |  |  |  | 0 | 0.95 | 0
Brick (solids) |  |  |  | 0 | 1.5 | 0
premix mortar (colored) |  |  |  | 0 | 14.45 | 0
premix mortar (standard gray) |  |  |  | 0 | 9.5 | 0
Masonry Cement |  | 7 bags/M |  | 0 | 11 | 0
Portland Cement |  | 1 bag/5 of masonry |  | 0 | 14 | 0
Sand |  | 3 to 1 by weight |  | 0 | 15 | 0
Weep Holes |  | approx. every 3lf |  | 0 | 0.65 | 0
Nervastral |  | 12"x150'/roll |  | 0 | 90 | 0
SureKlean #600 detergent |  | 600sf/gallon |  | 0 | 25 | 0
Ties |  | .10 ties per brick |  | 0 | 0.35 | 0
1" Mortar Net |  |  |  | 0 | 2.4 | 0
Misc. Tools |  |  |  | 0 | 200 | 0
Pallet charge |  |  |  | 0 | 28 | 0
freight/delivery |  |  |  | 0 | 75 | 0
[5 empty] | SUBTOTAL | 0
[5 empty] | 7% TAX | 0
[5 empty] | TOTAL | 0
4.22 | Concrete Masonry Units (Blockwork)
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
4.43 | Stone Masonry / Precast Sills & Caps
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
Unit Rate Estimate - rates updated March of 2026
Thin Stone Flats |  | 0 | SF | 12% waste factor | 0 | stone sf
Thin Stone Corners |  | 0 | LF | 12% waste factor | 0 | stone sf
Approx. per 292lf |  |  |  | TOTAL | 0 | stone sf
Full Bed Depth Stone |  | 0 | SF | 12% waste factor | 0 | stone sf
Approx. per 292lf |  |  |  | TOTAL | 0 | stone sf
|  |  |  | Approximate ton qty | 38 | sf/ton
|  |  |  | TOTAL | 0 | tons
per Laura at Watkins:
thin stone mortar coverage - Promix 70lb bag is 15sf/bag for joints; 7sf/bag for scratch coat
full bed depth stone mortar coverage - depends on stone size, but 7-10sf/bag gets close
german schmear style mortar coverage - depends on heaviness of schmear
approximate sf/ton for full bed depth stone - 38-40sf/ton
MATERIAL
Thin Stone Flats |  | $/sf |  | 0 | 12 | 0
Thin Stone Corners |  | $/each |  | 0 | 18 | 0
Full Bed Depth Stone |  | $/ton |  | 0 | 500 | 0
Premix Mortar (colored) |  |  |  | 0 | 14.45 | 0
Premix Mortar (standard gray) |  |  |  | 0 | 13.8 | 0
Scratch coat mortar |  |  |  | 0 | 13.8 | 0
Metal Lathe |  | 27"x96", assume 16sf with overlap |  | 0 | 14.1 | 0
Felt |  | 200sf/roll |  | 0 | 35 | 0
Lathe Bottom Weep Screed |  | assume 10' |  | 0 | 17 | 0
Rainscreen, Keene |  | 4'x65' |  | 0 | 10 | 0
Masonry Cement |  | 7 bags/M |  | 0 | 11 | 0
Portland Cement |  | 1 bag/5 of masonry |  | 0 | 14 | 0
Sand |  | 3 to 1 by weight |  | 0 | 15 | 0
Weep Holes |  | approx. every 3lf |  | 0 | 0.65 | 0
Nervastral |  | 12"x150'/roll |  | 0 | 90 | 0
SureKlean #600 detergent |  | 600sf/gallon |  | 0 | 25 | 0
Ties |  | .10 ties per brick |  | 0 | 0.35 | 0
1" Mortar Net |  |  |  | 0 | 2.4 | 0
Misc. Tools |  |  |  | 0 | 200 | 0
Pallet charge |  | approx. 150-200sf/pallet |  | 0 | 28 | 0
freight/delivery |  |  |  | 0 | 75 | 0
[5 empty] | SUBTOTAL | 0
[5 empty] | 7% TAX | 0
[5 empty] | TOTAL | 0

## DIV 5 METAL
05.000 | METAL
5.12 | Strucutural Steel - Material
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
5.528 | Metal Interior Railing
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
5.53 | Exterior Deck Railing
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
5.7 | Decorative Metal
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 6 CARPENTRY
06.000 | CARPENTRY
6.11 | Wood Framing
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
6.15 | Wood Decks
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
6.38 | Cabinetry
|  |  |  | Company | Company | Company | Company
Main Level
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
Lower Level
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
Upper Level
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
6.442 | Exterior Brackets/Timbers
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
6.46 | Wood Interior Trim
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
Unit Rate Estimate
| DESCRIPTION |  | SPECIES | QTY | UNIT PRICE | SUBTOTAL | NOTES
BASE AND CASING
| 3" Casing |  |  | 0 | 0 | 0
| 3 1/2" Casing |  |  | 0 | 0 | 0
| 4" Casing |  |  | 0 | 0 | 0
| 3" Base (Mechanical Rooms) |  |  | 0 | 0 | 0
| 4" Base |  |  | 0 | 0 | 0
| 6" Base |  |  | 0 | 0 | 0
| 8" Base |  |  | 0 | 0 | 0
| PVC Base - Azek (Garage) |  |  | 0 | 0 | 0
| Base Shoe |  |  | 0 | 0 | 0
| Window Jamb Extensions |  |  | 0 | 0 | 0
| Tooling/Setup Charge |  |  | 0 | 500 | 0
CASING DETAILS
| 1 1/2" bn |  |  | 0 | 0 | 0
| 1 x 6 S4S (for jamb) |  |  | 0 | 0 | 0
| stop |  |  | 0 | 0 | 0
| glass mullion (to match door profile) |  |  | 0 | 0 | 0
| backband (for front door) |  |  | 0 | 0 | 0
| Mullcenter (double door) |  |  | 0 | 0 | 0
| 1 x 4 S4S window stools |  |  | 0 | 0 | 0
| set up/freight for glass mullions |  |  | 0 | 0 | 0
CROWN MOLDING
| 6" CROWN |  |  | 0 | 0 | 0
| Built-Up Band |  |  | 0 | 0 | 0
| 1 x 4 S4S (backing material) |  |  | 0 | 0 | 0
BEAMS
| Industrial Board (structure) |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
DETAIL
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
DETAIL
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
DETAIL
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
STAIR PARTS
| Newel Posts |  |  | 0 | 0 | 0
| Wood Railing |  |  | 0 | 0 | 0
| Balusters |  |  | 0 | 0 | 0
| 1x12 skirt boards |  |  | 0 | 0 | 0
| 4" casing skirt board cap |  |  | 0 | 0 | 0
| 1/2x12 End Cap Treads |  |  | 0 | 0 | 0
| 1/2x8 End Cap Risers |  |  | 0 | 0 | 0
| Planing Charge |  |  | 0 | 0 | 0
| End Cap & Balcony Nosing |  |  | 0 | 0 | 0
MISC. TRIM DETAILS
| Glue, shims, fasteners, blades |  |  | 0 | 750 | 0
| Delivery |  |  | 0 | 150 | 0
[5 empty] | subtotal | 0
[5 empty] | 7% tax | 0
[5 empty] | TOTAL | 0
6.612 | Countertop Allowance
|  |  |  | Company | Company | Company | Company
Main Level
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
Lower Level
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
Upper Level
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0

## DIV 7 MOISTURE PROTECTION
07.000 | MOISTURE/THERMAL PROTECTION
7.13 | Waterproofing/Passive Radon/Termite Treatment
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.21 | Insulation
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.25 | Stucco System
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.3 | Roofing
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.455 | Siding
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.469 | Exterior Carsiding
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.6 | Flashing/Brickledge
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.63 | Gutters/Downspouts
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.92 | Joint Sealants
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 8 OPENINGS
08.000 | OPENINGS
8.14 | Interior Wood Doors
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.178 | Front Door
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.184 | Pet Door
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.385 | Garage Doors
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.5 | Windows
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.6 | Roof Windows/Skylights/Sun Tunnel
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.817 | Mirrors/Glass Inserts/Shower Doors
|  |  |  | Company | Company | Company | Company
Main Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
Lower Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
Upper Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
1
2
3
4
5
6
7
8
9 | Install
10 | McNeil Company Wood Backer Supply/Install
|  |  | TOTAL | 0 | 0 | 0 | 0

## DIV 9 FINISHES
09.000 | FINISHES
9.2 | Drywall
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
9.3 | Tile
Floor Tile
[8 empty] | TOTAL | 0
| Location | [7 empty] | 0
|  |  |  | Tile Material | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 75 | EA | 0
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Self Leveling | ALLOWANCE | 0 | 5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Tile Material | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 75 | EA | 0
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Self Leveling | ALLOWANCE | 0 | 5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Tile Material | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 75 | EA | 0
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Self Leveling | ALLOWANCE | 0 | 5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Tile Material | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 75 | EA | 0
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Self Leveling | ALLOWANCE | 0 | 5 | SF | 0
|  |  |  | In-Floor Heat | ALLOWANCE | 0 | 20 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Tile Material | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 75 | EA | 0
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Anti-fracture Membrane | ALLOWANCE | 0 | 2 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Tile Material | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 75 | EA | 0
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Anti-fracture Membrane | ALLOWANCE | 0 | 2 | SF | 0
Tile Backsplash
[8 empty] | TOTAL | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Deco | ALLOWANCE | 0 | 275 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 32 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 50 | EA | 0
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Deco | ALLOWANCE | 0 | 275 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 32 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 50 | EA | 0
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Deco | ALLOWANCE | 0 | 275 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 32 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 50 | EA | 0
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Deco | ALLOWANCE | 0 | 275 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 32 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 50 | EA | 0
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Deco | ALLOWANCE | 0 | 275 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 32 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 50 | EA | 0
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
Wall Tile/Columns
[8 empty] | TOTAL | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 35 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 32 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 50 | EA | 0
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
Shower/Tub Tile
[8 empty] | TOTAL | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 12 | SF | 0
|  |  |  | Deco Tile | ALLOWANCE | 0 | 400 | EA | 0
|  |  |  | Ceiling Tile | ALLOWANCE | 0 | 12 | SF | 0
|  |  |  | Floor Tile | ALLOWANCE | 0 | 20 | SF | 0
|  |  |  | Bullnose | ALLOWANCE | 0 | 15 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Miter Outside Corners - Addt'l Cost | ALLOWANCE | 0 | 300 | EA | 0
|  |  |  | Labor - install seat, shelves, jamb and/or curb | ALLOWANCE | 0 | 1000 | EA | 0
|  |  |  | Labor - floor | ALLOWANCE | 0 | 85 | SF | 0
|  |  |  | Tile Drain | ALLOWANCE | 0 | 150 | EA | 0
|  |  |  | Sealer/Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 100 | EA | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Deco Tile | ALLOWANCE | 0 | 400 | EA | 0
|  |  |  | Ceiling Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Floor Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Bullnose | ALLOWANCE | 0 | 15 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Labor - install shelves, curb | ALLOWANCE | 0 | 1000 | EA | 0
|  |  |  | Labor - floor | ALLOWANCE | 0 | 85 | SF | 0
|  |  |  | Tile Drain | ALLOWANCE | 0 | 150 | EA | 0
|  |  |  | Sealer/Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 100 | EA | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Deco Tile | ALLOWANCE | 0 | 400 | EA | 0
|  |  |  | Ceiling Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Floor Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Bullnose | ALLOWANCE | 0 | 15 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Labor - install shelves, curb | ALLOWANCE | 0 | 1000 | EA | 0
|  |  |  | Labor - floor | ALLOWANCE | 0 | 85 | SF | 0
|  |  |  | Tile Drain | ALLOWANCE | 0 | 150 | EA | 0
|  |  |  | Sealer/Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 100 | EA | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Deco Tile | ALLOWANCE | 0 | 400 | EA | 0
|  |  |  | Ceiling Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Floor Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Bullnose | ALLOWANCE | 0 | 15 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Labor - install shelves, curb | ALLOWANCE | 0 | 1000 | EA | 0
|  |  |  | Labor - floor | ALLOWANCE | 0 | 85 | SF | 0
|  |  |  | Tile Drain | ALLOWANCE | 0 | 150 | EA | 0
|  |  |  | Sealer/Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 100 | EA | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Deco Tile | ALLOWANCE | 0 | 400 | EA | 0
|  |  |  | Ceiling Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Floor Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Bullnose | ALLOWANCE | 0 | 15 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Labor - install shelves, curb | ALLOWANCE | 0 | 1000 | EA | 0
|  |  |  | Labor - floor | ALLOWANCE | 0 | 85 | SF | 0
|  |  |  | Tile Drain | ALLOWANCE | 0 | 150 | EA | 0
|  |  |  | Sealer/Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 100 | EA | 0
9.64 | Wood Flooring / LVP / LVT Allowance
| WOOD FLOOR / LVP / LVT AREAS | [5 empty] | TOTAL | 0
| Main Level | 0 | SF
| Lower Level | 0 | SF
| Upper Level | 0 | SF
| Subtotal | 0 | SF
| 7% waste - typical | 0 | SF
| 15% waste - diagonal/herringbone | 0 | SF
| Total | 0 | SF
| Prefin. wood materials (range from $5.50-$12) |  |  | ALLOWANCE | 0 | 0 | SF | 0
| Wood Installation Labor |  |  | ALLOWANCE | 0 | 0 | SF | 0
| Wood Stair Labor |  |  | ALLOWANCE | 0 | 25 | EA | 0
| Wood Vents (Flush Mount) |  |  | ALLOWANCE | 0 | 122 | EA | 0
| Miscellanous Underlayment/Floor Prep |  |  | ALLOWANCE | 0 | 3 | SF | 0
| LVP / LVT materials |  |  | ALLOWANCE | 0 | 0 | SF | 0
| LVP / LVT Installation Labor |  |  | ALLOWANCE | 0 | 0 | SF | 0
| LVP / LVT Prep / Glue / Transitions |  |  | ALLOWANCE | 0 | 0 | SF | 0
NOTES:
per Timberland - use $10/sf allowance for prefinished wood
9.657 | Rubber Athletic Flooring Allowance
| AREAS | [5 empty] | TOTAL | 0
| Main Level | 0 | SF
| Lower Level | 0 | SF
| Upper Level | 0 | SF
| Subtotal | 0 | SF
| 7% waste | 0 | SF
| Total | 0 | SF
| Carpet Tile/Rubber Flooring Material |  |  | ALLOWANCE | 0 | 0 | SF | 0
| Installation Labor |  |  | ALLOWANCE | 0 | 0 | SF | 0
9.672 | Epoxy Flooring
| AREAS | [5 empty] | TOTAL | 0
| Garage | 0 | SF
| Mechanical/Storage | 0 | SF
| Mechanical/Storage | 0 | SF
| Subtotal | 0 | SF
| 7% waste | 0 | SF
| Total | 0 | SF
| Epoxy Flooring Material / Installation |  |  | ALLOWANCE | 0 | 6 | SF | 0
9.68 | Carpet Allowance
| AREAS |  |  |  |  | TOTAL | 0
| Main Level | 0 | SF
| Lower Level | 0 | SF
| Upper Level | 0 | SF
| Stairs (x2 for risers) | 0 | SF
| Total SF | 0 | SF
| Conversion to SY (X 1.30 / 9) | 0 | SY
| 12' Roll Layout - Actual | 0 | SY
ALLOWANCE BREAKDOWN
| Installation Labor |  |  |  | 8 | PER SY
| Carpet Pad (memory foam) |  |  |  | 8 | PER SY
| Material Allowance |  |  |  | 40 | PER SY
| Floor Prep / Tack Strip / Etc. |  |  |  | 1.5 | PER SY
| Carpet Material, Labor, and Pad |  | ALLOWANCE | 0 | 57.5 | SY | 0
| Walk Off Carpet |  | ALLOWANCE | 0 | 50 | SY | 0
| VCT (furnace room) |  | ALLOWANCE | 0 | 3 | SF | 0
| Additional Labor for Stair |  | ALLOWANCE | 0 | 30 | EA | 0
9.72 | Wall Coverings/Faux Finishing
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
9.91 | Painting
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0

## DIV 10 SPECIALTIES
10.000 | SPECIALTIES
10.05 | Finish Hardware Allowance
Cabinet Hardware
| POWDER BATH |  | DOORS/DRAWERS |  | 2 | 15 | 30
| SERVICE ENTRY |  | DOORS/DRAWERS |  | 10 | 12 | 120
|  |  | HOOKS |  | 6 | 35 | 210
| PRIMARY BATH |  | DOORS/DRAWERS |  | 25 | 15 | 375
| PRIMARY WARDROBE |  | DOORS/DRAWERS |  | 24 | 12 | 288
| GATHERING ROOM |  | DOORS/DRAWERS |  | 6 | 15 | 90
| KITCHEN ISLAND |  | DOORS/DRAWERS |  | 22 | 18 | 396
|  |  | APPLIANCE PULLS |  | 2 | 350 | 700
| KITCHEN |  | DOORS/DRAWERS |  | 34 | 18 | 612
|  |  | APPLIANCE PULLS |  | 3 | 350 | 1050
| PANTRY |  | OPEN SHELVES
| LOUNGE |  | DOORS/DRAWERS |  | 15 | 18 | 270
|  |  | APPLIANCE PULLS |  | 2 | 200 | 400
| LAUNDRY |  | DOORS/DRAWERS |  | 25 | 10 | 250
| OFFICE |  | DOORS/DRAWERS |  | 20 | 12 | 240
| BATHROOM 2 |  | DOORS/DRAWERS |  | 7 | 10 | 70
| BATHROOM 3 |  | DOORS/DRAWERS |  | 10 | 10 | 100
| LL BAR |  | DOORS/DRAWERS |  | 23 | 12 | 276
| LL FAMILY ROOM |  | DOORS/DRAWERS |  | 6 | 12 | 72
| GARAGE |  | DOORS/DRAWERS |  | 11 | 10 | 110
| OUTDOOR |  | DOORS/DRAWERS |  | 4 | 10 | 40
[6 empty] | SUBTOTAL | 5699
[6 empty] | FREIGHT | 100
[6 empty] | 7% TAX | 405.93
[6 empty] | TOTAL | 6204.93
Door Hardware
| LOCATION |  |  |  | QTY | UNIT COST | SUBTOTAL
Lower Level
| DOOR LEVERS (PASSAGE/PRIVACY) |  |  | Emtek | 11 | 190 | 2090
| DUMMIES |  |  | Emtek | 0 | 185 | 0
| POCKET DOOR |  |  | Emtek | 0 | 275 | 0
| 3 1/2" HINGES - per pair |  |  |  | 17 | 14 | 238
| 4" HINGES - per pair |  |  |  | 0 | 18 | 0
| HINGE DOOR STOP |  |  |  | 6 | 10 | 60
| BASE DOOR STOP |  |  |  | 8 | 15 | 120
Main Level
| FRONT DOOR HARDWARE |  |  |  | 1 | 650 | 650
| PATIO - MULTIPOINT |  |  | Emtek | 0 | 575 | 0
| DOOR LEVERS (PASSAGE/PRIVACY) |  |  | Emtek | 7 | 190 | 1330
| DEADBOLTS (AT GARAGE) |  |  | Emtek | 1 | 100 | 100
| DUMMIES |  |  | Emtek | 2 | 185 | 370
| POCKET DOOR |  |  | Emtek | 5 | 275 | 1375
| FLUSH BOLT @ OFFICE |  |  |  | 2 | 75 | 150
| SUMP CLOSET KNOBS |  |  |  | 1 | 25 | 25
| 3 1/2" HINGES - per pair |  |  |  | 0 | 14 | 0
| 4" HINGES - per pair |  |  |  | 18 | 18 | 324
| SPRING HINGE |  |  |  | 2 | 45 | 90
| HINGE DOOR STOP |  |  |  | 6 | 10 | 60
| BASE DOOR STOP |  |  |  | 6 | 15 | 90
| FLOOR STOP |  |  |  | 1 | 50 | 50
[6 empty] | SUBTOTAL | 7122
[6 empty] | FREIGHT | 100
[6 empty] | 7% TAX | 505.54
[6 empty] | TOTAL | 7727.54
Bath Accessories - PER BRIGGS QUOTE
POWDER BATH
|  |  | TOILET PAPER HOLDERS |  | 0 | 75 | 0
|  |  | TOWEL RINGS |  | 0 | 75 | 0
PRIMARY BATH
|  |  | TOILET PAPER HOLDERS |  | 0 | 75 | 0
|  |  | TOWEL BARS |  | 0 | 100 | 0
|  |  | TOWEL RINGS |  | 0 | 75 | 0
|  |  | ROBE HOOKS |  | 0 | 35 | 0
BATHROOM
|  |  | TOILET PAPER HOLDERS |  | 0 | 75 | 0
|  |  | TOWEL BAR |  | 0 | 100 | 0
|  |  | TOWEL RINGS |  | 0 | 75 | 0
|  |  | ROBE HOOKS |  | 0 | 35 | 0
BATHROOM
|  |  | TOILET PAPER HOLDERS |  | 0 | 75 | 0
|  |  | TOWEL BARS |  | 0 | 100 | 0
|  |  | TOWEL RINGS |  | 0 | 75 | 0
|  |  | ROBE HOOKS |  | 0 | 35 | 0
BATHROOM
|  |  | TOILET PAPER HOLDERS |  | 0 | 75 | 0
|  |  | TOWEL BARS |  | 0 | 100 | 0
|  |  | TOWEL RINGS |  | 0 | 75 | 0
|  |  | ROBE HOOKS |  | 0 | 35 | 0
[6 empty] | SUBTOTAL | 0
[6 empty] | FREIGHT | 0
[6 empty] | 7% TAX | 0
[6 empty] | PER BRIGGS QUOTE - TOTAL | 1240
[6 empty] | TOTAL ALL ACCESSORIES | 15172.47
[6 empty] | TOTAL LABOR | 5200
10.14 | Address Numbers
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
10.31 | Fireplaces
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
10.314 | Fireplace Facings
[6 empty] | TOTAL | 0
Location | [6 empty] | 0
|  | Field Material | ALLOWANCE | 0 | 0 | SF | 0
|  | Labor/Setting Materials | ALLOWANCE | 0 | 0 | SF | 0
|  | Delivery | ALLOWANCE | 0 | 0 | EA | 0
|  | Sealer | ALLOWANCE | 0 | 0 | SF | 0
|  | Precast Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Metal Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Labor - Surround | ALLOWANCE | 0 | 0 | EA | 0
Location | [6 empty] | 0
|  | Field Material | ALLOWANCE | 0 | 0 | SF | 0
|  | Labor/Setting Materials | ALLOWANCE | 0 | 0 | SF | 0
|  | Delivery | ALLOWANCE | 0 | 0 | EA | 0
|  | Sealer | ALLOWANCE | 0 | 0 | SF | 0
|  | Precast Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Metal Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Labor - Surround | ALLOWANCE | 0 | 0 | EA | 0
Location | [6 empty] | 0
|  | Field Material | ALLOWANCE | 0 | 0 | SF | 0
|  | Labor/Setting Materials | ALLOWANCE | 0 | 0 | SF | 0
|  | Delivery | ALLOWANCE | 0 | 0 | EA | 0
|  | Sealer | ALLOWANCE | 0 | 0 | SF | 0
|  | Precast Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Metal Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Labor - Surround | ALLOWANCE | 0 | 0 | EA | 0
10.562 | Storage Shelving
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
10.566 | Wine Cellar Racks/Cooling
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
10.572 | Closets
|  |  |  | Company | Company | Company | Company
Main Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
Lower Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
Upper Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
10.712 | Exterior Shutters
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0

## DIV 11 EQUIPMENT
11.000 | EQUIPMENT
11.302 | Appliances Allowance
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
11.52 | TV's Allowance
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
11.66 | Athletic Equipment
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
11.678 | Game Room Equipment (Golf Simulator)
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 12 FURNISHINGS
12.000 | FURNISHINGS
12.17 | Art Glass
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
12.2 | Window Treatments
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
12.25 | Motorized Shades
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 13 SPECIAL CONST.
13.000 | SPECIAL CONSTRUCTION
13.112 | Swimming Pool
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
13.174 | Sauna
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
13.26 | Storm Shelter Room(s)
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
13.342 | Screen Porch Systems
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 14 CONVEYING SYSTEMS
14.000 | CONVEYING SYSTEMS
14.05 | Elevators
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 21 FIRE SUPRESSION
21.000 | FIRE SUPPRESSION
21.05 | Fire Suppression
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 22-23 PLUM-HVAC
22.000 | PLUMBING
22.05 | Plumbing
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
22.322 | Water Filtration System
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
22.4 | Plumbing Fixtures Allowance
|  | QUANITITY | UNIT COST | SUBTOTAL
BATHROOM
| SINK SS | 0 | 100 | 0
| FAUCET | 0 | 250 | 0
| TOILET | 0 | 400 | 0
| SEAT/TRIP LEVER | 0 | 115 | 0
| SHOWER VALVE/TRIM | 0 | 450 | 0
| FIBERGLASS SHOWER BASE | 0 | 650 | 0
BAR
| SINK | 0 | 450 | 0
| FAUCET | 0 | 475 | 0
| RO FAUCET | 0 | 400 | 0
| AIR SWITCH | 0 | 125 | 0
| DISPOSAL | 0 | 175 | 0
| BASKET STRAINER | 0 | 70 | 0
KITCHEN
| SINK | 0 | 800 | 0
| FAUCET | 0 | 500 | 0
| RO FAUCET | 0 | 400 | 0
| SOAP DISPENSER | 0 | 150 | 0
| AIR SWITCH | 0 | 125 | 0
| DISPOSAL | 0 | 300 | 0
| BASKET STRAINER | 0 | 70 | 0
| POT FILLER | 0 | 700 | 0
POWDER BATH
| SINK | 0 | 175 | 0
| FAUCET | 0 | 400 | 0
| TOILET | 0 | 400 | 0
| SEAT/TRIP LEVER | 0 | 115 | 0
LAUNDRY
| SINK | 0 | 225 | 0
| FAUCET | 0 | 200 | 0
| BASKET STRAINER | 0 | 70 | 0
PRIMARY BATH
| SINK | 0 | 150 | 0
| FAUCETS | 0 | 400 | 0
| TOILET | 0 | 400 | 0
| SEAT/TRIP LEVER | 0 | 115 | 0
| BIDET SEAT | 0 | 1000 | 0
| SHOWER VALVE/TRIM | 0 | 1250 | 0
| WHIRLPOOL TUB | 0 | 4750 | 0
| TUB VALVE/FAUCET | 0 | 1000 | 0
GUEST BATH
| SINK | 0 | 100 | 0
| FAUCET | 0 | 250 | 0
| TOILET | 0 | 400 | 0
| SEAT/TRIP LEVER | 0 | 115 | 0
| SHOWER VALVE/TRIM | 0 | 450 | 0
| FIBERGLASS SHOWER BASE | 0 | 650 | 0
|  |  | SUBTOTAL | 0
|  |  | FREIGHT | 0
|  |  | 7% TAX | 0
|  |  | TOTAL | 0
23.000 | HVAC
23.05 | HVAC
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
23.4 | Duct Cleaning
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 26-28 ELEC. - LV
26.000 | ELECTRICAL
26.05 | Electrical Service & Wiring
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
26.41 | Lightning Protection
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
26.505 | Light Fixtures Allowance
*ALLOWANCE UNIT COSTS INCLUDE ALL BULBS
| LOCATION | TYPE |  | QTY | UNIT PRICE | SUBTOTAL
Main Level
| FOYER | CEILING MOUNT |  | 9 | 550 | 4950
| FOYER/STAIR | ART LIGHT |  | 1 | 675 | 675
| OFFICE | ART LIGHT |  | 3 | 525 | 1575
| POWDER BATH | WALL MOUNT |  | 1 | 1200 | 1200
| POWDER BATH | CEILING MOUNT |  | 1 | 2500 | 2500
| KITCHEN | PENDANTS |  | 3 | 1200 | 3600
| KITCHEN | WALL MOUNT |  | 2 | 1200 | 2400
| DINING | CEILING MOUNT |  | 1 | 5000 | 5000
| LOUNGE | CEILING MOUNT |  | 1 | 3000 | 3000
| GATHERING ROOM | CANS - by elect. |  | 0 | 0 | 0
| LAUNDRY ROOM | CANS - by elect. |  | 0 | 0 | 0
| PRIMARY BEDROOM | CEILING MOUNT |  | 1 | 3000 | 3000
| PRIMARY BATHROOM | WALL MOUNT |  | 4 | 1000 | 4000
| PRIMARY WARDROBE | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| LAUNDRY ROOM | CANS - by elect. |  | 0 | 0 | 0
| SERVICE ENTRY | CANS - by elect. |  | 0 | 0 | 0
| GARAGE | LED - by elect. |  | 0 | 0 | 0
Lower Level
| BATHROOM 2 VANITY | WALL MOUNT |  | 1 | 525 | 525
| BATHROOM 3 VANITY | WALL MOUNT |  | 1 | 525 | 525
| BEDROOM 2 | CANS - by elect. |  | 0 | 0 | 0
| BEDROOM 3 | CANS - by elect. |  | 0 | 0 | 0
| WARDROBE 2 | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| WARDROBE 3 | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| FITNESS ROOM | CEILING FAN |  | 1 | 475 | 475
| BILLIARDS | CEILING MOUNT |  | 3 | 750 | 2250
| LL FAMILY ROOM | CANS - by elect. |  | 0 | 0 | 0
| MECHANICAL/STORAGE | LED - by elect. |  | 0 | 0 | 0
EXTERIOR LIGHTING
| FRONT ENTRY | WALL MOUNT |  | 1 | 800 | 800
| WALL PIERS | BASE MOUNT |  | 3 | 1000 | 3000
| COVERED PATIO | CEILING FAN |  | 2 | 525 | 1050
| COVERED PATIO | WALL MOUNT |  | 3 | 525 | 1575
| FLOODS | WALL MOUNT - by elect. |  | 0 | 0 | 0
[5 empty] | SUBTOTAL | 42100
[5 empty] | FREIGHT | 0
[5 empty] | 7% TAX | 2947
[5 empty] | TOTAL (INCLUDING BULBS) | 45047
26.57 | Lighting Control System Allowance
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
27.000 | COMMUNICATIONS
27.41 | Audio-Visual Systems/Structured Wire/Sound System Allowance
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
28.000 | ELECTRONIC SAFETY & SECURITY
28.07 | Security System/Fire Protection/Video Surveillance Allowance
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 31-32 EARTH-SITE
31.000 | EARTHWORK
31.218 | Site Demolition
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
31.23 | Excavation/Fill/Grading/Silt Fence
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
31.26 | Surveying
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.000 | EXTERIOR IMPROVEMENTS
32.13 | Exterior Concrete Flatwork
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
Unit Rate Estimate
Driveway |  | 0 | SF
Front Stoop |  | 0 | SF
Front Walk |  | 0 | SF
City Sidewalks |  | 0 | SF
AC Pads |  | 0 | SF
Pool Deck |  | 0 | SF
Rear Patio |  | 0 | SF
|  | 0 | SF
MATERIAL
sleeve materials (pvc for under slabs) |  |  | 0 | 75 | EA | 0
Granular (SF x .25ft x 1.25 / 18 = X tons) |  |  | 0 | 16 | TON | 0
Additive (Xypex for water impermeable) |  |  | 0 | 131.85 | BOX | 0
expansion joints at walls |  |  | 0 | 150 | EA | 0
SUBCONTRACTOR
Driveway (5" with rebar) |  |  | 0 | 0 | SF | 0
Driveway Curb |  |  | 0 | 0 | LF | 0
Street Curb Cut |  |  | 0 | 0 | SF | 0
Front Walks (4") |  |  | 0 | 0 | SF | 0
City Sidewalks (4") |  |  | 0 | 0 | SF | 0
Front Stoop |  |  | 0 | 800 | EA | 0
Concrete Steps |  |  | 0 | 0 | LF | 0
AC Pads (4") |  |  | 0 | 0 | SF | 0
Rear Patio (4") |  |  | 0 | 0 | SF | 0
Pool Deck (4") |  |  | 0 | 0 | SF | 0
Trench Drain |  |  | 0 | 0 | LF | 0
Paver inset areas |  |  | 0 | 0 | LF | 0
Additional Concrete Material for 5" thick |  |  | 0 | 82.5 | CY | 0
Pump Charge for elevated balconies |  |  | 0 | 1500 | EA | 0
Grading |  |  | 0 | 0.4 | SF | 0
Cure & Seal |  |  | 0 | 0.05 | SF | 0
Sealer (Application of Stifle) |  |  | 0 | 0.45 | SF | 0
[5 empty] | TOTAL | 0
32.142 | Pavers Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
Unit Rate Estimate
Driveway | 0 | SF
Front Walk | 0 | SF
Front Stoop | 0 | SF
Rear Patio | 0 | SF
Pool Deck | 0 | SF
| 0 | SF
| 0 | 8% waste
| 0 | total SFpavers
STEPPING STONES |  | 0 | EA
NOTE: verify full pallet quantities or sf count
Paver Material (incl tax) |  |  | ALLOWANCE | 0 | 6.25 | SF | 0
Bullnose Edging (lakeside nosing) |  |  | ALLOWANCE | 0 | 12 | LF | 0
Front Stoop (brick and mortar) |  |  | ALLOWANCE | 0 | 7.25 | SF | 0
Front Stoop |  |  | ALLOWANCE | 0 | 15.75 | SF | 0
Aluminum Edging |  |  | ALLOWANCE | 0 | 3.25 | LF | 0
Subcontractor Installation |  |  | ALLOWANCE | 0 | 6.75 | SF | 0
Palmeric Sand |  |  | ALLOWANCE | 0 | 1 |  | 0
additional for asphalt set |  |  | ALLOWANCE | 0 | 1.75 | SF | 0
Stepping Stones |  |  | ALLOWANCE | 0 | 100 | EA | 0
[6 empty] | TOTAL | 0
OPTION
Sealer / Enhancer |  |  | ALLOWANCE | 0 | 1.5 | SF | 0
32.18 | Athletic/Recreational Surfacing
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.181 | Artificial Turf
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.3 | Landscape Lighting Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.31 | Fences/Gates
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.32 | Retaining Walls Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.392 | Fire Pit Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.394 | Exterior Grill/Hood
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.8 | Irrigation Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.922 | Seeding/Sod Allowance
| Sod - Raw Area | 0 | SF | 0.33 | 0 | 0
| (less beds) |  |  |  | 7% TAX | 0
[5 empty] | TOTAL | 0
32.931 | Landscaping Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0

## DIV 33 UTILITES
33.000 | UTILITIES
33.02 | Sewer / Water Utilities
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
33.462 | Underground Buried Drainage
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0