## PROJECT SUMMARY
PROJECT COST SUMMARY |  | EXCLUDING LOWER LEVEL FINISH
PROJECT | CROCKETT | [6 empty] | LOWER LEVEL | 0
PM | Grady | [6 empty] | MAIN LEVEL | 2960
LOCATION | 1702 S 150th Ave.; Omaha, NE 68144 | [6 empty] | UPPER LEVEL | 1661
DATE | 2026-08-20 | [6 empty] | TOTAL FINISHED SF | 4621
LOT # | 22 Heartwood Estates | [6 empty] | GARAGE | 1121
ZONING | [7 empty] | LOWER UNFINISHED | 2784
[8 empty] | UPPER UNFINISHED | 577
[8 empty] | COVERED PATIO | 624
[8 empty] | TOTAL SF UNDER ROOF | 9727
PHASE | DESCRIPTION | ALLOW. | LABOR | MATERIAL | OTHER | SUBCONT. | DIVISION | FINISHED COST/SF | UNDER ROOF
1 | GENERAL REQUIREMENTS |  |  |  |  | TOTAL | 192211.66 | 41.5953 | 19.7606
01.120 | Superintendent | 0 | 89775 | 0 | 0 | 0 | 89775 | 19.4276 | 9.2295
01.170 | Travel/Pickup/Deliveries | 0 | 2500 | 0 | 0 | 0 | 2500 | 0.54101 | 0.25702
01.205 | MUD Fees | 0 | 0 | 0 | 4687 | 0 | 4687 | 1.0143 | 0.48185
01.214 | Bldg. Permit | 0 | 0 | 0 | 14170.46 | 0 | 14170.46 | 3.0665 | 1.4568
01.230 | Builders Risk | 0 | 0 | 0 | 4608 | 0 | 4608 | 0.99719 | 0.47373
01.235 | General Liability | 0 | 0 | 0 | 8864 | 0 | 8864 | 1.9182 | 0.91128
01.452 | Testing/Inspections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
01.454 | Mockups | 1500 | 0 | 0 | 0 | 0 | 1500 | 0.32461 | 0.15421
01.501 | Temporary Utilities | 0 | 0 | 0 | 7597.2 | 0 | 7597.2 | 1.6441 | 0.78104
01.538 | Technology / prints | 0 | 0 | 0 | 1500 | 0 | 1500 | 0.32461 | 0.15421
01.540 | Equipment (Forklift/Skid Loader) | 0 | 0 | 0 | 2250 | 0 | 2250 | 0.48691 | 0.23131
01.560 | Temporary Barriers/Enclosures/Protection | 0 | 2400 | 1100 | 0 | 0 | 3500 | 0.75741 | 0.35982
01.578 | Site Maintenance (Snow Removal/Mowing) | 0 | 1250 | 150 | 0 | 0 | 1400 | 0.30296 | 0.14393
01.740 | Cleaning & Waste Management (Dumpsters) | 0 | 12485 | 0 | 7400 | 6725 | 26610 | 5.7585 | 2.7357
01.810 | Warranties | 0 | 0 | 0 | 18000 | 0 | 18000 | 3.8953 | 1.8505
01.830 | Small Tools/Supply/Rentals | 0 | 0 | 0 | 2250 | 0 | 2250 | 0.48691 | 0.23131
01.840 | Punchlist | 0 | 3000 | 0 | 0 | 0 | 3000 | 0.64921 | 0.30842
2 | EXISTING CONDITIONS |  |  |  |  | TOTAL | 0 | 0 | 0
02.010 | Demolition | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CONCRETE |  |  |  |  | TOTAL | 111245 | 24.0738 | 11.4367
03.300 | Footings / Foundations | 0 | 0 | 0 | 0 | 80749 | 80749 | 17.4744 | 8.3015
03.320 | Interior Concrete Flatwork | 0 | 0 | 0 | 1700 | 28796 | 30496 | 6.5994 | 3.1352
4 | MASONRY |  |  |  |  | TOTAL | 116214 | 25.1491 | 11.9476
04.210 | Brick Masonry / Precast Sills & Caps | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
04.220 | Concrete Unit Masonry (Blockwork) | 0 | 0 | 1150 | 0 | 1550 | 2700 | 0.58429 | 0.27758
04.430 | Stone Masonry / Precast Sills & Caps | 0 | 0 | 14691 | 0 | 98823 | 113514 | 24.5648 | 11.67
5 | METAL |  |  |  |  | TOTAL | 18000 | 3.8953 | 1.8505
05.120 | Structural Steel Material | 0 | 0 | 15500 | 0 | 0 | 15500 | 3.3543 | 1.5935
05.528 | Metal Interior Railings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
05.530 | Exterior Railings (stairs) | 0 | 0 | 0 | 0 | 2500 | 2500 | 0.54101 | 0.25702
05.700 | Decorative Metal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | CARPENTRY |  |  |  |  | TOTAL | 614056.97 | 132.884 | 63.1291
06.110 | Wood Framing | 0 | 3640 | 131138.24 | 1500 | 108784 | 245062.24 | 53.0323 | 25.194
06.150 | Composite Decking | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
06.380 | Cabinetry Allowance (Kitchen Hood) | 206405 | 0 | 0 | 8000 | 0 | 214405 | 46.398 | 22.0423
06.442 | Exterior Brackets/Timbers | 0 | 600 | 881 | 0 | 0 | 1481 | 0.32049 | 0.15226
06.460 | Wood Interior Trim & Stair Parts | 0 | 0 | 30806.73 | 0 | 64960 | 95766.73 | 20.7242 | 9.8455
06.612 | Countertop Allowance | 57342 | 0 | 0 | 0 | 0 | 57342 | 12.409 | 5.8951
7 | MOISTURE/THERMAL PROT. |  |  |  |  | TOTAL | 168517 | 36.4676 | 17.3247
07.130 | Waterproofing/Passive Radon/Termite Treatment | 0 | 375 | 150 | 0 | 9839 | 10364 | 2.2428 | 1.0655
07.210 | Insulation | 0 | 0 | 0 | 0 | 27390 | 27390 | 5.9273 | 2.8159
07.250 | Stucco/EIFS System (EIFS chimney) | 0 | 0 | 0 | 6977 | 23370 | 30347 | 6.5672 | 3.1199
07.300 | Roofing | 0 | 0 | 0 | 0 | 64231 | 64231 | 13.8998 | 6.6034
07.455 | Siding | 0 | 0 | 5260 | 0 | 11450 | 16710 | 3.6161 | 1.7179
07.469 | Exterior Carsiding (cedar) | 0 | 0 | 5525 | 0 | w/ siding | 5525 | 1.1956 | 0.56801
07.600 | Flashing/Brick Ledge | 0 | 800 | 1050 | 0 | 0 | 1850 | 0.40035 | 0.19019
07.630 | Gutters/Downspouts | 0 | 0 | 0 | 0 | 6600 | 6600 | 1.4283 | 0.67852
07.920 | Joint Sealants | 0 | 0 | 0 | 0 | 5500 | 5500 | 1.1902 | 0.56544
8 | DOORS & WINDOWS |  |  |  |  | TOTAL | 160973.2547 | 34.8352 | 16.5491
08.140 | Interior Wood Doors | 0 | 0 | 24014.2547 | 0 | 0 | 24014.2547 | 5.1968 | 2.4688
08.164 | Exterior Doors (w/ windows) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
08.178 | Front Door | 14559 | 520 | 0 | 0 | 0 | 15079 | 3.2631 | 1.5502
08.184 | Pet Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
08.385 | Garage Doors | 0 | 0 | 0 | 0 | 7790 | 7790 | 1.6858 | 0.80086
08.500 | Windows (Pella Reserve) | 0 | 0 | 0 | 0 | 100832 | 100832 | 21.8204 | 10.3662
08.600 | Roof Window/Skylights/Sun Tunnel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
08.817 | Mirrors/Glass Inserts/Shower Doors | 13258 | 0 | 0 | 0 | 0 | 13258 | 2.8691 | 1.363
9 | FINISHES |  |  |  |  | TOTAL | 247499 | 53.5596 | 25.4445
09.200 | Drywall | 0 | 0 | 0 | 1000 | 46793 | 47793 | 10.3426 | 4.9134
09.300 | Tile Allowance
| Floor Tile | 29710 | 0 | 0 | 0 | 0 | 29710 | 6.4293 | 3.0544
| Wall Tile/Columns | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tile Backsplash | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Shower/Tub Tile | 35271 | 0 | 0 | 0 | 0 | 35271 | 7.6328 | 3.6261
09.640 | Wood Flooring Allowance | 38124 | 0 | 0 | 0 | 0 | 38124 | 8.2502 | 3.9194
09.657 | Rubber Athletic Flooring Allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
09.672 | Epoxy Flooring | 7352 | 0 | 0 | 0 | 0 | 7352 | 1.591 | 0.75583
09.680 | Carpet Allowance | 19595 | 0 | 0 | 0 | 0 | 19595 | 4.2404 | 2.0145
09.720 | Wall Coverings/Faux Finishing | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
09.910 | Painting (assuming prefinished cabinets) | 0 | 0 | 0 | 0 | 64894 | 64894 | 14.0433 | 6.6715
09.920 | Stone at M Bath | 4760 | 0 | 0 | 0 | 0 | 4760 | 1.0301 | 0.48936
10 | SPECIALTIES |  |  |  |  | TOTAL | 112354 | 24.3138 | 11.5507
10.050 | Finish Hardware Allowance | 15597 | 4000 | 0 | 0 | 0 | 19597 | 4.2409 | 2.0147
10.140 | Address Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.310 | Fireplaces (Great Room and Cap Allowance) | 5000 | 1040 | 0 | 1200 | 9005 | 16245 | 3.5155 | 1.6701
10.311 | Fireplaces (Patio) |  | 520 | 0 | 0 | 4992 | 5512 | 1.1928 | 0.56667
10.314 | Fireplace Facings Allowance | 16627 | 0 | 0 | 0 | 0 | 16627 | 3.5981 | 1.7094
10.552 | Mailbox | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.562 | Storage Shelving | OPTION | 250 | 250 | 0 | 0 | 500 | 0.1082 | 0.051403
10.566 | Wine Cellar Racks/Cooling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.572 | Closet Systems Allowance | 53873 | 0 | 0 | 0 | 0 | 53873 | 11.6583 | 5.5385
10.712 | Exterior Shutters | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | EQUIPMENT |  |  |  |  | TOTAL | 78810.9812 | 17.055 | 8.1023
11.3 | Appliance Allowance (incl. grill/laundry) | 77770.9812 | 1040 | 0 | 0 | 0 | 78810.9812 | 17.055 | 8.1023
11.52 | TV's Allowance | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.660 | Athletic Equipment | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.678 | Game Room Equipment (Golf Simulator) | OPTION | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | FURNISHINGS |  |  |  |  | TOTAL | 0 | 0 | 0
12.170 | Art Glass | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.200 | Window Treatments | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.250 | Motorized Shades | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | SPECIAL CONSTRUCTION |  |  |  |  | TOTAL | 137094 | 29.6676 | 14.0942
13.112 | Swimming Pool (utilities) | 0 | 0 | 0 | 9500 | 119450 | 128950 | 27.9052 | 13.2569
13.174 | Sauna | in LL option | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Hot Tub | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.342 | Screen Porch System (Sun Shade at Patio) | 8144 | 0 | 0 | 0 | 0 | 8144 | 1.7624 | 0.83726
14 | CONVEYING SYSTEMS |  |  |  |  | TOTAL | 0 | 0 | 0
14.050 | Elevator | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22-23 | PLUMBING/HVAC SYSTEMS |  |  |  |  | TOTAL | 181006.0016 | 39.1703 | 18.6086
22.050 | Plumbing | 0 | 0 | 0 | 0 | 57900 | 57900 | 12.5298 | 5.9525
22.322 | Water Filtration System Allowance | 0 | 0 | 0 | 0 | 6067 | 6067 | 1.3129 | 0.62373
22.400 | Plumbing Fixt. Allowance (Air Dryer System) | 40979.2666 | 2000 | 3809.735 | 0 | 0 | 46789.0016 | 10.1253 | 4.8102
23.050 | HVAC | 0 | 0 | 0 | 0 | 67500 | 67500 | 14.6072 | 6.9394
23.400 | Duct Cleaning | 0 | 0 | 0 | 0 | 2750 | 2750 | 0.59511 | 0.28272
26-28 | ELECTRICAL & LOW VOLTAGE |  |  |  |  | TOTAL | 211591 | 45.789 | 21.753
26.050 | Electrical Service & Wiring | 0 | 0 | 0 | 0 | 72595 | 72595 | 15.7098 | 7.4632
26.410 | Lightning Protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26.505 | Light Fixtures Allowance | 43496 | 0 | 0 | 0 | 0 | 43496 | 9.4127 | 4.4717
26.570 | Lighting Control System Allowance | 29500 | 0 | 0 | 0 | 0 | 29500 | 6.3839 | 3.0328
27.410 | AV Systems Pre-Wire/Sound System Allowance | 60000 | 0 | 0 | 0 | 0 | 60000 | 12.9842 | 6.1684
28.070 | Security System/Fire Protect./Video Surv. Allowance | 6000 | 0 | 0 | 0 | 0 | 6000 | 1.2984 | 0.61684
31-32 | EARTHWORK & EXTERIOR IMPROVEMENTS |  |  |  |  | TOTAL | 419485 | 90.778 | 43.1258
31.128 | Site Demolition | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31.230 | Excavation/Fill/Grading/Silt Fence | 0 | 0 | 0 | 0 | 50440 | 50440 | 10.9154 | 5.1856
31.260 | Surveying | 0 | 0 | 0 | 0 | 2000 | 2000 | 0.43281 | 0.20561
32.130 | Exterior Concrete Flatwork | 0 | 0 | 0 | 6750 | 51595 | 58345 | 12.6261 | 5.9983
32.931 | Sitework Allowances
| Landscape - Plantings & Beds | 70000 | 0 | 0 | 0 | 0 | 70000 | 15.1482 | 7.1965
| Paver Allowance | 15000 | 0 | 0 | 0 | 0 | 15000 | 3.2461 | 1.5421
| Retaining Walls Allowance | 153250 | 0 | 0 | 0 | 0 | 153250 | 33.1638 | 15.7551
| Landscape Lighting Allowance | 15000 | 0 | 0 | 0 | 0 | 15000 | 3.2461 | 1.5421
| Irrigation Allowance | 14500 | 0 | 0 | 0 | 0 | 14500 | 3.1378 | 1.4907
| Seeding/Sod Allowance | 12500 | 0 | 0 | 0 | 0 | 12500 | 2.705 | 1.2851
| Underground Buried Drainage Allowance | 15000 | 0 | 0 | 0 | 0 | 15000 | 3.2461 | 1.5421
| Athletic/Recreation Surfacing Allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Artificial Turf Allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fire Pit Allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Exterior Grill/Hood Allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32.310 | Fences/Gates | 13450 | 0 | 0 | 0 | 0 | 13450 | 2.9106 | 1.3827
33 | UTILITIES |  |  |  |  | TOTAL | 8500 | 1.8394 | 0.87386
33.020 | Water/Sewer Utilities | 0 | 0 | 0 | 0 | 8500 | 8500 | 1.8394 | 0.87386
50 | CONTINGENCY |  |  |  |  | TOTAL | 45000 | 9.7382 | 4.6263
50.050 | Contingency | 0 | 0 | 0 | 45000 | 0 | 45000 | 9.7382 | 4.6263
50.070 | Arch/Engr Fees (Separate Agreement) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 1093563.2478 | 126195 | 235475.9597 | 152953.66 | 1214370 | 3245941.5476 | 702.4327 | 333.7043
McNeil Company Builders
PROJECT COST SUMMARY---MARKUP ANALYSIS
Project: | CROCKETT | [5 empty] | LOWER LEVEL | 0
Location: | 1702 S 150th Ave.; Omaha, NE 68144 | [5 empty] | MAIN LEVEL | 2960
Date: | 46254 | [5 empty] | UPPER LEVEL | 1661
Lot: | 22 Heartwood Estates | [5 empty] | TOTAL FINISHED SF | 4621
[7 empty] | GARAGE | 1121
[7 empty] | LOWER UNFINISHED | 2784
[7 empty] | COVERED PATIO | 624
[7 empty] | TOTAL SF UNDER ROOF | 9727
MARKUP ADJUSTMENTS
ACTUAL COST
[6 empty] | Allowances |  | 1093563.2478
[6 empty] | Labor |  | 126195
[6 empty] | Material |  | 235475.9597
[6 empty] | Other |  | 152953.66
[6 empty] | Subcontractor |  | 1214370
[6 empty] | NO MARKUP TOTAL |  | 2822557.8675
[6 empty] | MARKUP PERCENTAGE |  | 15%
[6 empty] | MARKUP |  | 423383.6801
[6 empty] | BID |  | 3245941.5476

## DIV 1 GC
01.000 | GENERAL CONDITIONS
1.12 | Superintendent
|  |  | PROJECT DURATION - MONTHS | APPROX. HOURS/DAY | HOURS/WEEK | RATE/HOUR | COST/WEEK | PROJECT DURATION - WEEKS | TOTAL
|  | minimal supervision at start 3 wks | 0 | 0 | 15 | 90 | 1350 | 66.5 | 89775
1.17 | Travel/Pickup/Deliveries
| Rates updated March 2026 | [6 empty] | TOTAL | 2700
[5 empty] | HOURS/WEEK | RATE/HOUR | COST/WEEK | PROJECT DURATION - WEEKS | TOTAL
|  |  |  | Labor | 0.75 | 60 | 45 | 60 | 2700
1.205 | MUD Fees
| Rates updated March 2026 (based on Schachne) |  |  |  | TOTAL | 4687
| 1" Capital Facilities Charge (Impact Fee) |  |  | 1 | 3520 | 3520
| 1" Meter Install |  |  | 1 | 459 | 459
| Water Tap |  |  | 1 | 708 | 708
1.214 | Bldg. Permit
| Rates updated March 2026 | [6 empty] | TOTAL | 0
City of Omaha
https://permits.cityofomaha.org/fees
| $1.00-$2,000 |  | 41 |  |  |  | 0 | 41 | 0
| $2,000-$25,000 |  | $41.00 for first $2,000, plus $9.53 for each additional $1,000 |  |  |  | 0 | 41 | 0
[7 empty] | 0 | 9.53 | 0
| $25,001-$50,000 |  | $260.19 for first $25,000, plus $6.44 for each additional $1,000 |  |  |  | 0 | 260.19 | 0
[7 empty] | 0 | 6.44 | 0
| $50,001-$100,000 |  | $421.19 for first $50,000, plus $3.19 for each additional $1,000 |  |  |  | 0 | 421.19 | 0
[7 empty] | 0 | 3.19 | 0
| $100,001-$500,000 |  | $580.69 for first $100,000, plus $2.78 for each additional $1,000 |  |  |  | 0 | 580.69 | 0
[7 empty] | 0 | 2.78 | 0
| $500,001-$1,000,000 |  | $1,692.69 for first $500,000, plus $2.37 for each additional $1,000 |  |  |  | 0 | 1692.69 | 0
[7 empty] | 0 | 2.37 | 0
| $1,000,001 and up |  | $2877.69 for first $1,000,000, plus $1.96 for each additional $1,000 |  |  |  | 0 | 1000000 | 0
[7 empty] | 0 | 1.96 | 0
City of Blair
https://www.blairne.gov/DocumentCenter/View/52/Building-Permit-and-Zoning-Fees-PDF
| Finished SF (not including finished basement) |  |  | 0 | * | 102 | 0
| Finished Basement SF |  |  | 0 | * | 62 | 0
| Unfinished Basement SF |  |  | 0 | * | 32 | 0
| Garage SF |  |  | 0 | * | 30 | 0
0
[6 empty] | Multiply by .006 | 0.006
[6 empty] | Total | 0
1.23 | Builders Risk
[8 empty] | TOTAL | 4608
| Builders Risk (0.144/100 cost) |  |  |  |  | 32000 | 0.144 |  | 4608
| Misc. |  |  |  |  | 0 |  |  | 0
1.235 | General Liability
[8 empty] | TOTAL | 8864
| Liability (2.77/1000 cost) |  |  |  |  | 3200 | 2.77 |  | 8864
| Bond |  |  |  |  | 0 |  |  | 0
| Misc. |  |  |  |  | 0 |  |  | 0
1.452 | Testing/Inspections
[8 empty] | TOTAL | 0
| Soil Testing |  |  |  |  | 0 | 1500 |  | 0
| Call back after excavation for visual inspection |  |  |  |  | 0 | 200 |  | 0
1.454 | Mockups
[8 empty] | TOTAL | 1310
|  |  |  | Labor |  | 16 | 60 | HR | 960
|  |  |  | Materials |  | 1 | 350 | EA | 350
1.501 | Temporary Utilities
| Rates updated March 2026 | [6 empty] | TOTAL | 7597.2
| Temp Power Service |  | OPPD |  |  | 16 | 175 | /MONTH | 2800
| Temp Gas / Water Service |  | MUD |  |  | 6 | 250 | /MONTH | 1500
| Temp Heat for Interior |  | Labor / Material |  |  | 4 | 300 | ALLOWANCE | 1200
| Temp Heat for Exterior |  | Labor / Material |  |  | 0 | 200 | ALLOWANCE | 0
| Portable Toilet |  | Eagle Services |  | Monthly Charge (includes tax) | 16 | 128.4 | /MONTH | 2054.4
[5 empty] | Delivery & Pickup (inlcudes tax) | 2 | 21.4 | /MONTH | 42.8
1.538 | Technology
| Rates updated March 2026 | [6 empty] | TOTAL | 2000
[5 empty] | Copier | 1 | 500 | /JOB | 500
[5 empty] | Software | 15 | 100 | / MONTH | 1500
1.54 | Equipment (Forklift/Skid Loader)
| Rates updated March 2026 | [6 empty] | TOTAL | 1750
[5 empty] | Equipment | 1 | 1750 | /JOB | 1750
1.56 | Temporary Barries/Enclosures
| Rates updated March 2026 | [6 empty] | TOTAL | 3900
|  |  |  | Material |  | 2 | 750 | EA | 1500
|  |  |  | Labor | (2 guys at $60/hr) | 20 | 120 | HR | 2400
|  |  |  | Subcontract |  | 0 | 4500 | EA | 0
1.578 | Site Maintenance
| Rates updated March 2026 | [6 empty] | TOTAL | 4800
| Snow Removal |  |  | Labor |  | 20 | 60 | HR | 1200
| Mowing/Spraying/Weedeating |  |  | Labor |  | 60 | 60 | HR | 3600
1.74 | Cleaning & Waste Management
| Rates updated March 2026 | [6 empty] | TOTAL | 26610
|  |  | Interim Clean | Labor | 3 hrs/week | 195 | 55 | HR | 10725
|  |  | Final Clean | Labor |  | 32 | 55 | HR | 1760
|  |  | Final Clean | Subcontract |  | 6750 | 0.7 | SF | 4725
|  |  | Window Clean | Subcontract | 2-story | 1 | 2000 | EA | 2000
|  |  | Window Clean | Subcontract | Ranch | 0 | 750 | EA | 0
|  |  | Dumpsters | Other | S2 | 20 | 370 | /MONTH | 7400
Excludes drywall in phase
1.81 | Warranties
| Warranty Historical |  |  | Own | McNeil | 3000000 | 0.006 | /TOTAL/COST | 18000
1.83 | Small Tools/Supply/Rent
| Rates updated March 2026 | [6 empty] | TOTAL | 1270
[5 empty] | Tools/Supplies | 1 | 400 | /JOB | 400
[5 empty] | Floor Sander | 1 | 120 | /JOB | 120
[5 empty] | Other Equipment | 3 | 250 | /JOB | 750
1.84 | Punchlist
| Rates updated March 2026 | [6 empty] | TOTAL | 1500
[5 empty] | Labor | 1 | 1500 | /JOB | 1500

## DIV 2 EXIST. COND.
02.000 | EXISTING CONDITIONS
2.01 | Demolition
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 3 CONCRETE
03.000 | CONCRETE
3.3 | Footings/Foundations
|  |  |  | BDB | Midwest Poured Walls | StephenSmith
Base Bid |  |  |  | 79889 | 74895 | 62131 | 0
1
2
3 | sales tax adjustment (5.5 to 7) |  |  |  |  | 931.965
4
5
6
7
8
9
10
|  |  | TOTAL | 79889 | 74895 | 63062.965 | 0
3.32 | Interior Concrete Flatwork
|  |  |  | RME | Musicfield | AM Contracting
Base Bid |  |  |  | 0 | 0 | 0 | 0
1 | basement |  |  | 19783 | 23240.25
2 | garage |  |  | 8263 | 9808.75
3
4
5
6
7
8
9
10
|  |  | TOTAL | 28046 | 33049 | 0 | 0
Unit Rate Estimate - rates updated March of 2026
Lower Level Slab |  | 2790 | sf
Garage Slab |  | 1034 | sf
|  | 3824 | sf
MATERIAL
Poly (LL & GARAGE SLAB SF x 1.15 = sf) |  |  |  | 3824 | 0.075 | SF | 286.8
Lower Level Slab Granular (LL SF x .33ft x 1.25 / 18 = tons) |  |  |  | 63.9375 | 22 | TON | 1406.625
Garage Slab Granular (GARAGE SF x .33ft x 1.25 / 18 = tons) |  |  |  | 23.6958 | 22 | TON | 521.3083
Additive (Xypex for water impermeable) |  |  |  | 0 | 131.85 | BOX | 0
Expansion Joints at Walls |  |  | ls | 8.94 | 125 | EA | 1117.5
SUBCONTRACTOR
Lower Level Slab |  |  |  | 2790 | 6.75 | SF | 18832.5
Poly install |  |  |  | 3824 | 0.35 | SF | 1338.4
Step Down (form charge) |  |  |  | 0 | 10 | LF | 0
Garage Slab |  |  |  | 1034 | 6.75 | SF | 6979.5
Saw Cut slabs |  |  |  | 3824 | 0.05 | SF | 191.2
Grading |  |  |  | 3850 | 0.25 | SF | 962.5
Pump charge |  |  |  | 1 | 1700 | EA | 1700
Cure & Seal |  |  |  | 3824 | 0.12 | SF | 458.88
[6 empty] | TOTAL | 33795.2133

## DIV 4 MASONRY
04.000 | MASONRY
4.21 | Brick / Precast Sills & Caps
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
Unit Rate Estimate - rates updated March of 2026
Brick (Modular) |  | 0 | SF | 7 | 0 | brick ea
Soldiers/Rowblocks |  | 0 | LF | 3.5 | 0 | brick ea
Approx. per 292lf |  |  |  | RAW QTY BRICK | 0 | brick ea
|  |  |  | 12% WASTE FACTOR | 0 | brick ea
|  |  |  | TOTAL | 0 | brick ea
*adjust brick/cube quantity based on brick size |  |  |  | Qty of Full Cubes | 525 | brick/cube
|  |  |  | TOTAL | 0 | total cubes
Per Laura at Watkins:
125 brick/bag of masonry for this product
premix mortar - 35-40 brick/bag on modular / 30-32 brick per bag oversize
MATERIAL
Brick (modular) |  |  |  | 0 | 0.95 | 0
Brick (solids) |  |  |  | 0 | 1.5 | 0
premix mortar (colored) |  |  |  | 0 | 14.45 | 0
premix mortar (standard gray) |  |  |  | 0 | 9.5 | 0
Masonry Cement |  | 7 bags/M |  | 0 | 11 | 0
Portland Cement |  | 1 bag/5 of masonry |  | 0 | 14 | 0
Sand |  | 3 to 1 by weight |  | 0 | 15 | 0
Weep Holes |  | approx. every 3lf |  | 0 | 0.65 | 0
Nervastral |  | 12"x150'/roll |  | 0 | 90 | 0
SureKlean #600 detergent |  | 600sf/gallon |  | 0 | 25 | 0
Ties |  | .10 ties per brick |  | 0 | 0.35 | 0
1" Mortar Net |  |  |  | 0 | 2.4 | 0
Misc. Tools |  |  |  | 0 | 200 | 0
Pallet charge |  |  |  | 0 | 28 | 0
freight/delivery |  |  |  | 0 | 75 | 0
[5 empty] | SUBTOTAL | 0
[5 empty] | 7% TAX | 0
[5 empty] | TOTAL | 0
4.22 | Concrete Masonry Units (Blockwork)
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
4.43 | Stone Masonry / Precast Sills & Caps
|  |  |  | Ron Muller | Material | Arrowstone | COMBO
Base Bid |  |  |  | 63700 | 0 | 0 | 63700
1 | Qty variance for full depth |  |  | 3375 |  |  | 3375
2 | Thin Stone (Fireplace Stone - material only) |  |  |  | 22938.44 |  | 40040.54
3 | Delivery |  |  |  | 190 |  | 190
4
5 | See below |  |  |  | 41851.98 |  | 41851.98
6
7
8 | Precast |  |  |  |  | 14691 | 14691
9
10
|  |  | TOTAL | 67075 | 64980.42 | 14691 | 163848.52
Unit Rate Estimate - rates updated March of 2026
Thin Stone Flats |  | 1069 | SF | 12% waste factor | 1197.28 | stone sf
Thin Stone Corners |  | 130 | LF | 12% waste factor | 145.6 | stone sf
Approx. per 292lf |  |  |  | TOTAL | 1342.88 | stone sf
Full Bed Depth Stone |  | 1395 | SF | 12% waste factor | 1562.4 | stone sf
Approx. per 292lf |  |  |  | TOTAL | 1562.4 | stone sf
|  |  |  | Approximate ton qty | 38 | sf/ton
|  |  |  | TOTAL | 41.1158 | tons
per Laura at Watkins: |  |  |  |  | 2905.28 | TOTAL STONE SF
thin stone mortar coverage - Promix 70lb bag is 15sf/bag for joints; 7sf/bag for scratch coat
full bed depth stone mortar coverage - depends on stone size, but 7-10sf/bag gets close
german schmear style mortar coverage - depends on heaviness of schmear
approximate sf/ton for full bed depth stone - 38-40sf/ton
MATERIAL
Thin Stone Flats |  | $/sf |  | 0 | 12 | 0 | Fireplace Stone
Thin Stone Corners |  | $/each |  | 0 | 18 | 0 | Fireplace Stone
Full Bed Depth Stone |  | $/ton |  | 41 | 650 | 26650
Premix Mortar (colored) - FULL |  |  | 7 | 225 | 14.45 | 3251.25
Premix Mortar (colored) - THIN |  |  | 15 | 90 | 14.45 | 1300.5
Premix Mortar (standard gray) |  |  |  | 0 | 13.8 | 0
Scratch coat mortar |  |  | 7 | 195 | 13.8 | 2691
Metal Lathe |  | 27"x96", assume 16sf with overlap |  | 185 | 14.1 | 2608.5
Felt |  | 200sf/roll |  | 16 | 35 | 560
Lathe Bottom Weep Screed |  | assume 10' |  | 40 | 17 | 680
Rainscreen, Keene |  | 4'x65' |  | 20 | 10 | 200
Masonry Cement |  | 7 bags/M |  | 0 | 11 | 0
Portland Cement |  | 1 bag/5 of masonry |  | 0 | 14 | 0
Sand |  | 3 to 1 by weight |  | 0 | 15 | 0
Weep Holes |  | approx. every 3lf |  | 135 | 0.65 | 87.75
Nervastral |  | 12"x150'/roll |  | 0 | 90 | 0
SureKlean #600 detergent |  | 600sf/gallon |  | 5 | 25 | 125
Ties |  | .10 ties per brick |  | 0 | 0.35 | 0
1" Mortar Net |  |  |  | 0 | 2.4 | 0
Misc. Tools |  |  |  | 2 | 200 | 400
Pallet charge |  | approx. 150-200sf/pallet |  | 20 | 28 | 560
freight/delivery |  |  |  | 0 | 75 | 0
[5 empty] | SUBTOTAL | 39114
[5 empty] | 7% TAX | 2737.98
[5 empty] | TOTAL | 41851.98

## DIV 5 METAL
05.000 | METAL
5.12 | Strucutural Steel - Material
|  |  | Stabdard Iron | Company | Company | Company
Base Bid |  |  | 13412.23 | 0 | 0 | 0
1 | Priming steel |  | 700
2 | Delivery |  | Included
3
4
5
6
7
8
9
10
|  | TOTAL | 14112.23 | 0 | 0 | 0
5.528 | Metal Interior Railing
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
5.53 | Exterior Deck Railing
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
5.7 | Decorative Metal
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 6 CARPENTRY
06.000 | CARPENTRY
6.11 | Wood Framing
|  |  |  | LP | MX3 | Company | Company
Base Bid |  |  |  | 108784 | 116010 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 108784 | 116010 | 0 | 0
6.15 | Wood Decks
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
6.38 | Cabinetry
|  |  |  | CKF | Company | Company | Company
Main Level |  |  |  | Classic
| Kitchen | ALLOWANCE | *MATERIAL | 41686
PLUG | Coffee Bar Doors | ALLOWANCE | *MATERIAL | 5000
| Hidden Pantry | ALLOWANCE | *MATERIAL | 24459
| Planning Room | ALLOWANCE | *MATERIAL | 10456
| Drop Zone | ALLOWANCE | *MATERIAL | 11426
| Powder | ALLOWANCE | *MATERIAL | 1247
| Contemplation | ALLOWANCE | *MATERIAL | 10221
PLUG | Contemplation Arch | ALLOWANCE | *MATERIAL | 2000
| Laundry | ALLOWANCE | *MATERIAL | 12083
| Master Bath | ALLOWANCE | *MATERIAL | 10831
| Great Room | ALLOWANCE | *MATERIAL | 966
PLUG | Great Room Arch | ALLOWANCE | *MATERIAL | 2000
Upper Level
| Laundry | ALLOWANCE | *MATERIAL | 3516
| Bath 3 | ALLOWANCE | *MATERIAL | 3789
| Dressing 3/Bath 4 Linen | ALLOWANCE | *MATERIAL | 7821
| Dressing 4 | ALLOWANCE | *MATERIAL | 5331
PLUG | Dressing 4 Linen | ALLOWANCE | *MATERIAL | 2000
1 | Hardware |  |  | 3570
2 | Installation |  |  | 22517
3
4
5
|  |  | TOTAL | 180919 | 0 | 0 | 0
Exterior
| Patio | ALLOWANCE | *MATERIAL | 13389
6.442 | Exterior Brackets/Timbers
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
6.46 | Wood Interior Trim
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1 | LABOR
2 | MATERIAL
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
Unit Rate Estimate
| MAIN FLOOR |  | SPECIES | QTY | UNIT PRICE | SUBTOTAL | NOTES
BASE AND CASING
| 3" Casing |  |  | 0 | 0 | 0
| 3 1/2" Casing |  |  | 0 | 0 | 0
| 4" Casing |  |  | 0 | 0 | 0
| 3" Base (Mechanical Rooms) |  |  | 0 | 0 | 0
| 4" Base |  | POPLAR | 50 | 0 | 0 | LF
| 6" Base |  | POPLAR | 30 | 0 | 0 | LF
| 8" Base |  | POPLAR | 360 | 0 | 0 | LF
| PVC Base - Azek (Garage) |  | POPLAR | 160 | 0 | 0 | LF
| Base Shoe |  |  | 0 | 0 | 0
| 1x2s |  | POPLAR | 6 | 0 | 0 | 8', EA
| Window Jamb Extensions |  |  | 0 | 0 | 0
| Tooling/Setup Charge |  |  | 0 | 500 | 0
| UPPER FLOOR |  | SPECIES | QTY | UNIT PRICE | SUBTOTAL | NOTES
BASE AND CASING
| 3" Casing |  |  | 0 | 0 | 0
| 3 1/2" Casing |  |  | 0 | 0 | 0
| 4" Casing |  |  | 0 | 0 | 0
| 3" Base (Mechanical Rooms) |  |  | 0 | 0 | 0
| 4" Base |  | POPLAR | 210 | 0 | 0 | LF
| 6" Base |  | POPLAR | 280 | 0 | 0 | LF
| 8" Base |  |  | 0 | 0 | 0
| PVC Base - Azek (Garage) |  |  | 0 | 0 | 0
| Base Shoe |  |  | 0 | 0 | 0
| Window Jamb Extensions |  |  | 0 | 0 | 0
| Tooling/Setup Charge |  |  | 0 | 500 | 0
CASING DETAILS
| 1 1/2" bn |  |  | 0 | 0 | 0
| 1 x 6 S4S (for jamb) |  |  | 0 | 0 | 0
| stop |  |  | 0 | 0 | 0
| glass mullion (to match door profile) |  |  | 0 | 0 | 0
| backband (for front door) |  |  | 0 | 0 | 0
| Mullcenter (double door) |  |  | 0 | 0 | 0
| 1 x 4 S4S window stools |  |  | 0 | 0 | 0
| set up/freight for glass mullions |  |  | 0 | 0 | 0
CROWN MOLDING
| 3" CROWN |  | POPLAR | 330 | 0 | 0 | LF
| 6" CROWN |  | POPLAR | 80 | 0 | 0 | LF
| Built-Up Band |  |  | 0 | 0 | 0
| 1 x 4 S4S (backing material) |  |  | 0 | 0 | 0
BEAMS
| 1x8 |  | POPLAR | 76 | 0 | 0 | LF
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
STAIR PARTS
| Newel Posts |  |  | 0 | 0 | 0
| Wood Railing |  |  | 0 | 0 | 0
| Balusters |  |  | 0 | 0 | 0
| 1x12 skirt boards |  |  | 0 | 0 | 0
| 4" casing skirt board cap |  |  | 0 | 0 | 0
| 1/2x12 End Cap Treads |  |  | 0 | 0 | 0
| 1/2x8 End Cap Risers |  |  | 0 | 0 | 0
| Planing Charge |  |  | 0 | 0 | 0
| End Cap & Balcony Nosing |  |  | 0 | 0 | 0
MISC. TRIM DETAILS
| Glue, shims, fasteners, blades |  |  | 0 | 750 | 0
| Delivery |  |  | 0 | 150 | 0
[5 empty] | subtotal | 0
[5 empty] | 7% tax | 0
[5 empty] | TOTAL | 0
6.612 | Countertop Allowance
|  |  |  | CKF | Company | Company | Company
Main Level
| Dog Wash | ALLOWANCE | *MATERIAL | 40
| Primary Shower | ALLOWANCE | *MATERIAL | 656
| Kitchen | ALLOWANCE | *MATERIAL | 10834
PLUG | Kitchen 19" Splash | ALLOWANCE | *MATERIAL | 2000
| Kitchen Full Splash | ALLOWANCE | *MATERIAL | 9434
PLUG | Coffee | ALLOWANCE | *MATERIAL | 1500
PLUG | Coffee Full Splash | ALLOWANCE | *MATERIAL | 2000
| Hidden Pantry | ALLOWANCE | *MATERIAL | 2617
| Planning Room | ALLOWANCE | *MATERIAL | 1869
| Planning Full Splash | ALLOWANCE | *MATERIAL | 2913
| Drop Zone | ALLOWANCE | *MATERIAL | 1929
| Powder | ALLOWANCE | *MATERIAL | 815
| Contemplation | ALLOWANCE | *MATERIAL | 1408
| Laundry | ALLOWANCE | *MATERIAL | 2682
| M Bath | ALLOWANCE | *MATERIAL | 2644
| Primary Closet | ALLOWANCE | *MATERIAL | 2316
Upper Level
| Bath 3 Shower | ALLOWANCE | *MATERIAL | 305
| Bath 4 Shower | ALLOWANCE | *MATERIAL | 305
| Laundry | ALLOWANCE | *MATERIAL | 499
| Bath 3 Counter | ALLOWANCE | *MATERIAL | 1021
| Dressing 3 Counter | ALLOWANCE | *MATERIAL | 1762
| Dressing 4 Counter | ALLOWANCE | *MATERIAL | 1287
|  |  | TOTAL | 50836 | 0 | 0 | 0
OUTDOOR GRILL
| Patio | ALLOWANCE | *MATERIAL | 5030
| Patio full splash | ALLOWANCE | *MATERIAL | 2949
32.931 |  |  | TOTAL | 7979 | 0 | 0 | 0
FIREPLACE FACING - OUTDOOR
| Fireplace | ALLOWANCE | *MATERIAL | 527
10.314 |  |  | TOTAL | 527 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 59342 | 0 | 0 | 0

## DIV 7 MOISTURE PROTECTION
07.000 | MOISTURE/THERMAL PROTECTION
7.13 | Waterproofing/Passive Radon/Termite Treatment
|  |  | Jerry's | BDB | Stephen&Smith | Company
Base Bid |  |  | 8989 | 6356 | 3911 | 0 | Ftg Height | Length | Total SF
1 | Sump Pumps (2) |  | 850 | 650 | 500 |  | 1 | 45 | 45 | above ground
2 | Sewer line |  | incl? | 150 |  |  | 3 | 6 | 18 | above ground
3 | Drainage tile |  | incl | incl |  |  | 5 | 123 | 615 | above ground
4 | Drainboard |  |  | incl? |  |  | 10 | 75 | 750
5 | [6 empty] | 11 | 112 | 1232
6 | [6 empty] | 11.5 | 35 | 402.5
7 | [8 empty] | 3062.5
8
9
10
|  | TOTAL | 9839 | 7156 | 4411 | 0
7.21 | Insulation
|  |  | Neb Bldg Prod | SealRite | BC Drywall | Company
Base Bid |  |  | 17333 | 0 | 9750 | 0
1 | Insulate at basement concrete walls (unfinished) |  | 2853
2 | joists between 1st and 2nd floor |  | 6213
3 | garage walls |  | 1191
4 | garage attic |  | 895
5 | house attic upgrade from R38 to R-49 |  | 1046
6 | dining attic upgrade from R38 to R-49 |  | 32
7
8
9
10
|  | TOTAL | 29563 | 0 | 9750 | 0
7.25 | Stucco System
|  |  | Czech | FireplaceStone | Company | Company
Base Bid |  |  | 23370 | 19014 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 23370 | 19014 | 0 | 0
7.3 | Roofing
|  |  | Rooferees | Bradco | Company | Company
Base Bid |  |  | 88463 | 59032 | 0 | 0
1 | barrel roof (allowance) |  |  | 5000
2
3
4
5
6
7
8
9
10
|  | TOTAL | 88463 | 64032 | 0 | 0
7.455 | Siding
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.469 | Exterior Carsiding
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.6 | Flashing/Brickledge
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.63 | Gutters/Downspouts
|  |  | Rooferees | Bradco | Company | Company
Base Bid |  |  | 9398 | 5437 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 9398 | 5437 | 0 | 0
7.92 | Joint Sealants
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 8 OPENINGS
08.000 | OPENINGS
8.14 | Interior Wood Doors
|  |  |  | SE Smith | Christensen | Taylor Made | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
| Main Floor - Karona |  |  | 12372.27
| Upgrade - glass at Contemplation Doors |  |  | 1900
| Upper floor - Karona |  |  | 7156.94
| Upgrade - exterior frame at UL furnace |  |  | 500
| taxes |  |  | 1535.0447
| shims/misc. |  |  | 250
| delivery |  |  | 300
|  |  | TOTAL | 24014.2547 | 0 | 0 | 0
8.178 | Front Door
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.184 | Pet Door
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.385 | Garage Doors
|  |  |  | AAA | ODW | Company | Company
Base Bid |  |  |  | 6959 | 7179 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 6959 | 7179 | 0 | 0
8.5 | Windows
|  |  |  | Pella | Company | Company | Company
Base Bid |  |  |  | 113478.94 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 113478.94 | 0 | 0 | 0
8.6 | Roof Windows/Skylights/Sun Tunnel
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.817 | Mirrors/Glass Inserts/Shower Doors
|  |  |  | Company | Company | Company | Company
Main Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
Lower Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
Upper Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
1
2
3
4
5
6
7
8
9 | Install
10 | McNeil Company Wood Backer Supply/Install
|  |  | TOTAL | 0 | 0 | 0 | 0

## DIV 9 FINISHES
09.000 | FINISHES
9.2 | Drywall
|  |  |  | BC Drywall | Freedom | Christiansen | Company
Base Bid |  |  |  | 38325 | 44698 | 48300 | 0
1 | drywall returns |  |  | 1200
2 | drywall perimeter walls in basement |  |  | 2500
3 | 5/8" drywall at ceilings |  |  | 1000
4
5
6
7
8
9
10
|  |  | TOTAL | 43025 | 44698 | 48300 | 0
9.3 | Tile
Floor Tile
[8 empty] | TOTAL | 0
| LL Bath 009 | [7 empty] | 0 | ALTERNATE
|  |  |  | Tile Material | ALLOWANCE |  | 8 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE |  | 21 | SF | 0
|  |  |  | Delivery | ALLOWANCE |  | 75 | EA | 0
|  |  |  | Sealer | ALLOWANCE |  | 1.5 | SF | 0
|  |  |  | Self Leveling | ALLOWANCE |  | 5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Tile Material | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 75 | EA | 0
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Self Leveling | ALLOWANCE | 0 | 5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Tile Material | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 75 | EA | 0
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Self Leveling | ALLOWANCE | 0 | 5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Tile Material | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 75 | EA | 0
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Self Leveling | ALLOWANCE | 0 | 5 | SF | 0
|  |  |  | In-Floor Heat | ALLOWANCE | 0 | 20 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Tile Material | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 75 | EA | 0
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Anti-fracture Membrane | ALLOWANCE | 0 | 2 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Tile Material | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 75 | EA | 0
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Anti-fracture Membrane | ALLOWANCE | 0 | 2 | SF | 0
Tile Backsplash
[8 empty] | TOTAL | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Deco | ALLOWANCE | 0 | 275 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 32 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 50 | EA | 0
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Deco | ALLOWANCE | 0 | 275 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 32 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 50 | EA | 0
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Deco | ALLOWANCE | 0 | 275 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 32 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 50 | EA | 0
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Deco | ALLOWANCE | 0 | 275 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 32 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 50 | EA | 0
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Deco | ALLOWANCE | 0 | 275 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 32 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 50 | EA | 0
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
Wall Tile/Columns
[8 empty] | TOTAL | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 35 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 32 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 50 | EA | 0
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
Shower/Tub Tile
[8 empty] | TOTAL | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 12 | SF | 0
|  |  |  | Deco Tile | ALLOWANCE | 0 | 400 | EA | 0
|  |  |  | Ceiling Tile | ALLOWANCE | 0 | 12 | SF | 0
|  |  |  | Floor Tile | ALLOWANCE | 0 | 20 | SF | 0
|  |  |  | Bullnose | ALLOWANCE | 0 | 15 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Miter Outside Corners - Addt'l Cost | ALLOWANCE | 0 | 300 | EA | 0
|  |  |  | Labor - install seat, shelves, jamb and/or curb | ALLOWANCE | 0 | 1000 | EA | 0
|  |  |  | Labor - floor | ALLOWANCE | 0 | 85 | SF | 0
|  |  |  | Tile Drain | ALLOWANCE | 0 | 150 | EA | 0
|  |  |  | Sealer/Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 100 | EA | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Deco Tile | ALLOWANCE | 0 | 400 | EA | 0
|  |  |  | Ceiling Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Floor Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Bullnose | ALLOWANCE | 0 | 15 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Labor - install shelves, curb | ALLOWANCE | 0 | 1000 | EA | 0
|  |  |  | Labor - floor | ALLOWANCE | 0 | 85 | SF | 0
|  |  |  | Tile Drain | ALLOWANCE | 0 | 150 | EA | 0
|  |  |  | Sealer/Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 100 | EA | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Deco Tile | ALLOWANCE | 0 | 400 | EA | 0
|  |  |  | Ceiling Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Floor Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Bullnose | ALLOWANCE | 0 | 15 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Labor - install shelves, curb | ALLOWANCE | 0 | 1000 | EA | 0
|  |  |  | Labor - floor | ALLOWANCE | 0 | 85 | SF | 0
|  |  |  | Tile Drain | ALLOWANCE | 0 | 150 | EA | 0
|  |  |  | Sealer/Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 100 | EA | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Deco Tile | ALLOWANCE | 0 | 400 | EA | 0
|  |  |  | Ceiling Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Floor Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Bullnose | ALLOWANCE | 0 | 15 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Labor - install shelves, curb | ALLOWANCE | 0 | 1000 | EA | 0
|  |  |  | Labor - floor | ALLOWANCE | 0 | 85 | SF | 0
|  |  |  | Tile Drain | ALLOWANCE | 0 | 150 | EA | 0
|  |  |  | Sealer/Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 100 | EA | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Deco Tile | ALLOWANCE | 0 | 400 | EA | 0
|  |  |  | Ceiling Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Floor Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Bullnose | ALLOWANCE | 0 | 15 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Labor - install shelves, curb | ALLOWANCE | 0 | 1000 | EA | 0
|  |  |  | Labor - floor | ALLOWANCE | 0 | 85 | SF | 0
|  |  |  | Tile Drain | ALLOWANCE | 0 | 150 | EA | 0
|  |  |  | Sealer/Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 100 | EA | 0
9.64 | Wood Flooring / LVP / LVT Allowance
| WOOD FLOOR / LVP / LVT AREAS | [5 empty] | TOTAL | 0
| Main Level | 0 | SF
| Lower Level | 0 | SF
| Upper Level | 0 | SF
| Subtotal | 0 | SF
| 7% waste - typical | 0 | SF
| 15% waste - diagonal/herringbone | 0 | SF
| Total | 0 | SF
| Prefin. wood materials (range from $5.50-$12) |  |  | ALLOWANCE | 0 | 0 | SF | 0
| Wood Installation Labor |  |  | ALLOWANCE | 0 | 0 | SF | 0
| Wood Stair Labor |  |  | ALLOWANCE | 0 | 25 | EA | 0
| Wood Vents (Flush Mount) |  |  | ALLOWANCE | 0 | 122 | EA | 0
| Miscellanous Underlayment/Floor Prep |  |  | ALLOWANCE | 0 | 3 | SF | 0
| LVP / LVT materials |  |  | ALLOWANCE | 0 | 0 | SF | 0
| LVP / LVT Installation Labor |  |  | ALLOWANCE | 0 | 0 | SF | 0
| LVP / LVT Prep / Glue / Transitions |  |  | ALLOWANCE | 0 | 0 | SF | 0
NOTES:
per Timberland - use $10/sf allowance for prefinished wood
9.657 | Rubber Athletic Flooring Allowance
| AREAS | [5 empty] | TOTAL | 0 | ALTERNATE
| Main Level | 0 | SF
| Lower Level | 220 | SF
| Upper Level | 0 | SF
| Subtotal | 220 | SF
| 7% waste | 15.4 | SF
| Total | 235.4 | SF
| Carpet Tile/Rubber Flooring Material |  |  | ALLOWANCE | 235 | 0 | SF | 0
| Installation Labor |  |  | ALLOWANCE | 235 | 0 | SF | 0
9.672 | Epoxy Flooring
| AREAS | [5 empty] | TOTAL | 7351.5 | ALTERNATE
| Garage | 1057 | SF
| Mechanical/Storage | 0 | SF
| Mechanical/Storage | 0 | SF
| Subtotal | 1057 | SF
| 7% waste | 73.99 | SF
| Total | 1130.99 | SF
| Epoxy Flooring Material / Installation |  |  | ALLOWANCE | 1131 | 6.5 | SF | 7351.5
9.68 | Carpet Allowance
| AREAS |  |  |  |  | TOTAL | 19595
| Main Level | 168 | SF
| Lower Level | 0 | SF
| Upper Level | 1062 | SF
| Stairs (x2 for risers) | 249 | SF
| Total SF | 1479 | SF
| Conversion to SY (X 1.35 / 9) | 221.85 | SY
| 12' Roll Layout - Actual | 238 | SY
| ALLOWANCE BREAKDOWN |  |  | AVG
| Installation Labor |  |  | 230 | 8 | PER SY | 1840
| Carpet Pad (memory foam) |  |  | 230 | 7 | PER SY | 1610
| Material Allowance |  | INCL TAX | 230 | 65 | PER SY | 14950
| Floor Prep / Tack Strip / Etc. |  |  | 230 | 1.5 | PER SY | 345
| STAIRS |  |  | 34 | 25 |  | 850
19595
| Carpet Material, Labor, and Pad |  | ALLOWANCE | 230 | 81.5 | SY | 18745
| Walk Off Carpet |  | ALLOWANCE |  | 50 | SY | 0
| VCT (furnace room) |  | ALLOWANCE |  | 3 | SF | 0
| Additional Labor for Stair |  | ALLOWANCE | 34 | 25 | EA | 850
19595
9.72 | Wall Coverings/Faux Finishing
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
9.91 | Painting
|  |  |  | Ronson | Vaskelis | JWP | Company
Base Bid |  |  |  | 43402 | 120000 | 46210 | 0
1 | escalation (plugging 2%) |  |  | 2170.1 | 6000 | 2310.5
2 | garage |  |  | included |  | 4484
3 | exterior |  |  | included |  | 14200
4
5
6
7
8
9
10
|  |  | TOTAL | 45572.1 | 126000 | 67204.5 | 0

## DIV 10 SPECIALTIES
10.000 | SPECIALTIES
10.05 | Finish Hardware Allowance
Cabinet Hardware
| POWDER BATH |  | DOORS/DRAWERS |  | 0 | 10 | 0
| SERVICE ENTRY |  | DOORS/DRAWERS |  | 0 | 10 | 0
|  |  | HOOKS |  | 0 | 10 | 0
| PRIMARY BATH |  | DOORS/DRAWERS |  | 0 | 10 | 0
| PRIMARY WARDROBE |  | DOORS/DRAWERS |  | 0 | 10 | 0
| GREAT ROOM |  | DOORS/DRAWERS |  | 0 | 10 | 0
| KITCHEN ISLAND |  | DOORS/DRAWERS |  | 0 | 10 | 0
| KITCHEN |  | DOORS/DRAWERS |  | 0 | 10 | 0
|  |  | APPLIANCE PULLS |  | 0 | 350 | 0
| PANTRY |  | DOORS/DRAWERS |  | 0 | 10 | 0
| LAUNDRY |  | DOORS/DRAWERS |  | 0 | 10 | 0
| BATHROOM |  | DOORS/DRAWERS |  | 0 | 10 | 0
| BATHROOM |  | DOORS/DRAWERS |  | 0 | 10 | 0
| BATHROOM |  | DOORS/DRAWERS |  | 0 | 10 | 0
| BAR |  | DOORS/DRAWERS |  | 0 | 10 | 0
| GARAGE |  | DOORS/DRAWERS |  | 0 | 10 | 0
| OUTDOOR |  | DOORS/DRAWERS |  | 0 | 10 | 0
[6 empty] | SUBTOTAL | 0
[6 empty] | FREIGHT | 100
[6 empty] | 7% TAX | 7
[6 empty] | TOTAL | 107
Door Hardware
| LOCATION |  |  |  | QTY | UNIT COST | SUBTOTAL
Lower Level
| DOOR LEVERS (PASSAGE/PRIVACY) |  |  | Schlage Custom | 0 | 95 | 0
| DUMMIES |  |  | Schlage Custom | 0 | 445 | 0
| POCKET DOOR |  |  | Emtek | 0 | 275 | 0
| 3 1/2" HINGES - per pair |  |  |  | 0 | 14 | 0
| 4" HINGES - per pair |  |  |  | 0 | 18 | 0
| HINGE DOOR STOP |  |  |  | 0 | 10 | 0
| BASE DOOR STOP |  |  |  | 0 | 15 | 0
Main Level
| FRONT DOOR HARDWARE |  |  |  | 0 | 600 | 0
| PATIO - MULTIPOINT |  |  | Emtek | 0 | 575 | 0
| DOOR LEVERS (PASSAGE/PRIVACY) |  |  | Emtek | 0 | 187 | 0
| DEADBOLTS (AT GARAGE) |  |  | Emtek | 0 | 100 | 0
| DUMMIES |  |  | Emtek | 0 | 187 | 0
| POCKET DOOR |  |  | Emtek | 0 | 275 | 0
| BARN DOORS |  |  |  | 0 | 325 | 0
| BI-FOLD KNOBS |  |  |  | 0 | 25 | 0
| 3 1/2" HINGES - per pair |  |  |  | 0 | 14 | 0
| 4" HINGES - per pair |  |  |  | 0 | 50 | 0
| SPRING HINGE |  |  |  | 0 | 85.6 | 0
| HINGE DOOR STOP |  |  |  | 0 | 10 | 0
| BASE DOOR STOP |  |  |  | 0 | 15 | 0
| FLOOR STOP |  |  |  | 0 | 50 | 0
Upper Level
| DOOR LEVERS (PASSAGE/PRIVACY) |  |  |  | 0 | 95 | 0
| DUMMIES |  |  | Schlage Custom | 0 | 445 | 0
| POCKET DOOR |  |  | Emtek | 0 | 275 | 0
| 3 1/2" HINGES - per pair |  |  |  | 0 | 14 | 0
| 4" HINGES - per pair |  |  |  | 0 | 18 | 0
| HINGE DOOR STOP |  |  |  | 0 | 10 | 0
| BASE DOOR STOP |  |  |  | 0 | 15 | 0
[6 empty] | SUBTOTAL | 0
[6 empty] | FREIGHT | 100
[6 empty] | 7% TAX | 7
[6 empty] | TOTAL | 107
Bath Accessories
POWDER BATH
|  |  | TOILET PAPER HOLDERS |  | 0 | 75 | 0
|  |  | TOWEL RINGS |  | 0 | 75 | 0
PRIMARY BATH
|  |  | TOILET PAPER HOLDERS |  | 0 | 75 | 0
|  |  | TOWEL BARS |  | 0 | 100 | 0
|  |  | TOWEL RINGS |  | 0 | 75 | 0
|  |  | ROBE HOOKS |  | 0 | 35 | 0
BATHROOM
|  |  | TOILET PAPER HOLDERS |  | 0 | 75 | 0
|  |  | TOWEL BAR |  | 0 | 100 | 0
|  |  | TOWEL RINGS |  | 0 | 75 | 0
|  |  | ROBE HOOKS |  | 0 | 35 | 0
BATHROOM
|  |  | TOILET PAPER HOLDERS |  | 0 | 75 | 0
|  |  | TOWEL BARS |  | 0 | 100 | 0
|  |  | TOWEL RINGS |  | 0 | 75 | 0
|  |  | ROBE HOOKS |  | 0 | 35 | 0
BATHROOM
|  |  | TOILET PAPER HOLDERS |  | 0 | 75 | 0
|  |  | TOWEL BARS |  | 0 | 100 | 0
|  |  | TOWEL RINGS |  | 0 | 75 | 0
|  |  | ROBE HOOKS |  | 0 | 35 | 0
[6 empty] | SUBTOTAL | 0
[6 empty] | FREIGHT | 100
[6 empty] | 7% TAX | 7
[6 empty] | TOTAL | 107
[6 empty] | TOTAL ALL ACCESSORIES | 321
[6 empty] | TOTAL LABOR | 0
10.14 | Address Numbers
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
10.31 | Fireplaces
|  |  |  | Table Rock | Company | Company | Company
Base Bid |  |  |  | 5495 | 0 | 0 | 0
1 | equipment - hoisting |  |  | 1000
2
3 | Outdoor - Lifestyle Lanai 60 material |  |  | 4909
4 | Labor plug |  |  | 1500
5 | screen |  |  | 499
6 | drain pan |  |  | 256
7 | tax |  |  | 396.48
8
9
10
|  |  | TOTAL | 14055.48 | 0 | 0 | 0
10.314 | Fireplace Facings
[6 empty] | TOTAL | 527
PATIO | [6 empty] | 527
|  | Field Material | CKF | 1 | 527 | LS | 527
|  | Labor/Setting Materials | ALLOWANCE | 0 | 0 | SF | 0
|  | Delivery | ALLOWANCE | 0 | 0 | EA | 0
|  | Sealer | ALLOWANCE | 0 | 0 | SF | 0
|  | Precast Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Metal Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Labor - Surround | ALLOWANCE | 0 | 0 | EA | 0
Location | [6 empty] | 0
|  | Field Material | ALLOWANCE | 0 | 0 | SF | 0
|  | Labor/Setting Materials | ALLOWANCE | 0 | 0 | SF | 0
|  | Delivery | ALLOWANCE | 0 | 0 | EA | 0
|  | Sealer | ALLOWANCE | 0 | 0 | SF | 0
|  | Precast Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Metal Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Labor - Surround | ALLOWANCE | 0 | 0 | EA | 0
Location | [6 empty] | 0
|  | Field Material | ALLOWANCE | 0 | 0 | SF | 0
|  | Labor/Setting Materials | ALLOWANCE | 0 | 0 | SF | 0
|  | Delivery | ALLOWANCE | 0 | 0 | EA | 0
|  | Sealer | ALLOWANCE | 0 | 0 | SF | 0
|  | Precast Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Metal Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Labor - Surround | ALLOWANCE | 0 | 0 | EA | 0
10.562 | Storage Shelving
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
10.566 | Wine Cellar Racks/Cooling
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
10.572 | Closets
|  |  |  | Company | Company | Company | Company
Main Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
Lower Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
Upper Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
10.712 | Exterior Shutters
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0

## DIV 11 EQUIPMENT
11.000 | EQUIPMENT
11.302 | Appliances Allowance
|  |  | Ferguson | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
KITCHEN
| Kitchen hood |  | 1509
| Kitchen range |  | 12704
| Kitchen oven |  | 7099
| Kitchen STEAM OVEN |  | 8134
| Kitchen dishwasher |  | 2919
| Kitchen fridge |  | 10675.22
| Kitchen freezer |  | 9848
| built in column install |  | 380
PANTRY
| Pantry ice maker (PLUG) |  | 3000
| Pantry fridge/freezer combo |  | 2201.2
| Pantry Microwave (PLUG) |  | 750
PATIO
| Patio hood |  | 3139
| Patio grill |  | 3699
LAUNDRY
| Laundry washer main |  | 1169.86
| Laundry dryer main |  | 1265.92
| Steamer |  | 1699.98
| Laundry washer/dryer stack upstairs |  | 2299.98
| Delivery |  | 190
| SUBTOTAL |  | 72683.16
| TAX |  | 5087.8212
|  | TOTAL | 77770.9812 | 0 | 0 | 0
11.52 | TV's Allowance
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
11.66 | Athletic Equipment
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
11.678 | Game Room Equipment (Golf Simulator)
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 12 FURNISHINGS
12.000 | FURNISHINGS
12.17 | Art Glass
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
12.2 | Window Treatments
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
12.25 | Motorized Shades
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 13 SPECIAL CONST.
13.000 | SPECIAL CONSTRUCTION
13.112 | Swimming Pool
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
13.174 | Sauna
|  |  | Equinox III | Sanctuary 3 | Company | Company
Base Bid |  |  | 6999 | 8121 | 0 | 0
1 | shipping |  | 1500
2 | taxes |  | 489.94
3
4
5 | Labow |  | 1170 | 1170
6
7
8
9
10
|  | TOTAL | 10158.94 | 9291 | 0 | 0
13.26 | Storm Shelter Room(s)
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
13.342 | Screen Porch Systems
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 14 CONVEYING SYSTEMS
14.000 | CONVEYING SYSTEMS
14.05 | Elevators
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 21 FIRE SUPRESSION
21.000 | FIRE SUPPRESSION
21.05 | Fire Suppression
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 22-23 PLUM-HVAC
22.000 | PLUMBING
22.05 | Plumbing
|  |  | TNP | Walvoord | Company | Company
Base Bid |  |  | 87294.13 | 0 | 0 | 0
1 | basement breakout |  | -3968.81
2
3
4
5
6
7
8
9
10
|  | TOTAL | 83325.32 | 0 | 0 | 0
22.322 | Water Filtration System
|  |  | Futuramic | CleanWaterGuys | Company | Company
Base Bid |  |  | 0 | 6066.9 | 0 | 0
1 | water softener |  | 4263
2 | RO |  | 4289
3
4
5
6
7
8
9
10
|  | TOTAL | 8552 | 6066.9 | 0 | 0
22.4 | Plumbing Fixtures Allowance
|  | QUANITITY | UNIT COST | SUBTOTAL
KITCHEN
| SINK | 1 | 4585.5 | 4585.5
| DISPOSAL | 1 | 280.73 | 280.73
| BASKET STRAINER | 1 | 42.59 | 42.59
| FAUCET | 1 | 913.5 | 913.5
| RO FAUCET | 1 | 548.1 | 548.1
| SOAP DISPENSER | 1 | 205.54 | 205.54
| AIR SWITCH | 1 | 155.3 | 155.3
| POT FILLER | 0 | 700 | 0
GARAGE
| SINK | 1 | 139.98 | 139.98
| FAUCET | 1 | 157.5 | 157.5
| BASKET STRAINER | 0 | 70 | 0 | added
| DOG SHOWER ( faucet/hardware) | 1 | 422.95 | 422.95
LAUNDRY
| SINK | 1 | 531.19 | 531.19
| FAUCET | 1 | 635.6 | 635.6
| HANDLE | 1 | 144.9 | 144.9
| BASKET STRAINER | 1 | 162.4 | 162.4
POWDER BATH
| FAUCET | 1 | 507.5 | 507.5
| HANDLE | 1 | 203 | 203
| POPUP | 1 | 144.2 | 144.2
| SINK | 1 | 135.45 | 135.45
| TOILET | 1 | 683.11 | 683.11
| SEAT/TRIP LEVER | 1 | 61.56 | 61.56
PRIMARY BATH
| FAUCETS | 2 | 689.5 | 1379
| HANDLE | 2 | 255.5 | 511
| POPUP | 2 | 144.2 | 288.4
| SINK | 2 | 103.95 | 207.9
| SOAKER TUB | 1 | 5869.5 | 5869.5
| TUB FILLER Body | 1 | 1015.7 | 1015.7
| TUB FILLER Trim | 1 | 1208.2 | 1208.2
| TUB FILLER Unions | 1 | 1687.7 | 1687.7
| TUB FILLER Rough-in | 1 | 631.4 | 631.4
| SHOWER VALVE/TRIM | 1 | 634.2 | 634.2
| SHOWER VALVE/TRIM | 1 | 242.9 | 242.9
| SHOWER VALVE Rough in | 1 | 349.3 | 349.3
| SHOWER VALVE/TRIM | 1 | 701.4 | 701.4
| SHOWER VALVE Rough in | 1 | 464.1 | 464.1
| SHOWER HEAD 5" | 1 | 284.2 | 284.2
| SHOWER ARM | 1 | 128.1 | 128.1
| RAIN HEAD | 1 | 1166.2 | 1166.2
| SHOWER ARM | 1 | 175.7 | 175.7
| SHOWER HANDSET | 1 | 863.8 | 863.8
| DRAIN | 1 | 107.89 | 107.89
| TOILET | 1 | 683.11 | 683.11
| SEAT/TRIP LEVER | 1 | 61.56 | 61.56
BATHROOM 2
| FAUCET | 3 | 986.3 | 2958.9
| POPUP | 3 | 144.2 | 432.6
| SINK SS | 3 | 103.95 | 311.85
| SHOWER VALVE | 1 | 290.5 | 290.5
| SHOWER TRIM | 1 | 193.2 | 193.2
| SHOWER Rough in | 1 | 83.3 | 83.3
| SHOWER HEAD 5" | 1 | 284.2 | 284.2
| SHOWER ARM | 1 | 128.1 | 128.1
| DRAIN | 1 | 107.89 | 107.89
| TOILET | 1 | 683.11 | 683.11
| SEAT/TRIP LEVER | 1 | 61.56 | 61.56
BATHROOM 3
| FAUCET | 1 | 986.3 | 986.3
| POPUP | 1 | 144.2 | 144.2
| SINK SS | 1 | 103.95 | 103.95
| SHOWER VALVE | 1 | 290.5 | 290.5
| SHOWER TRIM | 1 | 193.2 | 193.2
| SHOWER Rough in | 1 | 83.3 | 83.3
| SHOWER HEAD 5" | 1 | 284.2 | 284.2
| SHOWER ARM | 1 | 128.1 | 128.1
| DRAIN | 1 | 107.89 | 107.89
| TOILET | 1 | 683.11 | 683.11
| SEAT/TRIP LEVER | 1 | 61.56 | 61.56
|  |  | SUBTOTAL | 37923.38
|  |  | FREIGHT | 375
|  |  | 7% TAX | 2680.8866
|  |  | TOTAL | 40979.2666 | BASE
AIRMADA SHOWER DRYING SYSTEM
| AIRMADA DRYING SYSTEM | 1 | 3510.5 | 3510.5
|  |  | FREIGHT | 50
|  |  | 7% TAX | 249.235
|  |  | TOTAL | 3809.735
BAR
| SINK | 1 | 358.15 | 358.15
| FAUCET | 1 | 449.4 | 449.4
| DISPOSAL | 1 | 280.73 | 280.73
| RO FAUCET | 0 | 400 | 0
| AIR SWITCH | 1 | 157.94 | 157.94
| BASKET STRAINER | 1 | 42.59 | 42.59
BASEMENT BATH
| FAUCET | 1 | 641.9 | 641.9
| FAUCET HANDLES | 1 | 238 | 238
| POPUP | 1 | 134.4 | 134.4
| SINK SS | 1 | 103.95 | 103.95
| SHOWER TRIM | 1 | 270.2 | 270.2
| SHOWER LEVER | 1 | 179.9 | 179.9
| SHOWER Rough in | 1 | 83.3 | 83.3
| SHOWER HEAD 5" | 1 | 245 | 245
| SHOWER ARM | 1 | 110.6 | 110.6
| DRAIN | 1 | 100.46 | 100.46
| TOILET | 1 | 683.11 | 683.11
| SEAT/TRIP LEVER | 1 | 55.95 | 55.95
|  |  | SUBTOTAL | 4135.58
|  |  | FREIGHT | 0
|  |  | 7% TAX | 289.4906
|  |  | TOTAL | 4425.0706 | ALTERNATE
23.000 | HVAC
23.05 | HVAC
|  |  | DK | Advanced | Company | Company
Base Bid |  |  | 62300 | 57000 | 0 | 0
1 | basement |  | not included?? | -1500
2
3
4
5
6
7
8
9
10
|  | TOTAL | 62300 | 55500 | 0 | 0
23.4 | Duct Cleaning
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 26-28 ELEC. - LV
26.000 | ELECTRICAL
26.05 | Electrical Service & Wiring
|  |  | Custom | Victory | Company | Company
Base Bid |  |  | 87275 | 56680 | 0 | 0
1 | Patio motorized screen |  | 100 | 150
2 | Lutron labor |  | 12000 | 4000
3 | garage heaters |  | 2700 | 4500
4 | deck heater |  | 2000 | 2065
5
6
7
8
9
10
|  | TOTAL | 104075 | 67395 | 0 | 0
26.41 | Lightning Protection
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
26.505 | Light Fixtures Allowance
*ALLOWANCE UNIT COSTS INCLUDE ALL BULBS
| LOCATION | TYPE |  | QTY | UNIT PRICE | SUBTOTAL
Main Level
| FOYER | CEILING MOUNT |  | 0 | 500 | 0
| DINING | CEILING MOUNT |  | 0 | 1000 | 0
| POWDER BATH | WALL MOUNT |  | 0 | 150 | 0
| KITCHEN | PENDANTS |  | 0 | 250 | 0
| GREAT ROOM | CEILING FAN |  | 0 | 400 | 0
| LAUNDRY ROOM | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| PRIMARY BEDROOM | CEILING FAN |  | 0 | 250 | 0
| PRIMARY BATHROOM | WALL MOUNT |  | 0 | 150 | 0
| PRIMARY WARDROBE | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| GUEST BEDROOM | CEILING FAN |  | 0 | 250 | 0
| GUEST BATHROOM VANITY | WALL MOUNT |  | 0 | 150 | 0
| SERVICE ENTRY | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| GARAGE | LED - by elect. |  | 0 | 0 | 0
Upper Level
| BEDROOM | CEILING FAN |  | 0 | 225 | 0
| BEDROOM | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| WARDROBE | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| BATHROOM VANITY | WALL MOUNT |  | 0 | 125 | 0
Lower Level
| BATHROOM VANITY | WALL MOUNT |  | 0 | 125 | 0
| BEDROOM | CEILING FAN |  | 0 | 225 | 0
| BEDROOM | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| WARDROBE | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| FITNESS ROOM | CEILING FAN |  | 0 | 225 | 0
| FITNESS WARDROBE | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| MECHANICAL/STORAGE | LED - by elect. |  | 0 | 0 | 0
EXTERIOR LIGHTING
| FRONT ENTRY | WALL MOUNT |  | 0 | 550 | 0
| GARAGE DOOR PIERS | WALL MOUNT |  | 0 | 300 | 0
| COVERED PATIO | CEILING FAN |  | 0 | 400 | 0
| COVERED PATIO | WALL MOUNT |  | 0 | 400 | 0
| LOWER PATIO | WALL MOUNT |  | 0 | 400 | 0
| FLOODS | WALL MOUNT - by elect. |  | 0 | 0 | 0
[5 empty] | SUBTOTAL | 0
[5 empty] | FREIGHT | 0
[5 empty] | 7% TAX | 0
[5 empty] | TOTAL (INCLUDING BULBS) | 0
26.57 | Lighting Control System Allowance
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
27.000 | COMMUNICATIONS
27.41 | Audio-Visual Systems/Structured Wire/Sound System Allowance
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
28.000 | ELECTRONIC SAFETY & SECURITY
28.07 | Security System/Fire Protection/Video Surveillance Allowance
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 31-32 EARTH-SITE
31.000 | EARTHWORK
31.218 | Site Demolition
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
31.23 | Excavation/Fill/Grading/Silt Fence
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
31.26 | Surveying
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.000 | EXTERIOR IMPROVEMENTS
32.13 | Exterior Concrete Flatwork
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
Unit Rate Estimate
Driveway |  | 1758 | SF
Front Stoop |  | 52 | SF
Front Walk |  | 217 | SF
City Sidewalks |  | 1647 | SF
AC and Pool Equip Pads |  | 107 | SF
Pool Deck |  | 1286 | SF
Rear Patio |  | 1151 | SF
|  | 6218 | SF
MATERIAL
sleeve materials (pvc for under slabs) |  |  | 3 | 75 | EA | 225
Granular (SF x .25ft x 1.25 / 18 = X tons) |  |  | 107.9514 | 16 | TON | 1727.2222
Additive (Xypex for water impermeable) |  |  | 0 | 131.85 | BOX | 0
expansion joints at walls |  |  | 3.64 | 150 | EA | 546
SUBCONTRACTOR
Driveway (5" with rebar) |  |  | 1758 | 7 | SF | 12306
Driveway Curb |  |  | 0 | 0 | LF | 0
Street Curb Cut |  |  | 72 | 25 | SF | 1800
Front Walks (4") |  |  | 217 | 6.5 | SF | 1410.5
City Sidewalks (4") |  |  | 1647 | 6.5 | SF | 10705.5
Front Stoop |  |  | 1 | 800 | EA | 800
Concrete Steps |  |  | 118 | 40 | LF | 4720
AC Pads (4") |  |  | 107 | 6.5 | SF | 695.5
Rear Patio (4") |  |  | 1151 | 6.5 | SF | 7481.5
Pool Deck (4") |  |  | 1286 | 6.5 | SF | 8359
Trench Drain |  |  | 0 | 0 | LF | 0
Paver inset areas |  |  | 0 | 0 | LF | 0
Additional Concrete Material for 5" thick |  |  | 0 | 82.5 | CY | 0
Pump Charge for elevated balconies |  |  | 2 | 1500 | EA | 3000
Grading |  |  | 6500 | 0.4 | SF | 2600
Cure & Seal |  |  | 6500 | 0.05 | SF | 325
Sealer (Application of Stifle) |  |  | 0 | 0.45 | SF | 0
[5 empty] | TOTAL | 56701.2222
32.142 | Pavers Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
Unit Rate Estimate
Driveway | 0 | SF
Front Walk | 0 | SF
Front Stoop | 0 | SF
Rear Patio | 0 | SF
Pool Deck | 0 | SF
| 0 | SF
| 0 | 8% waste
| 0 | total SFpavers
STEPPING STONES |  | 0 | EA
NOTE: verify full pallet quantities or sf count
Paver Material (incl tax) |  |  | ALLOWANCE | 0 | 6.25 | SF | 0
Bullnose Edging (lakeside nosing) |  |  | ALLOWANCE | 0 | 12 | LF | 0
Front Stoop (brick and mortar) |  |  | ALLOWANCE | 0 | 7.25 | SF | 0
Front Stoop |  |  | ALLOWANCE | 0 | 15.75 | SF | 0
Aluminum Edging |  |  | ALLOWANCE | 0 | 3.25 | LF | 0
Subcontractor Installation |  |  | ALLOWANCE | 0 | 6.75 | SF | 0
Palmeric Sand |  |  | ALLOWANCE | 0 | 1 |  | 0
additional for asphalt set |  |  | ALLOWANCE | 0 | 1.75 | SF | 0
Stepping Stones |  |  | ALLOWANCE | 0 | 100 | EA | 0
[6 empty] | TOTAL | 0
OPTION
Sealer / Enhancer |  |  | ALLOWANCE | 0 | 1.5 | SF | 0
32.18 | Athletic/Recreational Surfacing
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.181 | Artificial Turf
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.3 | Landscape Lighting Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.31 | Fences/Gates
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.32 | Retaining Walls Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.392 | Fire Pit Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.394 | Exterior Grill/Hood
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.8 | Irrigation Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.922 | Seeding/Sod Allowance
raw area - 20500sf
| Sod | 22000 | SF | 0.375 | 8250 | 8250
| (less beds) |  |  |  | 5.5% TAX | 453.75
| FINE GRADE/TOPSOIL |  |  |  |  | 3750
[5 empty] | TOTAL | 12453.75
[5 empty] | allowance | 12500
32.931 | Landscaping Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0

## DIV 33 UTILITES
33.000 | UTILITIES
33.02 | Sewer / Water Utilities
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
33.462 | Underground Buried Drainage
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0