## A
CONTRACTOR'S APPLICATION FOR PAYMENT
TO (OWNER): |  | Phil & Michelle Wood |  |  |  |  | APPLICATION NO.: | 5
PROJECT: |  | Wood Residence |  |  |  |  | APPLICATION DATE: | 2026-06-22
FROM (CONTRACTOR): |  | McNeil Company |  |  |  |  | PAYMENT DUE DATE: | 2026-06-28
CONTRACT FOR: |  | Phil & Michelle Wood
CHANGE ORDER SUMMARY
|  |  |  | CHANGES APPROVED PREVIOUS | CHANGES APPROVED THIS PERIOD | Application is made for Payment, as shown below, in connection with the Contract Continuation Sheet, B, is attached.
Number | Description |  |  | Value | Value
1 | Renovate LL bathrooms (Powder & #4) |  |  | 50903 |  | ORIGINAL CONTRACT SUM |  |  | 1459923.14
2 | Remove Primary Bed fireplace/facings and modify framing of this wall; paint frames & doors of Hearth & Great Room fireplaces in lieu of brand new frames & doors |  |  | -16706 |  | NET CHANGE BY CHANGE ORDERS |  |  | 103079
3 | Add trim mouldings/crown, lower level bedroom ceiling textures & framing down ceiling in Bed 5 |  |  | 10000 |  | CONTRACT SUM TO DATE |  |  | 1563002.14
4 | Upgrade Primary Suite doors to 90" in lieu of 84" |  |  | 2403 |  | TOTAL BILLED TO DATE |  |  | 175460
5 | Water Treatment - new soft water unit, whole house filtration system |  |  | 4640
6 | Crestron Lighting Control system |  |  | 29003 |  | CURRENT PAYMENT DUE |  |  | 38508.6707
7 | Hearth Room Cabinetry/Fireplace Facing |  |  | 20118
8 | Water Treatment - add RO system to Kitchen ($1951 Clean Water Guys, $767 Plumber) |  |  | 2718 |  | BALANCE TO FINISH, INCLUDING FEE |  |  | 1349033.4693
9
10
11
12
13
14
15
16
17
|  |  | TOTAL | 103079 | 0
|  |  |  | NET CHANGE BY CHANGE ORDERS | 103079

## B
CONTRACT CONTINUATION SHEET B
[5 empty] | APPLICATION NUMBER: |  |  |  | 5
[5 empty] | APPLICATION DATE: |  |  |  | 2026-06-22
[5 empty] | PAYMENT DUE DATE: |  |  |  | 2026-06-28
A | B | C | D | MCNEIL | E | MCNEIL TEAM |  |  | F | G | MCNEIL TEAM | [11 empty] | H
ITEM | DESCRIPTION OF WORK | ORIGINAL | CHANGE | CHANGE | CURRENT | TOTAL | ACCRUAL | ACCRUAL | TOTAL | TOTAL | Pay App #12 | Pay App #11 | Pay App #10 | Pay App #9 | Pay App #8 | Pay App #7 | Pay App #6 | Pay App #5 | Pay App #4 | Pay App #3 | Pay App #2 | Pay App #1 | BALANCE
NO |  | SCHEDULED | ORDER | ORDER | SCHEDULED | INVOICED | AMOUNT | DESCRIPTION | COMPLETED | PREVIOUS | [12 empty] | TO FINISH
|  | VALUE | VALUE | DESCRIPTION | VALUE | THIS PERIOD | THIS PERIOD |  | THIS PERIOD | COST
01-000 | General Requirements
01-120 | Superintendent | 53056 | 1360 | CO1 $1360 | 54416 | 948.2 |  |  | 948.2 | 18110 | [8 empty] | 1300 | 6518 | 5281 | 5011 | 35357.8
01-170 | Travel/Pickup/Delivery | 1690 | 150 | CO1 $150 | 1840 | 108.8 |  |  | 108.8 | 2886 | [8 empty] | 134 | 335 | 1525 | 892 | -1154.8
01-205 | MUD Fees | 0 | 0 |  | 0 |  |  |  | 0 | 0 | [8 empty] | 0 |  | 0 | 0 | 0
01-214 | Permits | 2400 | 0 |  | 2400 | 0 |  |  | 0 | 1379 | [8 empty] | 0 |  | 0 | 1379 | 1021
01-230 | Builder's Risk | 1443 | 64 | CO1 $64 | 1507 | 125.5833 |  |  | 125.5833 | 504 | [8 empty] | 126 | 126 | 126 | 126 | 877.4167
01-235 | General Liability | 2806 | 123 | CO1 $123 | 2929 | 244.0833 |  |  | 244.0833 | 976 | [8 empty] | 244 | 244 | 244 | 244 | 1708.9167
01-253 | Safety Supplies | 430 | 60 | CO1 $60 | 490 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 490
01-454 | Mockups | 0 | 0 |  | 0 | 321.02 |  |  | 321.02 | 677 | [8 empty] | 0 | 677 | 0 | 0 | -998.02
01-501 | Temporary Utilities & Toilets | 0 | 0 |  | 0 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
01-531 | Technology | 1275 | 0 |  | 1275 | 106.25 |  |  | 106.25 | 424 | [8 empty] | 106 | 106 | 106 | 106 | 744.75
01-560 | Temporary Barries/Enclosures | 6750 | 810 | CO1 $810 | 7560 | 0.34 |  |  | 0.34 | 5372 | [8 empty] | 0 | -339 | 110 | 5601 | 2187.66
01-740 | Cleaning & Waste Management | 20647 | 963 | CO1 $963 | 21610 | 127.95 |  |  | 127.95 | 6471 | [8 empty] | 635 | 2007 | 2449 | 1380 | 15011.05
01-810 | Warranties | 6471 | 264 | CO1 $264 | 6735 | 561.25 |  |  | 561.25 | 2244 | [8 empty] | 561 | 561 | 561 | 561 | 3929.75
01-830 | Small Tools/Supplies/Rental | 2060 | 75 | CO1 $75 | 2135 | 94.56 |  |  | 94.56 | 624 | [8 empty] | 27 | 299 | 83 | 215 | 1416.44
01-840 | Punchlist | 4700 | 300 | CO1 $300 | 5000 |  |  |  | 0 | 0 | [8 empty] | 0 |  | 0 | 0 | 5000
02-000 | Existing Conditions
02-010 | Demolition | 19030 | 1210 | CO1 $730 / CO7 $480 | 20240 | 303.86 |  |  | 303.86 | 21946 | [8 empty] | 113 | 972 | 1116 | 19745 | -2009.86
04-000 | Masonry
04-210 | Brick Masonry (repair) | 900 | 0 |  | 900 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 900
05-000 | Metal
05-120 | Structural Steel - Material | 0 | 0 |  | 0 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
06-000 | Carpentry
06-110 | Wood Framing | 35000 | 660 | CO3 $660 | 35660 | 825.8 |  | accrual Klassen total (3000+6000) | 825.8 | 26123 | [8 empty] | 2555 | 8346 | 10056 | 5166 | 8711.2
06-380 | Cabinetry Allowance | 154190 | 14548 | CO1 $5048 / CO7 $9500 | 168738 | 0.01 |  |  | 0.01 | 16312 | [8 empty] | 8 | 0 | 0 | 16304 | 152425.99
06-460 | Wood Interior Trim | 56095 | 4197 | CO3 $3601 / CO7 $596 | 60292 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 60292
06-612 | Countertop Allowance | 60872 | 4963 | CO1 $4963 | 65835 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 65835
07-000 | Moisture/Thermal Protection
07-130 | Waterproofing | 0 | 0 |  | 0 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
07-210 | Insulation | 8825 | 0 |  | 8825 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 8825
08-000 | Doors/Windows/Glazing
08-140 | Interior Wood Doors | 11003 | 1806 | CO4 $1806 | 12809 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 12809
08-178 | Front Door | 24678 | 0 |  | 24678 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 24678
08-500 | Windows - existing | 0 | 0 |  | 0 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
08-817 | Mirrors/Glass Inserts | 17689 | 4626 | CO1 $3616 / CO7 $1010 | 22315 | -0.07 |  |  | -0.07 | 1604 | [8 empty] | 1604 | 0 | 0 | 0 | 20711.07
09-000 | Finishes
09-200 | Drywall | 21099 | 3810 | CO1 $780 / CO3 $3030 | 24909 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 24909
09-300 | Tile | [17 empty] | 0 | 0
| Floor Tile | 44349 | 2200 | CO1 $2200 | 46549 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 46549
| Tile Backsplash | 5589 | 0 |  | 5589 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 5589
| Wall Tile/Columns | 0 | 0 |  | 0 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
| Shower/Tub Tile | 30137 | 6560 | CO1 $6560 | 36697 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 36697
09-640 | Wood Flooring | 10942 | 0 |  | 10942 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 10942
09-672 | Epoxy Flooring | 0 | 0 |  | 0 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
09-680 | Carpeting | 60538 | 0 |  | 60538 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 60538
09-720 | Wall Coverings/Faux Finishing | 0 | 0 |  | 0 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
09-910 | Painting | 135345 | 6935 | CO1 $3000 / CO3 $1320 / CO4 $115 / CO7 $2500 | 142280 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 142280
10-000 | Specialties
10-050 | Finish Hardware Allowance | 24458 | 1757.34 | CO1 $1479 / CO4 $115 / CO7 $163 | 26215.34 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 26215.34
10-310 | Fireplaces | 12155 | -11555 | CO2 -$11555 | 600 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 600
10-314 | Fireplace Facings Allowance | 7340 | 197 | CO2 -$2603 / CO7 $2800 | 7537 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 7537
10-562 | Storage Shelving | 3694 | 0 |  | 3694 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 3694
10-572 | Closet Allowance | 28438 | 0 |  | 28438 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 28438
11-000 | Architectural Equipment
11-302 | Residential Appliance Allowance | 49697 | 0 |  | 49697 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 49697
11-520 | TV's | 3294 | 0 |  | 3294 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 3294
12-000 | Furnishings
12-250 | Motorized Shades | 0 | 0 |  | 0 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0
13-000 | Special Construction
13-174 | Sauna | 9291 | 0 |  | 9291 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 9291
14-000 | Conveying Systems
22-000 | Plumbing
22-050 | Plumbing | 23770 | 1700 | CO1 $1050 / CO8 $650 | 25470 |  |  |  | 0 | 5200 | [8 empty] | 0 | 2700 | 2500 | 0 | 20270
22-322 | Water Filtration System | 0 | 5585.4 | CO5 $3932.25 / CO8 $1653.15 | 5585.4 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 5585.4
22-400 | Plumbing Fixtures | 25834 | 3364 | CO1 $3364 | 29198 | 0.24 |  |  | 0.24 | 5956 | [8 empty] | 5053 | 903 | 0 | 0 | 23241.76
23-000 | HVAC
23-050 | HVAC | 16402 | 0 |  | 16402 | -0.41 |  |  | -0.41 | 7863 | [8 empty] | 0 | 4650 | 3000 | 213 | 8539.41
23-400 | Duct Cleaning | 4450 | 100 | CO1 $100 | 4550 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 4550
26-000 | Electrical
26-050 | Electrical | 47805 | 6220 | CO1 $940 / CO2 $5280 | 54025 | -10000 | 38867 | Custom accrual per email 7/20/2026 | 28867 | 13590 | [8 empty] | 10000 | 0 | 980 | 2610 | 11568
26-505 | Light Fixtures Allowance | 67119 | 2889 | CO1 $2889 | 70008 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 70008
26-570 | Lighting Control System | 0 | 19298.33 | CO6 $19298.33 | 19298.33 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 19298.33
27-000 | Communications
27-410 | AV Systems/Structured Wire Allow. | 56029 | 0 |  | 56029 | 0 |  |  | 0 | 10434 | [8 empty] | 0 | 0 | 0 | 10434 | 45595
28-000 | Electronic Safety & Security
28-070 | Security System Allowance | 2750 | 0 |  | 2750 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 2750
50-050 | Contingency | 54188 | 2250 | CO1 $2250 | 56438 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 56438
| Arch/Engr Fees (Separate Agreement) | 500 | 0 |  | 500 |  |  |  | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 500
| Contractor's Fee | 222700.14 | 15748.2126 | CO1 $7764.90 / CO2 -$2548.44 / CO3 $1389 / CO4 $366.48 / CO6 $4424 / CO7 $3068.82 CO8 $414.93 | 238448.3526 |  |  |  | 5874.204 | 26765 | [8 empty] | 4044 | 5059 | 5065 | 12597 | 205809.1486
| TOTALS | 1459923.14 | 103238.2826 |  | 1563161.4226 | -6232.5333 | 38867 | 0 | 38508.6707 | 175460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26510 | 33164 | 33202 | 82584 | 1349192.7519
[19 empty] | 26510 | 33164 | 33202 | 82583
change order #3 - $10,000 even when added up together with fee already included, but $10,161 when added up then add fee. $160 is the difference from $51,240 on front sheet to $51,400

## LABOR JTD 7.21.2026
Wood Residence
2-2513
JTD Labor | 2026-07-21
Cost Code | Description | JTD Total Labor Hours | Employee | Billable Hours | Billing Rate | Total Billable Cost | Job Cost Report Total | Billing Difference
01-000 | GENERAL REQUIREMENTS
01-117 | Project Engineer Intern | 0 |  | 0 | 0 | 0 |  | 0
01-120 | Superintendent | 220.72 |  | 220.72 | 85 | 18761.2 | 15480.06 | 3416.03
|  |  | Ron Milhan - 197 | 220.72 | 85 | 18761.2
|  |  | Chris Magner | 0 | 90
01-125 | Assistant Superintendent | 5.94 |  | 5.94 | 75 | 297 | 162.11
|  |  | Ron Townsend - 178 | 0 | 60 | 0
|  |  | Max Fuerstenau - 204 | 0 | 60 | 0
|  |  | Austin Stroh - 242 | 5.07 | 50 | 253.5
|  |  | Braden Dall - 239 | 0.87 | 50 | 43.5
|  |  | Caleb Fossenbarger - 235 | 0 | 50 | 0
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
01-130 | Project Manager | 303 |  | 0 | 0 | 0 | 18818.47 | -18818.47
01-140 | Estimator | 116 |  | 0 | 0 | 0 | 6732.54 | -6732.54
01-170 | Travel/Pickup/Deliveries | 58.36 |  | 58.36 |  | 2994.8 | 1498.68 | 1496.12
|  |  | Ron Townsend - 178 | 0 | 60 | 0
|  |  | Max Fuerstenau - 204 | 7.68 | 60 | 460.8
|  |  | Austin Stroh - 242 | 18.81 | 50 | 940.5
|  |  | Braden Dall - 239 | 9.58 | 50 | 479
|  |  | Caleb Fossenbarger - 235 | 5.64 | 50 | 282
|  |  | Nathan Milhan - 233 | 16.65 | 50 | 832.5
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
01-454 | Mockups | 15.6 |  | 15.6 |  | 872.8 | 582.37 | 290.43
|  |  | Ron Townsend - 178 | 3.93 | 60 | 235.8
|  |  | Max Fuerstenau - 204 | 5.35 | 60 | 321
|  |  | Austin Stroh - 242 | 0 | 50 | 0
|  |  | Braden Dall - 239 | 2 | 50 | 100
|  |  | Caleb Fossenbarger - 235 | 0 | 50 | 0
|  |  | Nathan Milhan - 233 | 4.32 | 50 | 216
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
01-560 | Temp Barriers/Enclosures | 73.79 |  | 73.79 |  | 4050.6 | 2311.23 | 1739.37
|  |  | Ron Townsend - 178 | 6.55 | 60 | 393
|  |  | Max Fuerstenau - 204 | 24.99 | 60 | 1499.4
|  |  | Austin Stroh - 242 | 27.99 | 50 | 1399.5
|  |  | Braden Dall - 239 | 8.69 | 50 | 434.5
|  |  | Caleb Fossenbarger - 235 | 1 | 50 | 50
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 4.57 | 60 | 274.2
01-740 | Cleaning & Waste Management | 62.97 |  | 62.97 |  | 3312.9 | 1650.6 | 1662.3
|  |  | Ron Townsend - 178 | 0 | 60 | 0
|  |  | Max Fuerstenau - 204 | 16.44 | 60 | 986.4
|  |  | Austin Stroh - 242 | 14.49 | 50 | 724.5
|  |  | Braden Dall - 239 | 24.59 | 50 | 1229.5
|  |  | Caleb Fossenbarger - 235 | 7.45 | 50 | 372.5
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
| from 18-030 | 0 |  | 0
|  | 856.38 |  | 431.44 |  | 57265.7 | 47236.06
02-0000 | EXISTING CONDITIONS
02-010 | Demolition | 124.01 |  | 124.01 |  | 6603.8 | 3377.02 | 3226.78
|  |  | Ron Townsend - 178 | 7.88 | 60 | 472.8
|  |  | Max Fuerstenau - 204 | 32.45 | 60 | 1947
|  |  | Austin Stroh - 242 | 38.39 | 50 | 1919.5
|  |  | Braden Dall - 239 | 32.07 | 50 | 1603.5
|  |  | Caleb Fossenbarger - 235 | 13.22 | 50 | 661
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
|  | 124.01 |  | 124.01 |  | 6603.8 | 3377.02
06-0000 | CARPENTRY
06-110 | Wood Framing | 183.56 |  | 183.56 |  | 9679.9 | 5115.16 | 4564.74
|  |  | Ron Townsend - 178 | 17.15 | 60 | 1029
|  |  | Max Fuerstenau - 204 | 33.04 | 60 | 1982.4
|  |  | Austin Stroh - 242 | 59.26 | 50 | 2963
|  |  | Braden Dall - 239 | 42.38 | 50 | 2119
|  |  | Caleb Fossenbarger - 235 | 28.31 | 50 | 1415.5
|  |  | Nathan Milhan - 233 | 3.42 | 50 | 171
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
|  | 183.56 |  | 183.56 |  | 9679.9 | 5115.16
00-0000 | PHASE
[5 empty] | 0 | 0 |  | 0
|  | 0 |  | 0 |  | 0 | 0
00-0000 | PHASE
[5 empty] | 0 | 0 |  | 0
|  | 0 |  | 0 |  | 0 | 0
|  | 1163.95 |  | 739.01 |  | 73549.4 | 55728.24

## LABOR JTD 6.18.2026
Wood Residence
2-2513
JTD Labor | 2026-06-18
Cost Code | Description | JTD Total Labor Hours | Employee | Billable Hours | Billing Rate | Total Billable Cost | Job Cost Report Total | Billing Difference
01-000 | GENERAL REQUIREMENTS
01-117 | Project Engineer Intern | 0 |  | 0 | 0 | 0 |  | 0
01-120 | Superintendent | 209.57 |  | 209.57 | 85 | 17813.45 | 14676.4 | 3271.94
|  |  | Ron Milhan - 197 | 209.57 | 85 | 17813.45
|  |  | Chris Magner | 0 | 90
01-125 | Assistant Superintendent | 5.94 |  | 5.94 | 75 | 297 | 162.11
|  |  | Ron Townsend - 178 | 0 | 60 | 0
|  |  | Max Fuerstenau - 204 | 0 | 60 | 0
|  |  | Austin Stroh - 242 | 5.07 | 50 | 253.5
|  |  | Braden Dall - 239 | 0.87 | 50 | 43.5
|  |  | Caleb Fossenbarger - 235 | 0 | 50 | 0
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
01-130 | Project Manager | 233.5 |  | 0 | 0 | 0 | 11374.58 | -11374.58
01-140 | Estimator | 116 |  | 0 | 0 | 0 | 6732.54 | -6732.54
01-170 | Travel/Pickup/Deliveries | 56.19 |  | 56.19 |  | 2886.3 | 1458.77 | 1427.53
|  |  | Ron Townsend - 178 | 0 | 60 | 0
|  |  | Max Fuerstenau - 204 | 7.68 | 60 | 460.8
|  |  | Austin Stroh - 242 | 18.64 | 50 | 932
|  |  | Braden Dall - 239 | 7.58 | 50 | 379
|  |  | Caleb Fossenbarger - 235 | 5.64 | 50 | 282
|  |  | Nathan Milhan - 233 | 16.65 | 50 | 832.5
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
01-454 | Mockups | 10.25 |  | 10.25 |  | 551.8 | 350.91 | 200.89
|  |  | Ron Townsend - 178 | 3.93 | 60 | 235.8
|  |  | Max Fuerstenau - 204 |  | 60 | 0
|  |  | Austin Stroh - 242 |  | 50 | 0
|  |  | Braden Dall - 239 |  | 50 | 0
|  |  | Caleb Fossenbarger - 235 | 2 | 50 | 100
|  |  | Nathan Milhan - 233 | 4.32 | 50 | 216
|  |  | TJ Ingram |  | 75 | 0
|  |  | Jo Nutter - 188 |  | 60 | 0
01-560 | Temp Barriers/Enclosures | 73.79 |  | 73.79 |  | 4050.6 | 2310.87 | 1739.73
|  |  | Ron Townsend - 178 | 6.55 | 60 | 393
|  | moved .92 from 18-030 to 01-560 | Max Fuerstenau - 204 | 24.99 | 60 | 1499.4
|  |  | Austin Stroh - 242 | 27.99 | 50 | 1399.5
|  |  | Braden Dall - 239 | 8.69 | 50 | 434.5
|  |  | Caleb Fossenbarger - 235 | 1 | 50 | 50
|  |  | Nathan Milhan - 233 |  | 50 | 0
|  |  | TJ Ingram |  |  | 0
|  |  | Jo Nutter - 188 | 4.57 | 60 | 274.2
01-740 | Cleaning & Waste Management | 62.97 |  | 62.97 |  | 3312.9 | 1650.6 | 1662.3
|  |  | Ron Townsend - 178 |  | 60 | 0
|  |  | Max Fuerstenau - 204 | 16.44 | 60 | 986.4
|  |  | Austin Stroh - 242 | 14.49 | 50 | 724.5
|  |  | Braden Dall - 239 | 24.59 | 50 | 1229.5
|  |  | Caleb Fossenbarger - 235 | 7.45 | 50 | 372.5
|  |  | Nathan Milhan - 233 |  | 50 | 0
|  |  | TJ Ingram |  | 75 | 0
|  |  | Jo Nutter - 188 |  | 60 | 0
| from 18-030 | 0 |  | 0
|  | 768.21 |  | 412.77 |  | 54511.2 | 38716.78
02-0000 | EXISTING CONDITIONS
02-010 | Demolition | 118.41 |  | 118.41 |  | 6299.5 | 3180.94 | 3118.56
|  |  | Ron Townsend - 178 | 5.45 | 60 | 327
|  |  | Max Fuerstenau - 204 | 32.45 | 60 | 1947
|  |  | Austin Stroh - 242 | 37.22 | 50 | 1861
|  |  | Braden Dall - 239 | 30.07 | 50 | 1503.5
|  |  | Caleb Fossenbarger - 235 | 13.22 | 50 | 661
|  |  | Nathan Milhan - 233 |  | 50 | 0
|  |  | TJ Ingram |  | 75 | 0
|  |  | Jo Nutter - 188 |  | 60 | 0
|  | 118.41 |  | 118.41 |  | 6299.5 | 3180.94
06-0000 | CARPENTRY
06-110 | Wood Framing | 176.03 |  | 176.03 |  | 9228.1 | 4789.39 | 4438.71
|  |  | Ron Townsend - 178 | 17.15 | 60 | 1029
|  |  | Max Fuerstenau - 204 | 25.51 | 60 | 1530.6
|  |  | Austin Stroh - 242 | 59.26 | 50 | 2963
|  |  | Braden Dall - 239 | 42.38 | 50 | 2119
|  |  | Caleb Fossenbarger - 235 | 28.31 | 50 | 1415.5
|  |  | Nathan Milhan - 233 | 3.42 | 50 | 171
|  |  | TJ Ingram |  | 75 | 0
|  |  | Jo Nutter - 188 |  | 60 | 0
|  | 176.03 |  | 176.03 |  | 9228.1 | 4789.39
00-0000 | PHASE
[5 empty] | 0 | 0 |  | 0
|  | 0 |  | 0 |  | 0 | 0
00-0000 | PHASE
[5 empty] | 0 | 0 |  | 0
|  | 0 |  | 0 |  | 0 | 0
|  | 1062.65 |  | 707.21 |  | 70038.8 | 46687.11

## LABOR JTD 5.15.2026
Wood Residence
2-2513
JTD Labor | 2026-05-15
Cost Code | Description | JTD Total Labor Hours | Employee | Billable Hours | Billing Rate | Total Billable Cost | Job Cost Report Total | Billing Difference
01-000 | GENERAL REQUIREMENTS
01-117 | Project Engineer Intern | 0 |  | 0 | 0 | 0 |  | 0
01-120 | Superintendent | 194.27 |  | 194.27 | 85 | 16512.95 | 13573.64 | 3074.2
|  |  | Ron Milhan | 194.27 | 85 | 16512.95
|  |  | Chris Magner | 0 | 90
01-125 | Assistant Superintendent | 5.94 |  | 5.94 | 75 | 297 | 162.11
|  |  | Ron Townsend | 0 | 60 | 0
|  |  | Max Fuerstenau | 0 | 60 | 0
|  |  | Austin Stroh | 5.07 | 50 | 253.5
|  |  | Braden Dall | 0.87 | 50 | 43.5
|  |  | Caleb Fossenbarger | 0 | 50 | 0
|  |  | Nathan Milhan | 0 | 50 | 0
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter | 0 | 60 | 0
01-130 | Project Manager | 184.5 |  | 0 | 0 | 0 | 11374.58 | -11374.58
01-140 | Estimator | 116 |  | 0 | 0 | 0 | 6732.54 | -6732.54
01-170 | Travel/Pickup/Deliveries | 51.76 |  | 51.76 |  | 2664.8 | 1316.48 | 1348.32
|  |  | Ron Townsend | 0 | 60 | 0
|  |  | Max Fuerstenau | 7.68 | 60 | 460.8
|  |  | Austin Stroh | 16.09 | 50 | 804.5
|  |  | Braden Dall | 7.58 | 50 | 379
|  |  | Caleb Fossenbarger | 3.76 | 50 | 188
|  |  | Nathan Milhan | 16.65 | 50 | 832.5
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter | 0 | 60 | 0
01-454 | Mockups | 10.25 |  | 10.25 |  | 551.8 | 350.91 | 200.89
|  |  | Ron Townsend | 3.93 | 60 | 235.8
|  |  | Max Fuerstenau |  | 60 | 0
|  |  | Austin Stroh |  | 50 | 0
|  |  | Braden Dall |  | 50 | 0
|  |  | Caleb Fossenbarger | 2 | 50 | 100
|  |  | Nathan Milhan | 4.32 | 50 | 216
|  |  | TJ Ingram |  | 75 | 0
|  |  | Jo Nutter |  | 60 | 0
01-560 | Temp Barriers/Enclosures | 73.79 |  | 73.79 |  | 4050.6 | 2310.87 | 1739.73
|  |  | Ron Townsend | 6.55 | 60 | 393
|  | moved .92 from 18-030 to 01-560 | Max Fuerstenau | 24.99 | 60 | 1499.4
|  |  | Austin Stroh | 27.99 | 50 | 1399.5
|  |  | Braden Dall | 8.69 | 50 | 434.5
|  |  | Caleb Fossenbarger | 1 | 50 | 50
|  |  | Nathan Milhan |  | 50 | 0
|  |  | TJ Ingram |  |  | 0
|  |  | Jo Nutter | 4.57 | 60 | 274.2
01-740 | Cleaning & Waste Management | 62.97 |  | 62.97 |  | 3312.9 | 1650.6 | 1662.3
|  |  | Ron Townsend |  | 60 | 0
|  |  | Max Fuerstenau | 16.44 | 60 | 986.4
|  |  | Austin Stroh | 14.49 | 50 | 724.5
|  |  | Braden Dall | 24.59 | 50 | 1229.5
|  |  | Caleb Fossenbarger | 7.45 | 50 | 372.5
|  |  | Nathan Milhan |  | 50 | 0
|  |  | TJ Ingram |  | 75 | 0
|  |  | Jo Nutter |  | 60 | 0
| from 18-030 | 0 |  | 0
|  | 699.48 |  | 393.04 |  | 51467.2 | 37471.73
02-0000 | EXISTING CONDITIONS
02-010 | Demolition | 116.14 |  | 116.14 |  | 6186 | 3116 | 3070
|  |  | Ron Townsend | 5.45 | 60 | 327
|  |  | Max Fuerstenau | 32.45 | 60 | 1947
|  |  | Austin Stroh | 37.22 | 50 | 1861
|  |  | Braden Dall | 30.07 | 50 | 1503.5
|  |  | Caleb Fossenbarger | 10.95 | 50 | 547.5
|  |  | Nathan Milhan |  | 50 | 0
|  |  | TJ Ingram |  | 75 | 0
|  |  | Jo Nutter |  | 60 | 0
|  | 116.14 |  | 116.14 |  | 6186 | 3116
06-0000 | CARPENTRY
06-110 | Wood Framing | 157.88 |  | 157.88 |  | 8241.4 | 4123.07 | 4118.33
|  |  | Ron Townsend | 17.15 | 60 | 1029
|  |  | Max Fuerstenau | 17.59 | 60 | 1055.4
|  |  | Austin Stroh | 52.31 | 50 | 2615.5
|  |  | Braden Dall | 41.4 | 50 | 2070
|  |  | Caleb Fossenbarger | 26.01 | 50 | 1300.5
|  |  | Nathan Milhan | 3.42 | 50 | 171
|  |  | TJ Ingram |  | 75 | 0
|  |  | Jo Nutter |  | 60 | 0
|  | 157.88 |  | 157.88 |  | 8241.4 | 4123.07
00-0000 | PHASE
[5 empty] | 0 | 0 |  | 0
|  | 0 |  | 0 |  | 0 | 0
00-0000 | PHASE
[5 empty] | 0 | 0 |  | 0
|  | 0 |  | 0 |  | 0 | 0
|  | 973.5 |  | 667.06 |  | 65894.6 | 44710.8

## LABOR JTD 4.10.2026
Wood Residence
2-2513
JTD Labor | 2026-04-10
Cost Code | Description | JTD Total Labor Hours | Billable Hours | Billing Rate | Total Billable Cost | Job Cost Report Total | Billing Difference
01-000 | GENERAL REQUIREMENTS
01-117 | Project Engineer Intern | 0 | 0 | 0 | 0 |  | 0
01-120 | Superintendent | 121.08 | 121.08 | 85 | 10291.8 | 8306.01 | 1985.79
01-125 | Assistant Superintendent | 0 | 0 | 0 | 0 | 0 | 0
01-130 | Project Manager | 105 | 0 | 0 | 0 | 6250.04 | -6250.04
01-140 | Estimator | 116 | 0 | 0 | 0 | 6732.54 | -6732.54
01-170 | Travel/Pickup/Deliveries | 38.81 | 38.81 | 60 | 2328.6 | 1006.93 | 1321.67
01-171 | Mockups | 10.25 | 10.25 | 60 | 615 | 350.91 | 264.09
01-560 | Temp Barriers/Enclosures | 71.43 | 71.43 | 60 | 4388.6592 | 2223.59 | 2165.0692
| from 18-030 | 1.44 | 1.44
01-740 | Cleaning & Waste Management | 34.71 | 34.71 | 60 | 2132.5824 | 989.49 | 1143.0924
| from 18-030 | 1.44 | 1.44
|  | 500.16 | 279.16 |  | 19756.6416 | 25859.51
02-0000 | EXISTING CONDITIONS
02-010 | Demolition | 86.92 | 86.92 | 60 | 5215.2 | 2481.98 | 2733.22
|  | 86.92 | 86.92 |  | 5215.2 | 2481.98
06-0000 | PHASE
06-110 | Wood Framing | 77.09 | 77.09 | 60 | 4625.4 | 2180.48 | 2444.92
|  | 77.09 | 77.09 |  | 4625.4 | 2180.48
00-0000 | PHASE
|  |  |  | 0 | 0 |  | 0
|  | 0 | 0 |  | 0 | 0
00-0000 | PHASE
|  |  |  | 0 | 0 |  | 0
|  | 0 | 0 |  | 0 | 0

## LABOR JTD 3.7.2026
Wood Residence
2-2513
JTD Labor | 2026-03-07
Cost Code | Description | JTD Total Labor Hours | Billable Hours | Billing Rate | Total Billable Cost | Job Cost Report Total | Billing Difference
01-000 | GENERAL REQUIREMENTS
01-117 | Project Engineer Intern | 0 | 0 | 0 | 0 |  | 0
01-120 | Superintendent | 58.95 | 58.95 | 85 | 5010.75 | 4043.93 | 966.82
01-125 | Assistant Superintendent | 0 | 0 | 0 | 0 | 0 | 0
01-130 | Project Manager | 49 | 0 | 0 | 0 | 2943.25 | -2943.25
01-140 | Estimator | 116 | 0 | 0 | 0 | 6732.54 | -6732.54
01-170 | Travel/Pickup/Deliveries | 12 | 12 | 60 | 804 | 366.09 | 437.91
| from 18-030 | 7 | 7
01-560 | Temp Barriers/Enclosures | 59.43 | 59.43 | 60 | 4278.96 | 2010.58 | 2268.38
| from 18-030 | 12 | 12
01-740 | Cleaning & Waste Management | 6.94 | 6.94 | 60 | 527.44 | 117.98 | 409.46
| from 18-030 | 16 | 16
|  | 337.32 | 172.32 |  | 10621.15 | 16214.37
02-0000 | EXISTING CONDITIONS
02-010 | Demolition | 69.54 | 69.54 | 60 | 4698.8178 | 2104.69 | 2594.1278
| from 18-030 | 7.57 | 7.57
|  | 69.54 | 69.54 |  | 4698.8178 | 2104.69
00-0000 | PHASE
|  |  |  | 0 | 0 |  | 0
|  | 0 | 0 |  | 0 | 0
00-0000 | PHASE
|  |  |  | 0 | 0 |  | 0
|  | 0 | 0 |  | 0 | 0
00-0000 | PHASE
|  |  |  | 0 | 0 |  | 0
|  | 0 | 0 |  | 0 | 0