## PROJECT SUMMARY
PROJECT COST SUMMARY
PROJECT | Hogan Residence
PROJECT MANAGER | [7 empty] | LOWER LEVEL | 2072
LOCATION | 811 N 143rd Plaza, Omaha, NE 68154 | [6 empty] | MAIN LEVEL | 2867
DATE | July 2026 | [6 empty] | TOTAL FINISHED SF | 4939
LOT # | 21 | [6 empty] | GARAGE | 756
ZONING | [7 empty] | LOWER UNFINISHED | 1567
[8 empty] | COVERED PATIO | 380
[8 empty] | TOTAL SF UNDER ROOF | 7642
PHASE | DESCRIPTION | ALLOW. | LABOR | MATERIAL | OTHER | SUBCONT. | DIVISION | FINISHED COST/SF | UNDER ROOF | Deposit | Lot | Pay App #1 | Pay App #2 | Pay App #3 | Pay App #4 | Pay App #5 | Pay App #6 | Pay App #7 | Pay App #8 | Pay App #9 | Pay App #10 | Pay App #11 | Pay App #12 | Pay App #13 | Pay App #14 | Pay App #15 | Pay App #16 | Pay App #17
1 | GENERAL REQUIREMENTS |  |  |  |  | TOTAL | 159593 | 32.3128 | 20.8837 | [19 empty] | 0
01.120 | Superintendent | 0 | 70125 | 0 | 0 | 0 | 70125 | 14.1982 | 9.1763 |  |  | 1500 | 1500 | 1500 | [14 empty] | 4500
01.170 | Travel/Pickup/Deliveries | 0 | 0 | 0 | 3000 | 0 | 3000 | 0.60741 | 0.39257 | [19 empty] | 0
01.205 | MUD Fees | 0 | 0 | 0 | 4350 | 0 | 4350 | 0.88075 | 0.56922 | [19 empty] | 0
01.214 | Bldg. Permit | 0 | 0 | 0 | 6822 | 0 | 6822 | 1.3813 | 0.8927 |  |  | 6822 | [16 empty] | 6822
01.230 | Builders Risk | 0 | 0 | 0 | 3096 | 0 | 3096 | 0.62685 | 0.40513 | [19 empty] | 0
01.235 | General Liability | 0 | 0 | 0 | 5956 | 0 | 5956 | 1.2059 | 0.77938 | [19 empty] | 0
01.452 | Testing/Inspections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0
01.454 | Mockups | 0 | 1500 | 750 | 0 | 0 | 2250 | 0.45556 | 0.29443 | [19 empty] | 0
01.501 | Temporary Utilities | 0 | 0 | 0 | 2719 | 5250 | 7969 | 1.6135 | 1.0428 | [19 empty] | 0
01.538 | Technology | 0 | 0 | 0 | 1200 | 0 | 1200 | 0.24296 | 0.15703 | [19 empty] | 0
01.540 | Equipment (Forklift/Skid Loader) | 0 | 0 | 0 | 1750 | 0 | 1750 | 0.35432 | 0.229 | [19 empty] | 0
01.560 | Temporary Barriers/Enclosures/Protection | 0 | 2400 | 750 | 0 | 0 | 3150 | 0.63778 | 0.4122 | [19 empty] | 0
01.578 | Site Maintenance (Snow Removal/Mowing) | 0 | 900 | 0 | 0 | 0 | 900 | 0.18222 | 0.11777 | [19 empty] | 0
01.740 | Cleaning & Waste Management (Dumpsters) | 0 | 13200 | 0 | 8250 | 4800 | 26250 | 5.3148 | 3.435 | [19 empty] | 0
01.810 | Warranties | 0 | 0 | 0 | 15600 | 0 | 15600 | 3.1585 | 2.0414 | [19 empty] | 0
01.830 | Small Tools/Supply/Rentals | 0 | 0 | 0 | 2175 | 0 | 2175 | 0.44037 | 0.28461 | [19 empty] | 0
01.840 | Punchlist | 0 | 5000 | 0 | 0 | 0 | 5000 | 1.0124 | 0.65428 | [19 empty] | 0
2 | EXISTING CONDITIONS |  |  |  |  | TOTAL | 0 | 0 | 0 | [19 empty] | 0
02.010 | Demolition | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0
3 | CONCRETE |  |  |  |  | TOTAL | 120023 | 24.3011 | 15.7057 | [19 empty] | 0
03.300 | Footings / Foundations | 0 | 0 | 0 | 450 | 92051 | 92501 | 18.7287 | 12.1043 |  |  | 92051 | [16 empty] | 92051
03.320 | Interior Concrete Flatwork | 0 | 0 | 0 | 0 | 27522 | 27522 | 5.5724 | 3.6014 |  |  |  | 16513 | 11009 | [14 empty] | 27522
4 | MASONRY |  |  |  |  | TOTAL | 134740 | 27.2808 | 17.6315 | [19 empty] | 0
04.210 | Brick Masonry | 0 | 0 | 31622 | 0 | 19565 | 51187 | 10.3638 | 6.6981 | [19 empty] | 0
04.220 | Concrete Unit Masonry (Blockwork) | 0 | 0 | 1150 | 0 | 1350 | 2500 | 0.50618 | 0.32714 |  |  | 950 | [16 empty] | 950
04.430 | Stone Masonry / Precast Sills & Caps | 0 | 0 | 25118 | 17440 | 38495 | 81053 | 16.4108 | 10.6063 | [19 empty] | 0
5 | METAL |  |  |  |  | TOTAL | 20019 | 4.0532 | 2.6196 | [19 empty] | 0
05.120 | Structural Steel Material | 0 | 0 | 0 | 0 | 14069 | 14069 | 2.8486 | 1.841 |  |  |  |  | 14069 | [14 empty] | 14069
05.528 | Metal Interior Railing | 0 | 0 | 0 | 0 | 5250 | 5250 | 1.063 | 0.68699 | [19 empty] | 0
05.530 | Exterior Railing | 0 | 0 | 0 | 0 | 700 | 700 | 0.14173 | 0.091599 | [19 empty] | 0
05.700 | Decorative Metal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0
6 | CARPENTRY |  |  |  |  | TOTAL | 548781 | 111.1118 | 71.8112 | [19 empty] | 0
06.110 | Wood Framing | 0 | 4250 | 90086 | 0 | 90008 | 184344 | 37.3242 | 24.1225 |  |  |  |  | 46086 | [14 empty] | 46086
06.380 | Cabinetry Allowance | 214500 | 500 | 2800 | 0 | 0 | 217800 | 44.098 | 28.5004 | [19 empty] | 0
06.442 | Exterior Brackets/Timbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0
06.460 | Wood Interior Trim / Stair Parts / Garage Step | 0 | 0 | 30687 | 0 | 65000 | 95687 | 19.3738 | 12.5212 | [19 empty] | 0
06.612 | Countertop Allowance | 50950 | 0 | 0 | 0 | 0 | 50950 | 10.3159 | 6.6671 | [19 empty] | 0
7 | MOISTURE/THERMAL PROT. |  |  |  |  | TOTAL | 153965 | 31.1733 | 20.1472 | [19 empty] | 0
07.130 | Waterproofing/Passive Radon/Termite Treatment | 0 | 0 | 0 | 850 | 10420 | 11270 | 2.2818 | 1.4747 |  |  | 5210 | 5210 | [15 empty] | 10420
07.210 | Insulation | 0 | 0 | 0 | 0 | 21370 | 21370 | 4.3268 | 2.7964 | [19 empty] | 0
07.250 | Stucco/EIFS System | 0 | 0 | 0 | 0 | 4800 | 4800 | 0.97186 | 0.62811 | [19 empty] | 0
07.300 | Roofing | 0 | 0 | 0 | 0 | 83700 | 83700 | 16.9468 | 10.9526 | [19 empty] | 0
07.455 | Siding | 0 | 0 | 5225 | 200 | 4450 | 9875 | 1.9994 | 1.2922 | [19 empty] | 0
07.469 | Exterior Carsiding | 0 | 0 | 5250 | 0 | 3300 | 8550 | 1.7311 | 1.1188 | [19 empty] | 0
07.600 | Flashing/Brick Ledge | 0 | 0 | 0 | 0 | 2050 | 2050 | 0.41506 | 0.26825 | [19 empty] | 0
07.630 | Gutters/Downspouts | 0 | 0 | 0 | 0 | 6600 | 6600 | 1.3363 | 0.86365 | [19 empty] | 0
07.920 | Joint Sealants | 0 | 0 | 0 | 0 | 5750 | 5750 | 1.1642 | 0.75242 | [19 empty] | 0
8 | DOORS & WINDOWS |  |  |  |  | TOTAL | 121369 | 24.5736 | 15.8818 | [19 empty] | 0
08.140 | Interior Wood Doors (Karona) | 0 | 0 | 22700 | 0 | 0 | 22700 | 4.5961 | 2.9704 | [19 empty] | 0
08.178 | Front Door | 19750 | 900 | 0 | 0 | 0 | 20650 | 4.181 | 2.7022 | [19 empty] | 0
08.385 | Garage Doors | 0 | 0 | 0 | 0 | 6750 | 6750 | 1.3667 | 0.88328 | [19 empty] | 0
08.500 | Windows (Pella Reserve) | 0 | 0 | 0 | 750 | 51199 | 51949 | 10.5181 | 6.7978 | [19 empty] | 0
08.600 | Roof Window/Skylights/Sun Tunnel | 0 | 800 | 4500 | 0 | 0 | 5300 | 1.0731 | 0.69354 | [19 empty] | 0
08.817 | Mirrors/Glass Inserts/Shower Doors | 14020 | 0 | 0 | 0 | 0 | 14020 | 2.8386 | 1.8346 | [19 empty] | 0
9 | FINISHES |  |  |  |  | TOTAL | 265200.7575 | 53.6952 | 34.7031 | [19 empty] | 0
09.200 | Drywall | 0 | 0 | 0 | 1200 | 42613 | 43813 | 8.8708 | 5.7332 | [19 empty] | 0
09.300 | Tile Allowance | [27 empty] | 0
| Floor Tile | 41605 | 0 | 0 | 0 | 0 | 41605 | 8.4238 | 5.4443 | [19 empty] | 0
| Backsplash & Wall Tile | 6325 | 0 | 0 | 0 | 0 | 6325 | 1.2806 | 0.82766 | [19 empty] | 0
| Shower/Tub Tile | 27424 | 0 | 0 | 0 | 0 | 27424 | 5.5525 | 3.5886 | [19 empty] | 0
09.640 | Wood/LVP/LVT Flooring Allowance | 27378 | 0 | 0 | 0 | 0 | 27378 | 5.5432 | 3.5826 | [19 empty] | 0
09.657 | Fitness Room Carpet Tile | 5750 | 0 | 0 | 0 | 0 | 5750 | 1.1642 | 0.75242 | [19 empty] | 0
09.672 | Epoxy Flooring | 6588.2575 | 0 | 0 | 0 | 0 | 6588.2575 | 1.3339 | 0.86211 | [19 empty] | 0
09.680 | Carpet Allowance | 19744.5 | 0 | 0 | 0 | 0 | 19744.5 | 3.9977 | 2.5837 | [19 empty] | 0
09.720 | Wall Coverings/Faux Finishing | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0
09.910 | Painting | 0 | 0 | 0 | 0 | 86573 | 86573 | 17.5284 | 11.3286 | [19 empty] | 0
10 | SPECIALTIES |  |  |  |  | TOTAL | 100931 | 20.4355 | 13.2074 | [19 empty] | 0
10.050 | Finish Hardware Allowance | 15172 | 5200 | 0 | 0 | 0 | 20372 | 4.1247 | 2.6658 | [19 empty] | 0
10.140 | Address Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0
10.310 | Fireplaces / Chimney Pot | 0 | 360 | 5260 | 750 | 28770 | 35140 | 7.1148 | 4.5983 | [19 empty] | 0
10.314 | Fireplace Facings Allowance | 12318 | 0 | 0 | 0 | 0 | 12318 | 2.494 | 1.6119 | [19 empty] | 0
10.552 | Mailbox | 850 | 0 | 0 | 0 | 0 | 850 | 0.1721 | 0.11123 | [19 empty] | 0
10.562 | Storage Shelving | alternate | 240 | 300 | 0 | 0 | 540 | 0.10933 | 0.070662 | [19 empty] | 0
10.572 | Closet Systems Allowance | 31711 | 0 | 0 | 0 | 0 | 31711 | 6.4205 | 4.1496 | [19 empty] | 0
11 | EQUIPMENT |  |  |  |  | TOTAL | 84018 | 17.0111 | 10.9942 | [19 empty] | 0
11.3 | Appliance Allowance (Wolf package) | 83518 | 500 | 0 | 0 | 0 | 84018 | 17.0111 | 10.9942 | [19 empty] | 0
11.52 | TV's Allowance | alternate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0
12 | FURNISHINGS |  |  |  |  | TOTAL | 0 | 0 | 0 | [19 empty] | 0
12.170 | Art Glass | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0
12.200 | Window Treatments | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0
12.250 | Motorized Shades | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0
13 | SPECIAL CONSTRUCTION |  |  |  |  | TOTAL | 1200 | 0.24296 | 0.15703 | [19 empty] | 0
13.342 | Covered Patio Sunshade | 1200 | 0 | 0 | 0 | 0 | 1200 | 0.24296 | 0.15703 | [19 empty] | 0
14 | CONVEYING SYSTEMS |  |  |  |  | TOTAL | 0 | 0 | 0 | [19 empty] | 0
14.050 | Elevator (rough-in only, future) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0
22-23 | PLUMBING/HVAC SYSTEMS |  |  |  |  | TOTAL | 167553 | 33.9245 | 21.9253 | [19 empty] | 0
22.050 | Plumbing (incl. garage drain) | 0 | 0 | 0 | 0 | 62753 | 62753 | 12.7056 | 8.2116 |  |  |  | 5000 | [15 empty] | 5000
22.322 | Water Filtration System Allowance | 6100 | 0 | 0 | 0 | 0 | 6100 | 1.2351 | 0.79822 | [19 empty] | 0
22.400 | Plumbing Fixtures Allowance | 33900 | 0 | 0 | 0 | 0 | 33900 | 6.8637 | 4.436 | [19 empty] | 0
23.050 | HVAC (incl. garage heater option) | 0 | 0 | 0 | 4900 | 56900 | 61800 | 12.5127 | 8.0869 | [19 empty] | 0
23.400 | Duct Cleaning | 0 | 0 | 0 | 0 | 3000 | 3000 | 0.60741 | 0.39257 | [19 empty] | 0
26-28 | ELECTRICAL & LOW VOLTAGE |  |  |  |  | TOTAL | 210376.5 | 42.595 | 27.529 | [19 empty] | 0
26.050 | Electrical Service & Wiring | 0 | 0 | 0 | 0 | 75000 | 75000 | 15.1853 | 9.8142 | [19 empty] | 0
26.410 | Lightning Protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0
26.505 | Light Fixtures Allowance | 52376.5 | 0 | 0 | 0 | 0 | 52376.5 | 10.6047 | 6.8538 | [19 empty] | 0
26.570 | Lighting Control System Allowance | alternate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0
27.410 | AV Systems Allowance | 79500 | 0 | 0 | 0 | 0 | 79500 | 16.0964 | 10.403 | [19 empty] | 0
28.070 | Security System/Fire Protect. Allowance | 3500 | 0 | 0 | 0 | 0 | 3500 | 0.70865 | 0.458 | [19 empty] | 0
31-32 | EARTHWORK & EXTERIOR IMPROVEMENTS |  |  |  |  | TOTAL | 260944 | 52.8334 | 34.146 | [19 empty] | 0
31.128 | Site Demolition | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0
31.230 | Excavation/Fill/Grading/Silt Fence | 0 | 0 | 0 | 4500 | 22500 | 27000 | 5.4667 | 3.5331 |  |  | 18500 | 4000 | [15 empty] | 22500
31.260 | Surveying | 0 | 0 | 0 | 0 | 2250 | 2250 | 0.45556 | 0.29443 |  |  | 1500 | [16 empty] | 1500
32.130 | Exterior Concrete Flatwork | 0 | 0 | 0 | 0 | 14680 | 14680 | 2.9723 | 1.921 | [19 empty] | 0
32.931 | Landscaping Allowance | [27 empty] | 0
| Plantings & Beds | 45000 | 0 | 0 | 0 | 0 | 45000 | 9.1112 | 5.8885 | [19 empty] | 0
| Paver Allowance | 32500 | 0 | 0 | 0 | 0 | 32500 | 6.5803 | 4.2528 | [19 empty] | 0
| Retaining Walls Allowance | 55500 | 0 | 0 | 0 | 0 | 55500 | 11.2371 | 7.2625 | [19 empty] | 0
| Landscape Lighting Allowance | 12500 | 0 | 0 | 0 | 0 | 12500 | 2.5309 | 1.6357 | [19 empty] | 0
| Irrigation Allowance | 7000 | 0 | 0 | 0 | 0 | 7000 | 1.4173 | 0.91599 | [19 empty] | 0
| Topsoil/Fine Grade/Sod Allowance | 14000 | 0 | 0 | 0 | 0 | 14000 | 2.8346 | 1.832 | [19 empty] | 0
| Underground Buried Drainage Allowance | 30000 | 0 | 0 | 0 | 0 | 30000 | 6.0741 | 3.9257 | [19 empty] | 0
32.310 | Fences/Gates | 0 | 0 | 0 | 0 | 20514 | 20514 | 4.1535 | 2.6844 | [19 empty] | 0
33 | UTILITIES |  |  |  |  | TOTAL | 4000 | 0.80988 | 0.52342 | [19 empty] | 0
33.020 | Water/Sewer Utilities | 0 | 0 | 0 | 0 | 4000 | 4000 | 0.80988 | 0.52342 | [19 empty] | 0
50 | CONTIGENCY |  |  |  |  | TOTAL | 50000 | 10.1235 | 6.5428 | [19 empty] | 0
50.050 | Contigency | 50000 | 0 | 0 | 0 | 0 | 50000 | 10.1235 | 6.5428 | [19 empty] | 0
50.070 | Arch/Engr Fees (Separate Agreement) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0
| TOTAL | 1000680.2575 | 105875 | 226198 | 85958 | 984002 | 2763120.2461 | 559.4493 | 361.5703 | 190000 | 255000 | 126533 | 32223 | 72664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231420
[12 empty] | 18979.95 | 4833.45 | 10899.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34713
[12 empty] | 145512.95 | 37056.45 | 83563.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 266133
McNeil Company Builders
PROJECT COST SUMMARY---MARKUP ANALYSIS
Project: | Hogan Residence
Location: | 811 N 143rd Plaza, Omaha, NE 68154 | [5 empty] | LOWER LEVEL | 2072
Date: | July 2026 | [5 empty] | MAIN LEVEL | 2867
Lot: | 21 | [5 empty] | TOTAL FINISHED SF | 4939
[7 empty] | GARAGE | 756
[7 empty] | LOWER UNFINISHED | 1567
[7 empty] | COVERED PATIO | 380
[7 empty] | TOTAL SF UNDER ROOF | 7642
MARKUP ADJUSTMENTS
ACTUAL COST
[6 empty] | Allowances |  | 1000680.2575
[6 empty] | Labor |  | 105875
[6 empty] | Material |  | 226198
[6 empty] | Other |  | 85958
[6 empty] | Subcontractor |  | 984002
[6 empty] | NO MARKUP TOTAL |  | 2402713.2575
[6 empty] | MARKUP PERCENTAGE |  | 15%
[6 empty] | MARKUP |  | 360406.9886
[6 empty] | BID |  | 2763120.2461

## Cash Flow Version 2
Approximate Cashflow Projection
Hogan Residence
2026-08-17
MACKINTOSH |  |  |  |  | HOGAN
Bldg Months |  | Payment |  | % of Contract | Bldg Months | Payment | % of Contract
| Deposit | 110000 |  |  | Deposit | 190000
1 | - | 0 |  | - | 1 | 0 | -
2 | 2024-01-31 | 234944 |  | 10% | 2 | 276314 | 10%
3 | 2024-02-29 | 94949 |  | 4% | 3 | 110525 | 4%
4 | 2024-04-30 | 166645 |  | 7% | 4 | 193418 | 7%
5 | 2024-05-31 | 142429 |  | 6% | 5 | 165787 | 6%
6 | 2024-06-30 | 67713 |  | 3% | 6 | 110525 | 4%
7 | 2024-07-31 | 140380 |  | 6% | 7 | 165787 | 6%
8 | 2024-08-31 | 163694 |  | 7% | 8 | 193418 | 7%
9 | 2024-09-30 | 213471 |  | 9% | 9 | 193418 | 7%
10 | 2024-10-31 | 165645 |  | 7% | 10 | 193418 | 7%
11 | 11/31/2024 | 0 | 80392 |  | 11 | 110525 | 4%
12 | 2024-12-31 | 160783 | 80392 | 7% | 12 | 110525 | 4%
13 | 2025-01-31 | 122809 |  | 5% | 13 | 138156 | 5%
14 | 2025-02-28 | 0 | 94794 |  | 14 | 110525 | 4%
15 | 2025-03-31 | 189587 | 94794 | 8% | 15 | 110525 | 4%
16 | 4/31/2025 | 0 | 148965 |  | 16 | 193418 | 7%
17 | 2025-05-31 | 0 | 148965 |  | 17 | 193418 | 7%
18 | 2026-07-31 | 446895 | 148965 | 20% | 18 | 193418 | 7%
| less deposit | -110000 |  |  | less deposit | -190000
| TOTAL SUM | 2309944 |  |  | TOTAL SUM | 2763120

## Cash Flow Version 2 Homeowner
Approximate Cashflow Projection - Hogan
2026-08-17
August 2026 | Lot Purchase | 255000
Home Construction
Month | Invoice # | Approx. Payment
August 2026 | Deposit | 190000
September 2026 | 1 | 0
October 2026 | 2 | 276314
November 2026 | 3 | 110525
December 2026 | 4 | 193418
January 2027 | 5 | 165787
February 2027 | 6 | 110525
March 2027 | 7 | 165787
April 2027 | 8 | 193418
May 2027 | 9 | 193418
June 2027 | 10 | 193418
July 2027 | 11 | 110525
August 2027 | 12 | 110525
September 2027 | 13 | 138156
October 2027 | 14 | 110525
November 2027 | 15 | 110525
December 2027 | 16 | 138156
January 2028 | 17 | 193418
February 2028 | 18 | 248680
| less deposit | -190000
| TOTAL SUM (HOUSE ONLY) | 2763120

## DIV 1 GC
01.000 | GENERAL CONDITIONS
1.12 | Superintendent
|  |  | PROJECT DURATION - MONTHS | APPROX. HOURS/DAY | HOURS/WEEK | RATE/HOUR | COST/WEEK | PROJECT DURATION - WEEKS | TOTAL
|  | minimal supervision at start 3 wks | 16 | 3 | 15 | 85 | 1275 | 55 | 70125
1.17 | Travel/Pickup/Deliveries
| Rates updated March 2026 | [6 empty] | TOTAL | 3000
|  |  |  | Labor |  | 50 | 60 | HR | 3000
1.205 | MUD Fees
| Rates updated March 2026 (based on Schachne) |  |  |  | TOTAL | 4350
| 1" Capital Facilities Charge (Impact Fee) |  |  | 1 | 3200 | 3200
| 1" Meter Install |  |  | 1 | 500 | 500
| Water Tap |  |  | 1 | 650 | 650
1.214 | Bldg. Permit
| Rates updated March 2026 | [6 empty] | TOTAL | 0
City of Omaha
https://permits.cityofomaha.org/fees
| $1.00-$2,000 |  | 41 |  |  |  | 0 | 41 | 0
| $2,000-$25,000 |  | $41.00 for first $2,000, plus $9.53 for each additional $1,000 |  |  |  | 0 | 41 | 0
[7 empty] | 0 | 9.53 | 0
| $25,001-$50,000 |  | $260.19 for first $25,000, plus $6.44 for each additional $1,000 |  |  |  | 0 | 260.19 | 0
[7 empty] | 0 | 6.44 | 0
| $50,001-$100,000 |  | $421.19 for first $50,000, plus $3.19 for each additional $1,000 |  |  |  | 0 | 421.19 | 0
[7 empty] | 0 | 3.19 | 0
| $100,001-$500,000 |  | $580.69 for first $100,000, plus $2.78 for each additional $1,000 |  |  |  | 0 | 580.69 | 0
[7 empty] | 0 | 2.78 | 0
| $500,001-$1,000,000 |  | $1,692.69 for first $500,000, plus $2.37 for each additional $1,000 |  |  |  | 0 | 1692.69 | 0
[7 empty] | 0 | 2.37 | 0
| $1,000,001 and up |  | $2877.69 for first $1,000,000, plus $1.96 for each additional $1,000 |  |  |  | 0 | 1000000 | 0
[7 empty] | 0 | 1.96 | 0
City of Blair
https://www.blairne.gov/DocumentCenter/View/52/Building-Permit-and-Zoning-Fees-PDF
| Finished SF (not including finished basement) |  |  | 0 | * | 102 | 0
| Finished Basement SF |  |  | 0 | * | 62 | 0
| Unfinished Basement SF |  |  | 0 | * | 32 | 0
| Garage SF |  |  | 0 | * | 30 | 0
0
[6 empty] | Multiply by .006 | 0.006
[6 empty] | Total | 0
1.23 | Builders Risk
[8 empty] | TOTAL | 0
| Builders Risk (0.144/100 cost) |  |  |  |  | 0 | 0.144 |  | 0
| Misc. |  |  |  |  | 0 |  |  | 0
1.235 | General Liability
[8 empty] | TOTAL | 0
| Liability (2.77/1000 cost) |  |  |  |  | 0 | 2.77 |  | 0
| Bond |  |  |  |  | 0 |  |  | 0
| Misc. |  |  |  |  | 0 |  |  | 0
1.452 | Testing/Inspections
[8 empty] | TOTAL | 0
| Soil Testing |  |  |  |  | 0 | 1500 |  | 0
| Call back after excavation for visual inspection |  |  |  |  | 0 | 200 |  | 0
1.454 | Mockups
[8 empty] | TOTAL | 2250
|  |  |  | Labor |  | 25 | 60 | HR | 1500
|  |  |  | Materials |  | 1 | 500 | EA | 750
1.501 | Temporary Utilities
| Rates updated March 2026 | [6 empty] | TOTAL | 7968.8
| Temp Power Service |  | OPPD |  |  | 15 | 150 | /MONTH | 2250
| Temp Gas / Water Service |  | MUD |  |  | 12 | 250 | /MONTH | 3000
| Temp Heat for Interior |  | Labor / Material |  |  | 1 | 350 | ALLOWANCE | 350
| Temp Heat for Exterior |  | Labor / Material |  |  | 1 | 400 | ALLOWANCE | 400
| Portable Toilet |  | Eagle Services |  | Monthly Charge (includes tax) | 15 | 128.4 | /MONTH | 1926
[5 empty] | Delivery & Pickup (inlcudes tax) | 2 | 21.4 | /MONTH | 42.8
1.538 | Technology
| Rates updated March 2026 | [6 empty] | TOTAL | 1200
[5 empty] | Equipment | 1 | 1200 | /JOB | 1200
1.54 | Equipment (Forklift/Skid Loader)
| Rates updated March 2026 | [6 empty] | TOTAL | 1750
[5 empty] | Equipment | 1 | 1750 | /JOB | 1750
1.56 | Temporary Barries/Enclosures
| Rates updated March 2026 | [6 empty] | TOTAL | 3150
|  |  |  | Material |  | 1 | 750 | EA | 750
|  |  |  | Labor | (2 guys at $60/hr) | 20 | 120 | HR | 2400
|  |  |  | Subcontract |  | 0 | 4500 | EA | 0
1.578 | Site Maintenance
| Rates updated March 2026 | [6 empty] | TOTAL | 900
| Snow Removal |  |  | Labor |  | 5 | 60 | HR | 300
| Mowing/Spraying/Weedeating |  |  | Labor |  | 10 | 60 | HR | 600
1.74 | Cleaning & Waste Management
| Rates updated March 2026 | [6 empty] | TOTAL | 22125
|  |  | Interim Clean | Labor | 3 hrs/week | 170 | 60 | HR | 10200
|  |  | Final Clean | Labor |  | 0 | 60 | HR | 0
|  |  | Final Clean | Subcontract |  | 1 | 4800 | EA | 4800
|  |  | Window Clean | Subcontract | 2-story | 0 | 1200 | EA | 0
|  |  | Window Clean | Subcontract | Ranch | 0 | 750 | EA | 0
|  |  | Dumpsters | Other | S2 | 19 | 375 | /MONTH | 7125
Excludes drywall in phase
1.81 | Warranties
| Warranty Historical |  |  | Own | McNeil | 2700000 | 0.006 | /TOTAL/COST | 16200
1.83 | Small Tools/Supply/Rent
| Rates updated March 2026 | [6 empty] | TOTAL | 2175
[5 empty] | Tools/Supplies | 1 | 2000 | /JOB | 2000
[5 empty] | Floor Sander | 1 | 175 | /JOB | 175
[5 empty] | Other Equipment | 0 | 250 | /JOB | 0
1.84 | Punchlist
| Rates updated March 2026 | [6 empty] | TOTAL | 2250
[5 empty] | Labor | 1 | 2250 | /JOB | 2250

## DIV 2 EXIST. COND.
02.000 | EXISTING CONDITIONS
2.01 | Demolition
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 3 CONCRETE
03.000 | CONCRETE
3.3 | Footings/Foundations
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
3.32 | Interior Concrete Flatwork
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
Unit Rate Estimate - rates updated March of 2026
Lower Level Slab |  | 0 | sf
Garage Slab |  | 0 | sf
|  | 0 | sf
MATERIAL
Poly (LL & GARAGE SLAB SF x 1.15 = sf) |  |  |  | 0 | 0.075 | SF | 0
Lower Level Slab Granular (LL SF x .33ft x 1.25 / 18 = tons) |  |  |  | 0 | 22 | TON | 0
Garage Slab Granular (GARAGE SF x .33ft x 1.25 / 18 = tons) |  |  |  | 0 | 22 | TON | 0
Additive (Xypex for water impermeable) |  |  |  | 0 | 131.85 | BOX | 0
Expansion Joints at Walls |  |  | ls | 0 | 125 | EA | 0
SUBCONTRACTOR
Lower Level Slab |  |  |  | 0 | 6.75 | SF | 0
Poly install |  |  |  | 0 | 0.35 | SF | 0
Step Down (form charge) |  |  |  | 0 | 10 | LF | 0
Garage Slab |  |  |  | 0 | 6.75 | SF | 0
Saw Cut slabs |  |  |  | 0 | 0.05 | SF | 0
Grading |  |  |  | 0 | 0.25 | SF | 0
Pump charge |  |  |  | 0 | 1700 | EA | 0
Cure & Seal |  |  |  | 0 | 0.12 | SF | 0
[6 empty] | TOTAL | 0

## DIV 4 MASONRY
04.000 | MASONRY
4.21 | Brick / Precast Sills & Caps
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
OLD CAROLINA TYRON HMOS | [7 empty] | WILLIAMSBURG CHERRY OR WELLINGTON
Unit Rate Estimate - rates updated March of 2026 | [7 empty] | Unit Rate Estimate - rates updated March of 2026
Brick (Modular) |  | 1600 | SF | 4.5 | 7200 | brick ea |  | Brick (Modular) | 1600 | SF | 4.5 | 7200 | brick ea
Soldiers/Rowblocks |  | 275 | LF | 3.5 | 962.5 | brick ea |  | Soldiers/Rowblocks | 275 | LF | 3.5 | 962.5 | brick ea
Approx. per 292lf |  |  |  | RAW QTY BRICK | 8162.5 | brick ea |  | Approx. per 292lf |  |  | RAW QTY BRICK | 8162.5 | brick ea
|  |  |  | 12% WASTE FACTOR | 979.5 | brick ea |  |  |  |  | 12% WASTE FACTOR | 979.5 | brick ea
|  |  |  | TOTAL | 9142 | brick ea |  |  |  |  | TOTAL | 9142 | brick ea
*adjust brick/cube quantity based on brick size |  |  |  | Qty of Full Cubes | 344 | brick/cube |  | *adjust brick/cube quantity based on brick size |  |  | Qty of Full Cubes | 416 | brick/cube
|  |  |  | TOTAL | 26.5756 | total cubes |  |  |  |  | TOTAL | 21.976 | total cubes
Per Laura at Watkins:
125 brick/bag of masonry for this product
premix mortar - 35-40 brick/bag on modular / 30-32 brick per bag oversize
MATERIAL | [7 empty] | MATERIAL
Brick (modular) |  | 344brick/cube x 27 cubes |  | 9288 | 2.45 | 22755.6 |  | Brick (modular) | 416brick/cube x 22 cubes |  | 9152 | 0.53 | 4850.56
Brick (solids) |  |  |  | 0 | 1.5 | 0 |  | Brick (solids) |  |  | 0 | 1.5 | 0
premix mortar (colored) |  | 9288/30 + waste |  | 325 | 14.45 | 4696.25 |  | premix mortar (colored) | 9142/30 |  | 325 | 14.45 | 4696.25
premix mortar (standard gray) |  |  |  | 0 | 9.5 | 0 |  | premix mortar (standard gray) |  |  | 0 | 9.5 | 0
Masonry Cement |  | 7 bags/M |  | 0 | 11 | 0 |  | Masonry Cement | 7 bags/M |  | 0 | 11 | 0
Portland Cement |  | 1 bag/5 of masonry |  | 0 | 14 | 0 |  | Portland Cement | 1 bag/5 of masonry |  | 0 | 14 | 0
Sand |  | 3 to 1 by weight |  | 0 | 15 | 0 |  | Sand | 3 to 1 by weight |  | 0 | 15 | 0
Weep Holes |  | approx. every 3lf | 260lf/3 | 100 | 0.65 | 65 |  | Weep Holes | approx. every 3lf |  | 100 | 0.65 | 65
Nervastral |  | 12"x150'/roll | 260/150 | 2 | 90 | 180 |  | Nervastral | 12"x150'/roll |  | 2 | 90 | 180
SureKlean #600 detergent |  | 600sf/gallon | 1600/600 | 3 | 25 | 75 |  | SureKlean #600 detergent | 600sf/gallon | 1600/600 | 3 | 25 | 75
Ties |  | .10 ties per brick |  | 930 | 0.35 | 325.5 |  | Ties | .10 ties per brick |  | 930 | 0.35 | 325.5
1" Mortar Net |  |  |  | 0 | 2.4 | 0 |  | 1" Mortar Net |  |  | 0 | 2.4 | 0
Misc. Tools |  |  |  | 1 | 250 | 250 |  | Misc. Tools |  |  | 1 | 250 | 250
Pallet charge |  |  |  | 27 | 28 | 756 |  | Pallet charge |  |  | 27 | 28 | 756
freight/delivery |  |  |  | 3 | 150 | 450 |  | freight/delivery |  |  | 3 | 150 | 450
[5 empty] | SUBTOTAL | 29553.35 | [5 empty] | SUBTOTAL | 11648.31
[5 empty] | 7% TAX | 2068.7345 | [5 empty] | 7% TAX | 815.3817
[5 empty] | TOTAL | 31622.0845 | [5 empty] | TOTAL | 12463.6917
4.22 | Concrete Masonry Units (Blockwork)
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
4.43 | Stone Masonry / Precast Sills & Caps
|  |  |  | Baltazar | Precast | Company | Company
Base Bid |  |  |  | 25117.8755 |  | 0 | 0
1 | Artisan Stone |  |  |  | 13132
2 | Dreamcast (outdoor fireplace surround) |  |  |  | 4308
3
4
5
6
7
8
9
10
|  |  | TOTAL | 25117.8755 | 17440 | 0 | 0
OPTION - MORE THIN STONE, LESS FULL BED DEPTH
Unit Rate Estimate - rates updated March of 2026 | [7 empty] | Unit Rate Estimate - rates updated March of 2026
Thin Stone Flats |  | 341 | SF | 12% waste factor | 381.92 | stone sf |  | Thin Stone Flats | 341 | SF | 12% waste factor | 381.92 | stone sf
Thin Stone Corners |  | 52 | LF | 12% waste factor | 58.24 | stone lf |  | Thin Stone Corners | 52 | LF | 12% waste factor | 58.24 | stone lf
Approx. per 292lf |  |  |  | TOTAL | 440.16 | stone sf |  | Approx. per 292lf |  |  | TOTAL | 440.16 | stone sf
Full Bed Depth Stone |  | 782 | SF | 12% waste factor | 875.84 | stone sf |  | Full Bed Depth Stone | 782 | SF | 12% waste factor | 875.84 | stone sf
Approx. per 292lf |  |  |  | TOTAL | 875.84 | stone sf |  | Approx. per 292lf |  |  | TOTAL | 875.84 | stone sf
|  |  |  | Approximate ton qty | 40 | sf/ton |  |  |  |  | Approximate ton qty | 40 | sf/ton
|  |  |  | TOTAL | 21.896 | tons |  |  |  |  | TOTAL | 21.896 | tons
per Laura at Watkins: | [7 empty] | per Laura at Watkins:
thin stone mortar coverage - Promix 70lb bag is 15sf/bag for joints; 7sf/bag for scratch coat | [7 empty] | thin stone mortar coverage - Promix 70lb bag is 15sf/bag for joints; 7sf/bag for scratch coat
full bed depth stone mortar coverage - depends on stone size, but 7-10sf/bag gets close | [7 empty] | full bed depth stone mortar coverage - depends on stone size, but 7-10sf/bag gets close
german schmear style mortar coverage - depends on heaviness of schmear | [7 empty] | german schmear style mortar coverage - depends on heaviness of schmear
approximate sf/ton for full bed depth stone - 38-40sf/ton | [7 empty] | approximate sf/ton for full bed depth stone - 38-40sf/ton
MATERIAL | [7 empty] | MATERIAL
Thin Stone Flats |  | $/sf |  | 382 | 10.45 | 3991.9 |  | Thin Stone Flats | $/sf |  | 382 | 10.45 | 3991.9
Thin Stone Corners |  | $/each |  | 58 | 14 | 812 |  | Thin Stone Corners | $/each |  | 58 | 14 | 812
Full Bed Depth Stone |  | $/ton | 876/40 | 22 | 650 | 14300 |  | Full Bed Depth Stone | $/ton | 876/40 | 22 | 650 | 14300
Premix Mortar (colored) |  |  | 876/7 | 125 | 14.45 | 1806.25 |  | Premix Mortar (colored) |  | 876/7 | 125 | 14.45 | 1806.25
Premix Mortar (colored) |  |  | 400/15 | 30 | 14.45 | 433.5 |  | Premix Mortar (colored) |  | 400/15 | 30 | 14.45 | 433.5
Premix Mortar (standard gray) |  |  |  | 0 | 13.8 | 0 |  | Premix Mortar (standard gray) |  |  | 0 | 13.8 | 0
Scratch coat mortar |  |  | 400/7 | 60 | 13.8 | 828 |  | Scratch coat mortar |  | 400/7 | 60 | 13.8 | 828
Metal Lathe |  | 27"x96", assume 16sf with overlap |  | 25 | 14.1 | 352.5 |  | Metal Lathe | 27"x96", assume 16sf with overlap |  | 25 | 14.1 | 352.5
Felt |  | 200sf/roll | 400/200 | 2 | 35 | 70 |  | Felt | 200sf/roll | 400/200 | 2 | 35 | 70
Lathe Bottom Weep Screed |  | assume 10' |  | 4 | 17 | 68 |  | Lathe Bottom Weep Screed | assume 10' |  | 4 | 17 | 68
Rainscreen, Keene |  | 4'x65' (260sf) | 1260/260 | 5 | 10 | 50 |  | Rainscreen, Keene | 4'x65' (260sf) | 1260/260 | 5 | 10 | 50
Masonry Cement |  | 7 bags/M |  | 0 | 11 | 0 |  | Masonry Cement | 7 bags/M |  | 0 | 11 | 0
Portland Cement |  | 1 bag/5 of masonry |  | 0 | 14 | 0 |  | Portland Cement | 1 bag/5 of masonry |  | 0 | 14 | 0
Sand |  | 3 to 1 by weight |  | 0 | 15 | 0 |  | Sand | 3 to 1 by weight |  | 0 | 15 | 0
Weep Holes |  | approx. every 3lf |  | 50 | 0.65 | 32.5 |  | Weep Holes | approx. every 3lf |  | 50 | 0.65 | 32.5
Nervastral |  | 12"x150'/roll |  | 2 | 90 | 180 |  | Nervastral | 12"x150'/roll |  | 2 | 90 | 180
SureKlean #600 detergent |  | 600sf/gallon | 1260/600 | 2 | 25 | 50 |  | SureKlean #600 detergent | 600sf/gallon | 1260/600 | 2 | 25 | 50
Ties |  | .10 ties per brick |  | 0 | 0.35 | 0 |  | Ties | .10 ties per brick |  | 0 | 0.35 | 0
1" Mortar Net |  |  |  | 0 | 2.4 | 0 |  | 1" Mortar Net |  |  | 0 | 2.4 | 0
Misc. Tools |  |  |  | 1 | 200 | 200 |  | Misc. Tools |  |  | 1 | 200 | 200
Pallet charge |  | approx. 150-200sf/pallet |  | 0 | 28 | 0 |  | Pallet charge | approx. 150-200sf/pallet |  | 0 | 28 | 0
freight/delivery |  |  |  | 2 | 150 | 300 |  | freight/delivery |  |  | 2 | 150 | 300
[5 empty] | SUBTOTAL | 23474.65 | [5 empty] | SUBTOTAL | 23474.65
[5 empty] | 7% TAX | 1643.2255 | [5 empty] | 7% TAX | 1643.2255
[5 empty] | TOTAL | 25117.8755 | [5 empty] | TOTAL | 25117.8755

## DIV 5 METAL
05.000 | METAL
5.12 | Strucutural Steel - Material
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
5.528 | Metal Interior Railing
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
5.53 | Exterior Deck Railing
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
5.7 | Decorative Metal
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 6 CARPENTRY
06.000 | CARPENTRY
6.11 | Wood Framing
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
6.15 | Wood Decks
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
6.38 | Cabinetry
|  |  |  | Company | Company | Company | Company
Main Level
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
Lower Level
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
Upper Level
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
6.442 | Exterior Brackets/Timbers
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
6.46 | Wood Interior Trim
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
Unit Rate Estimate
| DESCRIPTION |  | SPECIES | QTY | UNIT PRICE | SUBTOTAL | NOTES
BASE AND CASING
| 2 1/2" Casing SEC-085 |  | Poplar | 2300 | 1.41 | 3243 | (135) 8', (105) 10', (6) 12', (7) 14'
| 4" Base SEB-252 |  | Poplar | 320 | 2.11 | 675.2
| 6" Base SEB-252 |  | Poplar | 740 | 3.06 | 2264.4
| PVC Base - Azek (Garage) |  |  | 115 | 7 | 805
| Base Shoe |  | Poplar | 600 | 0.98 | 588
| Base Shoe |  | Beech | 200 | 1.12 | 224
| Window Jamb Extensions 1X10 |  | Poplar | 158 | 6.71 | 1060.18 | (10) 8', (5) 10', (2) 14'
BEAMS
| Industrial Board (structure) |  |  | 1 | 500 | 500
| 3x/4"x10" SBM-002 |  | Poplar | 286 | 4.47 | 1278.42 | (6) 8', (17) 14'
6" Crown - included in Ceiling Details
| Backer - 1x4 |  | Poplar | 100 | 2.76 | 276
| Arched mouldings |  |  | 3 | 750 | 2250
CEILING DETAILS
| 5 1/2" Flat (1x6) |  | Poplar | 308 | 3.99 | 1228.92 | (16) 8', (12) 10', (5) 12'
| 6" Crown SER-129 |  | Beech | 312 | 4.5 | 1404 | (8) 8', (20) 10', (4) 12'
| 6" Crown SER-129 |  | Poplar | 712 | 3.99 | 2840.88 | (50) 8', (20) 10', (7) 12', (2) 14'
| Applied Moulding SEH-045 |  | Poplar | 60 | 1.1 | 66 | (6) 10'
| Backer - 1x4 |  | Poplar | 100 | 2.76 | 276
FOYER PANELED OPENINGS
| 2 1/2" Casing SEC-085 |  | Beech | 176 | 2.08 | 366.08 | (7) 8', (12) 10'
| 3/4"x4x10 |  | Beech | 5 | 203.74 | 1018.7
| 3/4"x4x8 |  | Beech | 2 | 146.85 | 293.7
| Backer - 1x4 |  | Poplar | 75 | 2.76 | 207
PRIMARY BEDROOM ACCENT WALL
| In Cabinetry |  |  | 0 | 0 | 0
| 6" Crown SER-129 |  | Beech | 10 | 4.5 | 45
| 6" Base SEB-252 |  | Beech | 10 | 3.5 | 35
PRIMARY BATHROOM MIRRORS
| In Cabinetry |  |  | 0 | 0 | 0
| 6" Crown SER-129 - included in crown section above |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
FOYER WALL MOULDINGS
| SEH-045 |  | Poplar | 332 | 1.1 | 365.2 | (22) 8', (12) 10', (3) 12'
| 1/2"x1" Double Eased Edge |  | Poplar | 112 | 0.98 | 109.76 | (9) 8', (4) 10'
STAIR PARTS
| Wood Handrail |  | Beech | 30 | 30 | 900 | (1) 8', (1) 10', (1) 12'
| 1x12 skirt boards |  | Poplar | 48 | 10.44 | 501.12 | (2) 10, (2) 14'
| SEC-085 skirt board cap |  | Poplar | 48 | 1.41 | 67.68 | (2) 10, (2) 14'
| 1/2"x12" End Cap Treads |  | White Oak | 20 | 20.25 | 405 | (2) 10'
| 1/2"x8" End Cap Risers |  | Poplar | 20 | 4 | 80 | (2) 10'
| Planing Charge |  |  | 1 | 75 | 75
| End Cap Nosing |  | White Oak | 30 | 3.44 | 103.2 | (3) 10'
| End Cap & Balcony Nosing |  | White Oak | 10 | 3.44 | 34.4 | (1) 10'
GARAGE STEP
| Timbertech composite decking |  |  | 1 | 700 | 700
MISC. TRIM DETAILS
| Tooling/Setup Charge |  |  | 1 | 500 | 500
| Glue, shims, fasteners, blades |  |  | 1 | 1200 | 1200
| Delivery |  |  | 3 | 150 | 450
[5 empty] | subtotal | 26436.84
[5 empty] | 7% tax | 1850.5788
[5 empty] | TOTAL | 28287.4188
6.612 | Countertop Allowance
|  |  |  | Company | Company | Company | Company
Main Level
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
Lower Level
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
Upper Level
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0

## DIV 7 MOISTURE PROTECTION
07.000 | MOISTURE/THERMAL PROTECTION
7.13 | Waterproofing/Passive Radon/Termite Treatment
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.21 | Insulation
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.25 | Stucco System
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.3 | Roofing
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.455 | Siding
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.469 | Exterior Carsiding
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.6 | Flashing/Brickledge
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.63 | Gutters/Downspouts
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.92 | Joint Sealants
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 8 OPENINGS
08.000 | OPENINGS
8.14 | Interior Wood Doors
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.178 | Front Door
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.184 | Pet Door
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.385 | Garage Doors
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.5 | Windows
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.6 | Roof Windows/Skylights/Sun Tunnel
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.817 | Mirrors/Glass Inserts/Shower Doors
|  |  |  | Company | Company | Company | Company
Main Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
Lower Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
Upper Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
1
2
3
4
5
6
7
8
9 | Install
10 | McNeil Company Wood Backer Supply/Install
|  |  | TOTAL | 0 | 0 | 0 | 0

## DIV 9 FINISHES
09.000 | FINISHES
9.2 | Drywall
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
9.3 | Tile
Floor Tile
[8 empty] | TOTAL | 41605
| Kitchen | [7 empty] | 5125
| raw area - 112sf + waste |  |  | Tile Material | ALLOWANCE | 140 | 12 | SF | 1680
| say 140sf order |  |  | Labor/Setting Materials | ALLOWANCE | 140 | 22.5 | SF | 3150
|  |  |  | Delivery | ALLOWANCE | 1 | 100 | EA | 100
|  |  |  | Sealer | ALLOWANCE | 130 | 1.5 | SF | 195
|  |  |  | Self Leveling | ALLOWANCE | 0 | 5 | SF | 0
| Laundry | [7 empty] | 2555
| raw area - 62sf + waste |  |  | Tile Material | ALLOWANCE | 80 | 10 | SF | 800
| say 80sf order |  |  | Labor/Setting Materials | ALLOWANCE | 80 | 21 | SF | 1680
|  |  |  | Delivery | ALLOWANCE | 1 | 75 | EA | 75
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Self Leveling | ALLOWANCE | 0 | 5 | SF | 0
| Master Bath | [7 empty] | 7330
| raw area - 103sf + waste |  |  | Tile Material | ALLOWANCE | 130 | 15 | SF | 1950
| say 130sf order |  |  | Labor/Setting Materials | ALLOWANCE | 120 | 22.5 | SF | 2700
|  |  |  | Delivery | ALLOWANCE | 1 | 100 | EA | 100
|  |  |  | Sealer | ALLOWANCE | 120 | 1.5 | SF | 180
|  |  |  | Self Leveling | ALLOWANCE | 0 | 5 | SF | 0
|  |  |  | In-Floor Heat | ALLOWANCE | 120 | 20 | SF | 2400
| Lower Level Billiards, Hall, Bath 2, Storage Closet | [7 empty] | 24540
| raw area - 653sf + waste |  |  | Tile Material | ALLOWANCE | 760 | 10 | SF | 7600
| say 760sf |  |  | Labor/Setting Materials | ALLOWANCE | 720 | 21 | SF | 15120
|  |  |  | Delivery | ALLOWANCE | 1 | 300 | EA | 300
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Anti-fracture Membrane | ALLOWANCE | 760 | 2 | SF | 1520
| Lower Level Bath 3 | [7 empty] | 2055
| raw area - 46sf + waste |  |  | Tile Material | ALLOWANCE | 60 | 10 | SF | 600
| say 60sf |  |  | Labor/Setting Materials | ALLOWANCE | 60 | 21 | SF | 1260
|  |  |  | Delivery | ALLOWANCE | 1 | 75 | EA | 75
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Anti-fracture Membrane | ALLOWANCE | 60 | 2 | SF | 120
Backsplash & Wall Tile
[8 empty] | TOTAL | 6325
| Service Entry Hooks Wall | [7 empty] | 1750
| 28sf + waste |  |  | Field Tile | ALLOWANCE | 40 | 20 | SF | 800
say 40sf to order
|  |  |  | Labor/Setting Materials | ALLOWANCE | 30 | 30 | SF | 900
|  |  |  | Delivery | ALLOWANCE | 1 | 50 | EA | 50
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
| Kitchen - Hood Wall Above Slab Splash | [7 empty] | 1500
| 20sf + waste = 25sf |  |  | Field Tile | ALLOWANCE | 25 | 20 | SF | 500
|  |  |  | Deco | ALLOWANCE | 1 | 150 | EA | 150
|  |  |  | Labor/Setting Materials | ALLOWANCE | 25 | 32 | SF | 800
|  |  |  | Delivery | ALLOWANCE | 1 | 50 | EA | 50
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
| Pantry Backsplash | [7 empty] | 985
| 14sf + waste = 18sf |  |  | Field Tile | ALLOWANCE | 18 | 15 | SF | 270
|  |  |  | Deco | ALLOWANCE | 1 | 125 | EA | 125
|  |  |  | Labor/Setting Materials | ALLOWANCE | 18 | 30 | SF | 540
|  |  |  | Delivery | ALLOWANCE | 1 | 50 | EA | 50
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
| LL Bar Backsplash | [7 empty] | 2090
| 36sf + waste = 45sf |  |  | Field Tile | ALLOWANCE | 45 | 12 | SF | 540
|  |  |  | Deco | ALLOWANCE | 1 | 150 | EA | 150
|  |  |  | Labor/Setting Materials | ALLOWANCE | 45 | 30 | SF | 1350
|  |  |  | Delivery | ALLOWANCE | 1 | 50 | EA | 50
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
Shower/Tub Tile
[8 empty] | TOTAL | 27424
| Primary Shower | [7 empty] | 16340
| 183sf + waste = 230sf |  |  | Field Tile | ALLOWANCE | 230 | 13.5 | SF | 3105
|  |  |  | Deco Tile | ALLOWANCE | 1 | 550 | EA | 550
| 30sf + waste = 40sf |  |  | Ceiling Tile | ALLOWANCE | 40 | 13.5 | SF | 540
| 30sf + waste = 40sf |  |  | Floor Tile | ALLOWANCE | 40 | 18.5 | SF | 740
| 25lf + waste = 32lf |  |  | Bullnose | ALLOWANCE | 32 | 15 | EA | 480
|  |  |  | Labor/Setting Materials | ALLOWANCE | 270 | 22.5 | SF | 6075
|  |  |  | Miter Outside Corners - Addt'l Cost | ALLOWANCE | 0 | 300 | EA | 0
|  |  |  | Labor - install seat, shelves, jamb and curb | ALLOWANCE | 1 | 1200 | EA | 1200
|  |  |  | Labor - floor | ALLOWANCE | 40 | 85 | SF | 3400
|  |  |  | Tile Drain | ALLOWANCE | 1 | 150 | EA | 150
|  |  |  | Sealer/Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 1 | 100 | EA | 100
| Bath 2 | [7 empty] | 5798
| 96sf + waste = 120sf |  |  | Field Tile | ALLOWANCE | 120 | 10 | SF | 1200
|  |  |  | Deco Tile | ALLOWANCE | 1 | 400 | EA | 400
| 15sf + waste = 19sf |  |  | Ceiling Tile | ALLOWANCE | 19 | 10 | SF | 190
| 15sf + waste = 19sf |  |  | Floor Tile | ALLOWANCE | fiberglass base | 15 | SF | 0
| 23lf + waste = 30lf |  |  | Bullnose | ALLOWANCE | 30 | 15 | EA | 450
|  |  |  | Labor/Setting Materials | ALLOWANCE | 139 | 22 | SF | 3058
|  |  |  | Labor - install shelves | ALLOWANCE | 1 | 400 | EA | 400
|  |  |  | Labor - floor | ALLOWANCE | fiberglass base | 85 | SF | 0
|  |  |  | Tile Drain | ALLOWANCE | 0 | 150 | EA | 0
|  |  |  | Sealer/Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 1 | 100 | EA | 100
| Bath 3 | [7 empty] | 5286
| 103sf + waste = 130sf |  |  | Field Tile | ALLOWANCE | 103 | 10 | SF | 1030
|  |  |  | Deco Tile | ALLOWANCE | 1 | 400 | EA | 400
| 16sf + waste = 20sf |  |  | Ceiling Tile | ALLOWANCE | 20 | 10 | SF | 200
| 16sf + waste = 20sf |  |  | Floor Tile | ALLOWANCE | fiberglass base | 15 | SF | 0
| 23lf + waste = 30lf |  |  | Bullnose | ALLOWANCE | 30 | 15 | EA | 450
|  |  |  | Labor/Setting Materials | ALLOWANCE | 123 | 22 | SF | 2706
|  |  |  | Labor - install shelves | ALLOWANCE | 1 | 400 | EA | 400
|  |  |  | Labor - floor | ALLOWANCE | fiberglass base | 85 | SF | 0
|  |  |  | Tile Drain | ALLOWANCE | 0 | 150 | EA | 0
|  |  |  | Sealer/Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 1 | 100 | EA | 100
9.64 | Wood Flooring / LVP / LVT Allowance
| WOOD FLOOR / LVP / LVT AREAS | [5 empty] | TOTAL | 0
| Main Level | 0 | SF
| Lower Level | 0 | SF
| Upper Level | 0 | SF
| Subtotal | 0 | SF
| 7% waste - typical | 0 | SF
| 15% waste - diagonal/herringbone | 0 | SF
| Total | 0 | SF
| Prefin. wood materials (range from $5.50-$12) |  |  | ALLOWANCE | 0 | 0 | SF | 0
| Wood Installation Labor |  |  | ALLOWANCE | 0 | 0 | SF | 0
| Wood Stair Labor |  |  | ALLOWANCE | 0 | 25 | EA | 0
| Wood Vents (Flush Mount) |  |  | ALLOWANCE | 0 | 122 | EA | 0
| Miscellanous Underlayment/Floor Prep |  |  | ALLOWANCE | 0 | 3 | SF | 0
| LVP / LVT materials |  |  | ALLOWANCE | 0 | 0 | SF | 0
| LVP / LVT Installation Labor |  |  | ALLOWANCE | 0 | 0 | SF | 0
| LVP / LVT Prep / Glue / Transitions |  |  | ALLOWANCE | 0 | 0 | SF | 0
NOTES:
per Timberland - use $10/sf allowance for prefinished wood
9.657 | Fitness Room Carpet Tile
| AREAS | [5 empty] | TOTAL | 5750
| LL Fitness Room | 231 | SF
| Subtotal | 231 | SF
| 7% waste | 16.17 | SF
| Total | 247.17 | SF
| Carpet Tile/Rubber Flooring Material & Labor |  |  | ALLOWANCE | 250 | 23 | SF | 5750
| Installation Labor |  |  | ALLOWANCE | 0 | 0 | SF | 0
9.672 | Epoxy Flooring
| AREAS | polyaspartic | concrete paint |  |  |  | TOTAL | 6588.2575
| Garage | 715
| Mechanical/Storage 1 |  | 322
| Mechanical/Storage 2 |  | 292
| Subtotal | 715 | 614
| 5% waste | 50.05 | 42.98
| Total | 765.05 | 656.98
| Polyaspartic (mtl and install) |  |  | ALLOWANCE | 765.05 | 6.25 | SF | 4781.5625
| Concrete Porch Paint (mtl and install) |  |  | ALLOWANCE | 656.98 | 2.75 | SF | 1806.695
9.68 | Carpet Allowance
| AREAS | [5 empty] | TOTAL | 19744.5
| Main Level | 242 | SF
| Lower Level Bedrooms | 531 | SF
| Lower Level Family Room | 328 | SF
| Stairs (x2 for risers) | 80 | SF
| Total SF | 1181 | SF
| Conversion to SY (X 1.35 / 9) | 177.15 | SY
| 12' Roll Layout - Actual | 173.33 | SY
ALLOWANCE BREAKDOWN
| Installation Labor | pattern repeat |  |  | 12.5 | PER SY
| Carpet Pad (memory foam) |  |  |  | 9.5 | PER SY
| Material Allowance | with tax |  |  | 85 | PER SY
| Floor Prep / Tack Strip / Etc. |  |  |  | 1.5 | PER SY
| Carpet Material, Labor, and Pad |  | ALLOWANCE | 177 | 108.5 | SY | 19204.5
| Walk Off Carpet |  | ALLOWANCE | 0 | 50 | SY | 0
| VCT (furnace room) |  | ALLOWANCE | 0 | 3 | SF | 0
| Additional Labor for Stair |  | ALLOWANCE | 18 | 30 | EA | 540
9.72 | Wall Coverings/Faux Finishing
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
9.91 | Painting
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0

## DIV 10 SPECIALTIES
10.000 | SPECIALTIES
10.05 | Finish Hardware Allowance
Cabinet Hardware
| POWDER BATH |  | DOORS/DRAWERS |  | 2 | 15 | 30
| SERVICE ENTRY |  | DOORS/DRAWERS |  | 10 | 12 | 120
|  |  | HOOKS |  | 6 | 35 | 210
| PRIMARY BATH |  | DOORS/DRAWERS |  | 25 | 15 | 375
| PRIMARY WARDROBE |  | DOORS/DRAWERS |  | 24 | 12 | 288
| GATHERING ROOM |  | DOORS/DRAWERS |  | 6 | 15 | 90
| KITCHEN ISLAND |  | DOORS/DRAWERS |  | 22 | 18 | 396
|  |  | APPLIANCE PULLS |  | 2 | 350 | 700
| KITCHEN |  | DOORS/DRAWERS |  | 34 | 18 | 612
|  |  | APPLIANCE PULLS |  | 3 | 350 | 1050
| PANTRY |  | OPEN SHELVES
| LOUNGE |  | DOORS/DRAWERS |  | 15 | 18 | 270
|  |  | APPLIANCE PULLS |  | 2 | 200 | 400
| LAUNDRY |  | DOORS/DRAWERS |  | 25 | 10 | 250
| OFFICE |  | DOORS/DRAWERS |  | 20 | 12 | 240
| BATHROOM 2 |  | DOORS/DRAWERS |  | 7 | 10 | 70
| BATHROOM 3 |  | DOORS/DRAWERS |  | 10 | 10 | 100
| LL BAR |  | DOORS/DRAWERS |  | 23 | 12 | 276
| LL FAMILY ROOM |  | DOORS/DRAWERS |  | 6 | 12 | 72
| GARAGE |  | DOORS/DRAWERS |  | 11 | 10 | 110
| OUTDOOR |  | DOORS/DRAWERS |  | 4 | 10 | 40
[6 empty] | SUBTOTAL | 5699
[6 empty] | FREIGHT | 100
[6 empty] | 7% TAX | 405.93
[6 empty] | TOTAL | 6204.93
Door Hardware
| LOCATION |  |  |  | QTY | UNIT COST | SUBTOTAL
Lower Level
| DOOR LEVERS (PASSAGE/PRIVACY) |  |  | Emtek | 11 | 190 | 2090
| DUMMIES |  |  | Emtek | 0 | 185 | 0
| POCKET DOOR |  |  | Emtek | 0 | 275 | 0
| 3 1/2" HINGES - per pair |  |  |  | 17 | 14 | 238
| 4" HINGES - per pair |  |  |  | 0 | 18 | 0
| HINGE DOOR STOP |  |  |  | 6 | 10 | 60
| BASE DOOR STOP |  |  |  | 8 | 15 | 120
Main Level
| FRONT DOOR HARDWARE |  |  |  | 1 | 650 | 650
| PATIO - MULTIPOINT |  |  | Emtek | 0 | 575 | 0
| DOOR LEVERS (PASSAGE/PRIVACY) |  |  | Emtek | 7 | 190 | 1330
| DEADBOLTS (AT GARAGE) |  |  | Emtek | 1 | 100 | 100
| DUMMIES |  |  | Emtek | 2 | 185 | 370
| POCKET DOOR |  |  | Emtek | 5 | 275 | 1375
| FLUSH BOLT @ OFFICE |  |  |  | 2 | 75 | 150
| SUMP CLOSET KNOBS |  |  |  | 1 | 25 | 25
| 3 1/2" HINGES - per pair |  |  |  | 0 | 14 | 0
| 4" HINGES - per pair |  |  |  | 18 | 18 | 324
| SPRING HINGE |  |  |  | 2 | 45 | 90
| HINGE DOOR STOP |  |  |  | 6 | 10 | 60
| BASE DOOR STOP |  |  |  | 6 | 15 | 90
| FLOOR STOP |  |  |  | 1 | 50 | 50
[6 empty] | SUBTOTAL | 7122
[6 empty] | FREIGHT | 100
[6 empty] | 7% TAX | 505.54
[6 empty] | TOTAL | 7727.54
Bath Accessories - PER BRIGGS QUOTE
POWDER BATH
|  |  | TOILET PAPER HOLDERS |  | 0 | 75 | 0
|  |  | TOWEL RINGS |  | 0 | 75 | 0
PRIMARY BATH
|  |  | TOILET PAPER HOLDERS |  | 0 | 75 | 0
|  |  | TOWEL BARS |  | 0 | 100 | 0
|  |  | TOWEL RINGS |  | 0 | 75 | 0
|  |  | ROBE HOOKS |  | 0 | 35 | 0
BATHROOM
|  |  | TOILET PAPER HOLDERS |  | 0 | 75 | 0
|  |  | TOWEL BAR |  | 0 | 100 | 0
|  |  | TOWEL RINGS |  | 0 | 75 | 0
|  |  | ROBE HOOKS |  | 0 | 35 | 0
BATHROOM
|  |  | TOILET PAPER HOLDERS |  | 0 | 75 | 0
|  |  | TOWEL BARS |  | 0 | 100 | 0
|  |  | TOWEL RINGS |  | 0 | 75 | 0
|  |  | ROBE HOOKS |  | 0 | 35 | 0
BATHROOM
|  |  | TOILET PAPER HOLDERS |  | 0 | 75 | 0
|  |  | TOWEL BARS |  | 0 | 100 | 0
|  |  | TOWEL RINGS |  | 0 | 75 | 0
|  |  | ROBE HOOKS |  | 0 | 35 | 0
[6 empty] | SUBTOTAL | 0
[6 empty] | FREIGHT | 0
[6 empty] | 7% TAX | 0
[6 empty] | PER BRIGGS QUOTE - TOTAL | 1240
[6 empty] | TOTAL ALL ACCESSORIES | 15172.47
[6 empty] | TOTAL LABOR | 5200
10.14 | Address Numbers
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
10.31 | Fireplaces
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
10.314 | Fireplace Facings
[6 empty] | TOTAL | 12318
Gathering Room | [6 empty] | 9518
|  | Thin Stone - Flats | ALLOWANCE | 50 | 10.5 | SF | 525
|  | Thin Stone - Corners | ALLOWANCE | 12 | 14 | SF | 168
|  | Setting Materials | ALLOWANCE | 1 | 350 | SF | 350
|  | Labor | ALLOWANCE | 50 | 20 | SF | 1000
|  | Delivery | ALLOWANCE | 1 | 75 | EA | 75
|  | Sealer | ALLOWANCE | 0 | 0 | SF | 0
|  | Stone Slab Surround & Hearth | ALLOWANCE | 1 | 7400 | EA | 7400
|  | Wood mantle & wood paneling | ALLOWANCE | in cabinetry | 0 | EA | 0
|  | Labor - Surround | ALLOWANCE | 0 | 0 | EA | 0
LL Family Room | [6 empty] | 2800
|  | Field Material | ALLOWANCE | 0 | 0 | SF | 0
|  | Labor/Setting Materials | ALLOWANCE | 0 | 0 | SF | 0
|  | Delivery | ALLOWANCE | 0 | 0 | EA | 0
|  | Drywall | ALLOWANCE | in drywall | 0 | SF | 0
|  | Stone Slab Surround & Hearth | ALLOWANCE | 1 | 2800 | EA | 2800
|  | Wood paneling | ALLOWANCE | in cabinetry | 0 | EA | 0
|  | Labor - Surround | ALLOWANCE | 0 | 0 | EA | 0
Exterior Covered Patio - accounted for in 04-430 Stone Masonry | [6 empty] | 0
|  | Field Material | ALLOWANCE | 0 | 0 | SF | 0
|  | Labor/Setting Materials | ALLOWANCE | 0 | 0 | SF | 0
|  | Delivery | ALLOWANCE | 0 | 0 | EA | 0
|  | Sealer | ALLOWANCE | 0 | 0 | SF | 0
|  | Precast Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Metal Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Labor - Surround | ALLOWANCE | 0 | 0 | EA | 0
10.562 | Storage Shelving
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
10.566 | Wine Cellar Racks/Cooling
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
10.572 | Closets
|  |  |  | Company | Company | Company | Company
Main Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
Lower Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
Upper Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
10.712 | Exterior Shutters
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0

## DIV 11 EQUIPMENT
11.000 | EQUIPMENT
11.302 | Appliances Allowance
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
11.52 | TV's Allowance
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
11.66 | Athletic Equipment
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
11.678 | Game Room Equipment (Golf Simulator)
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 12 FURNISHINGS
12.000 | FURNISHINGS
12.17 | Art Glass
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
12.2 | Window Treatments
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
12.25 | Motorized Shades
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 13 SPECIAL CONST.
13.000 | SPECIAL CONSTRUCTION
13.112 | Swimming Pool
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
13.174 | Sauna
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
13.26 | Storm Shelter Room(s)
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
13.342 | Screen Porch Systems
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 14 CONVEYING SYSTEMS
14.000 | CONVEYING SYSTEMS
14.05 | Elevators
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 21 FIRE SUPRESSION
21.000 | FIRE SUPPRESSION
21.05 | Fire Suppression
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 22-23 PLUM-HVAC
22.000 | PLUMBING
22.05 | Plumbing
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
22.322 | Water Filtration System
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
22.4 | Plumbing Fixtures Allowance
|  | QUANITITY | UNIT COST | SUBTOTAL
BATHROOM
| SINK SS | 0 | 100 | 0
| FAUCET | 0 | 250 | 0
| TOILET | 0 | 400 | 0
| SEAT/TRIP LEVER | 0 | 115 | 0
| SHOWER VALVE/TRIM | 0 | 450 | 0
| FIBERGLASS SHOWER BASE | 0 | 650 | 0
BAR
| SINK | 0 | 450 | 0
| FAUCET | 0 | 475 | 0
| RO FAUCET | 0 | 400 | 0
| AIR SWITCH | 0 | 125 | 0
| DISPOSAL | 0 | 175 | 0
| BASKET STRAINER | 0 | 70 | 0
KITCHEN
| SINK | 0 | 800 | 0
| FAUCET | 0 | 500 | 0
| RO FAUCET | 0 | 400 | 0
| SOAP DISPENSER | 0 | 150 | 0
| AIR SWITCH | 0 | 125 | 0
| DISPOSAL | 0 | 300 | 0
| BASKET STRAINER | 0 | 70 | 0
| POT FILLER | 0 | 700 | 0
POWDER BATH
| SINK | 0 | 175 | 0
| FAUCET | 0 | 400 | 0
| TOILET | 0 | 400 | 0
| SEAT/TRIP LEVER | 0 | 115 | 0
LAUNDRY
| SINK | 0 | 225 | 0
| FAUCET | 0 | 200 | 0
| BASKET STRAINER | 0 | 70 | 0
PRIMARY BATH
| SINK | 0 | 150 | 0
| FAUCETS | 0 | 400 | 0
| TOILET | 0 | 400 | 0
| SEAT/TRIP LEVER | 0 | 115 | 0
| BIDET SEAT | 0 | 1000 | 0
| SHOWER VALVE/TRIM | 0 | 1250 | 0
| WHIRLPOOL TUB | 0 | 4750 | 0
| TUB VALVE/FAUCET | 0 | 1000 | 0
GUEST BATH
| SINK | 0 | 100 | 0
| FAUCET | 0 | 250 | 0
| TOILET | 0 | 400 | 0
| SEAT/TRIP LEVER | 0 | 115 | 0
| SHOWER VALVE/TRIM | 0 | 450 | 0
| FIBERGLASS SHOWER BASE | 0 | 650 | 0
|  |  | SUBTOTAL | 0
|  |  | FREIGHT | 0
|  |  | 7% TAX | 0
|  |  | TOTAL | 0
23.000 | HVAC
23.05 | HVAC
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
23.4 | Duct Cleaning
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 26-28 ELEC. - LV
26.000 | ELECTRICAL
26.05 | Electrical Service & Wiring
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
26.41 | Lightning Protection
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
26.505 | Light Fixtures Allowance
*ALLOWANCE UNIT COSTS INCLUDE ALL BULBS
| LOCATION | TYPE |  | QTY | UNIT PRICE | SUBTOTAL
Main Level
| FOYER | CEILING MOUNT |  | 9 | 550 | 4950
| FOYER/STAIR | ART LIGHT |  | 1 | 675 | 675
| OFFICE | ART LIGHT |  | 3 | 675 | 2025
| POWDER BATH | WALL MOUNT |  | 1 | 1200 | 1200
| POWDER BATH | CEILING MOUNT |  | 1 | 2500 | 2500
| KITCHEN | PENDANTS |  | 3 | 1200 | 3600
| KITCHEN | WALL MOUNT |  | 2 | 1200 | 2400
| DINING | CEILING MOUNT |  | 1 | 5000 | 5000
| LOUNGE | CEILING MOUNT |  | 1 | 7500 | 7500
| GATHERING ROOM | CANS - by elect. |  | 0 | 0 | 0
| LAUNDRY ROOM | CANS - by elect. |  | 0 | 0 | 0
| PRIMARY BEDROOM | CEILING MOUNT |  | 1 | 3000 | 3000
| PRIMARY BATHROOM | WALL MOUNT |  | 4 | 1000 | 4000
| PRIMARY WARDROBE | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| LAUNDRY ROOM | CANS - by elect. |  | 0 | 0 | 0
| SERVICE ENTRY | CANS - by elect. |  | 0 | 0 | 0
| GARAGE | LED - by elect. |  | 0 | 0 | 0
Lower Level
| BATHROOM 2 VANITY | WALL MOUNT |  | 1 | 750 | 750
| BATHROOM 3 VANITY | WALL MOUNT |  | 1 | 750 | 750
| BEDROOM 2 | CANS - by elect. |  | 0 | 0 | 0
| BEDROOM 3 | CANS - by elect. |  | 0 | 0 | 0
| WARDROBE 2 | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| WARDROBE 3 | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| FITNESS ROOM | CEILING FAN |  | 1 | 600 | 600
| BILLIARDS | CEILING MOUNT |  | 3 | 750 | 2250
| LL FAMILY ROOM | CANS - by elect. |  | 0 | 0 | 0
| MECHANICAL/STORAGE | LED - by elect. |  | 0 | 0 | 0
EXTERIOR LIGHTING
| FRONT ENTRY | WALL MOUNT |  | 1 | 1000 | 1000
| WALL PIERS | BASE MOUNT |  | 3 | 1000 | 3000
| COVERED PATIO | CEILING FAN |  | 2 | 750 | 1500
| COVERED PATIO | WALL MOUNT |  | 3 | 750 | 2250
| FLOODS | WALL MOUNT - by elect. |  | 0 | 0 | 0
[5 empty] | SUBTOTAL | 48950
[5 empty] | FREIGHT | 0
[5 empty] | 7% TAX | 3426.5
[5 empty] | TOTAL (INCLUDING BULBS) | 52376.5
26.57 | Lighting Control System Allowance
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
27.000 | COMMUNICATIONS
27.41 | Audio-Visual Systems/Structured Wire/Sound System Allowance
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
28.000 | ELECTRONIC SAFETY & SECURITY
28.07 | Security System/Fire Protection/Video Surveillance Allowance
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 31-32 EARTH-SITE
31.000 | EARTHWORK
31.218 | Site Demolition
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
31.23 | Excavation/Fill/Grading/Silt Fence
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
31.26 | Surveying
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.000 | EXTERIOR IMPROVEMENTS
32.13 | Exterior Concrete Flatwork
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
Unit Rate Estimate
Driveway |  | 0 | SF
Front Stoop |  | 0 | SF
Front Walk |  | 0 | SF
City Sidewalks |  | 0 | SF
AC Pads |  | 0 | SF
Pool Deck |  | 0 | SF
Rear Patio |  | 0 | SF
|  | 0 | SF
MATERIAL
sleeve materials (pvc for under slabs) |  |  | 0 | 75 | EA | 0
Granular (SF x .25ft x 1.25 / 18 = X tons) |  |  | 0 | 16 | TON | 0
Additive (Xypex for water impermeable) |  |  | 0 | 131.85 | BOX | 0
expansion joints at walls |  |  | 0 | 150 | EA | 0
SUBCONTRACTOR
Driveway (5" with rebar) |  |  | 0 | 0 | SF | 0
Driveway Curb |  |  | 0 | 0 | LF | 0
Street Curb Cut |  |  | 0 | 0 | SF | 0
Front Walks (4") |  |  | 0 | 0 | SF | 0
City Sidewalks (4") |  |  | 0 | 0 | SF | 0
Front Stoop |  |  | 0 | 800 | EA | 0
Concrete Steps |  |  | 0 | 0 | LF | 0
AC Pads (4") |  |  | 0 | 0 | SF | 0
Rear Patio (4") |  |  | 0 | 0 | SF | 0
Pool Deck (4") |  |  | 0 | 0 | SF | 0
Trench Drain |  |  | 0 | 0 | LF | 0
Paver inset areas |  |  | 0 | 0 | LF | 0
Additional Concrete Material for 5" thick |  |  | 0 | 82.5 | CY | 0
Pump Charge for elevated balconies |  |  | 0 | 1500 | EA | 0
Grading |  |  | 0 | 0.4 | SF | 0
Cure & Seal |  |  | 0 | 0.05 | SF | 0
Sealer (Application of Stifle) |  |  | 0 | 0.45 | SF | 0
[5 empty] | TOTAL | 0
32.142 | Pavers Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
Unit Rate Estimate
Driveway | 0 | SF
Front Walk | 0 | SF
Front Stoop | 0 | SF
Rear Patio | 0 | SF
Pool Deck | 0 | SF
| 0 | SF
| 0 | 8% waste
| 0 | total SFpavers
STEPPING STONES |  | 0 | EA
NOTE: verify full pallet quantities or sf count
Paver Material (incl tax) |  |  | ALLOWANCE | 0 | 6.25 | SF | 0
Bullnose Edging (lakeside nosing) |  |  | ALLOWANCE | 0 | 12 | LF | 0
Front Stoop (brick and mortar) |  |  | ALLOWANCE | 0 | 7.25 | SF | 0
Front Stoop |  |  | ALLOWANCE | 0 | 15.75 | SF | 0
Aluminum Edging |  |  | ALLOWANCE | 0 | 3.25 | LF | 0
Subcontractor Installation |  |  | ALLOWANCE | 0 | 6.75 | SF | 0
Palmeric Sand |  |  | ALLOWANCE | 0 | 1 |  | 0
additional for asphalt set |  |  | ALLOWANCE | 0 | 1.75 | SF | 0
Stepping Stones |  |  | ALLOWANCE | 0 | 100 | EA | 0
[6 empty] | TOTAL | 0
OPTION
Sealer / Enhancer |  |  | ALLOWANCE | 0 | 1.5 | SF | 0
32.18 | Athletic/Recreational Surfacing
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.181 | Artificial Turf
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.3 | Landscape Lighting Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.31 | Fences/Gates
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.32 | Retaining Walls Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.392 | Fire Pit Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.394 | Exterior Grill/Hood
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.8 | Irrigation Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.922 | Seeding/Sod Allowance
| Sod - Raw Area | 0 | SF | 0.33 | 0 | 0
| (less beds) |  |  |  | 7% TAX | 0
[5 empty] | TOTAL | 0
32.931 | Landscaping Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0

## DIV 33 UTILITES
33.000 | UTILITIES
33.02 | Sewer / Water Utilities
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
33.462 | Underground Buried Drainage
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0