## Sheet1
[5 empty] | #VALUE! |  |  |  | CONSTRUCTION SCHEDULE
Project Name: |  | Wood Residence | [6 empty] | 2026-01-08 | [52 empty] | 2027-01-14
Address: |  | 3435 N 140th Circle, Omaha, NE 68154 | [6 empty] | 2026-01-08 |  |  |  | 2026-02-05 |  |  |  | 2026-03-05 |  |  |  |  | 2026-04-02 |  |  |  |  | 2026-05-07 |  |  |  | 2026-06-04 |  |  |  | 2026-07-02 |  |  |  |  | 2026-08-06 |  |  |  | 2026-09-10 |  |  |  | 2026-10-08 |  |  |  |  | 2026-11-05 |  |  |  | 2026-12-10 |  |  |  |  | 2027-01-14 |  |  |  | 2027-02-18 |  |  |  | 2027-03-18
Project Start Date: |  | 2026-09-01 | [5 empty] | Week Starting: | time axis 2026-01-01 to 2027-03-18
# | Task Name |  |  | Duration | Start | Finish | Status | % Complete
1 | PRECONSTRUCTION
2 | Startup |  |  | 1 | 2026-01-15 | 2026-01-15
3 | Mobilize - Contract/Deposit |  |  | 1 | 2026-01-15 | 2026-01-15
4 | Permit |  |  | 0 | 2026-03-09 | 2026-03-09 | bar: 2026-03-05
5 | Selections/Approvals |  |  | 205 | 2026-01-16 | 2026-11-09
6 | CONSTRUCTION |  |  | 528 | 2026-01-19 | 2028-02-23
7 | Shell |  |  | 95 | 2026-01-19 | 2026-06-02
8 | Demolition/Removals |  |  | 24 | 2026-01-19 | 2026-02-20
9 | MEP Disconnects |  |  | 8 | 2026-01-19 | 2026-01-28
10 | Temp Protection (McNeil Demo) |  |  | 5 | 2026-01-19 | 2026-01-23
11 | Subcontractor Demolition/Cleanup |  |  | 10 | 2026-02-02 | 2026-02-13
12 | Framing Evaluation/Addt'l Demo |  |  | 1 | 2026-02-16 | 2026-02-16
13 | Framing |  |  | 22 | 2026-02-19 | 2026-03-20
14 | Temp walls/cribbing |  |  | 2 | 2026-02-19 | 2026-02-20
15 | Main Level Walls/Beams |  |  | 17 | 2026-02-23 | 2026-03-17
16 | Lower Level Walls/Ceilings |  |  | 3 | 2026-03-18 | 2026-03-20
17 | Rough-Ins |  |  | 49 | 2026-03-18 | 2026-05-26
18 | Fireplace Rough-In |  |  | 2 | 2026-03-18 | 2026-03-19
19 | HVAC |  |  | 3 | 2026-03-24 | 2026-03-26
20 | Plumbing |  |  | 7 | 2026-03-23 | 2026-03-31
21 | CLIENT ELECTRICAL MTG |  |  | 0 | 2026-04-03 | 2026-04-03 | bar: 2026-04-02
22 | Electrical |  |  | 15 | 2026-04-13 | 2026-05-01
23 | AV Sound/Security |  |  | 13 | 2026-04-13 | 2026-04-29
24 | Foam/Caulk/Photos |  |  | 2 | 2026-04-30 | 2026-05-01
25 | Inspections/compliance |  |  | 5 | 2026-05-04 | 2026-05-08
26 | Insulation |  |  | 2 | 2026-05-11 | 2026-05-12
27 | Interior Finishes |  |  | 357 | 2026-05-14 | 2027-10-18
28 | Drywall/Prime/Clean |  |  | 20 | 2026-05-14 | 2026-06-11
29 | Tile (Upper Level) |  |  | 20 | 2026-06-29 | 2026-07-27
30 | Cabinets |  |  | 45 | 2026-06-17 | 2026-08-20
31 | Trim |  |  | 50 | 2026-06-22 | 2026-08-31
32 | Fireplace Facings |  |  | 5 | 2026-09-01 | 2026-09-08
33 | Countertops (Ph. 1) |  |  | 5 | 2026-09-18 | 2026-09-24
34 | Tile (Main Level) |  |  | 25 | 2026-08-20 | 2026-09-24
35 | Countertops (Ph. 2) |  |  | 5 | 2026-10-09 | 2026-10-16
36 | Paint/Stain |  |  | 55 | 2026-09-01 | 2026-11-19
37 | Sauna Install |  |  | 2 | 2026-11-19 | 2026-11-20
38 | Mirrors/Glass Shelves/Etc. |  |  | 4 | 2026-11-19 | 2026-11-24
39 | Finish Hardware |  |  | 7 | 2026-11-18 | 2026-11-27
40 | Wood Floor Install (pre-finished) |  |  | 10 | 2026-11-23 | 2026-12-07
41 | Plumbing Finish |  |  | 10 | 2026-11-18 | 2026-12-02
42 | Appliances |  |  | 3 | 2026-12-04 | 2026-12-08
43 | Window Cleaning/Rough Clean |  |  | 3 | 2026-12-09 | 2026-12-11
44 | Closet Systems |  |  | 15 | 2026-11-18 | 2026-12-09
45 | HVAC Finish |  |  | 5 | 2026-12-14 | 2026-12-18
46 | Electrical Finish |  |  | 17 | 2026-11-25 | 2026-12-18
47 | Sauna Install |  |  | 3 | 2026-12-22 | 2026-12-24
48 | Preliminary Cleaning |  |  | 3 | 2026-12-22 | 2026-12-24
49 | Carpet |  |  | 10 | 2026-12-29 | 2027-01-12
50 | Final Inspections |  |  | 5 | 2027-01-14 | 2027-01-21
51 | AV Sound/Security Finish |  |  | 15 | 2027-01-04 | 2027-01-25
52 | Preliminary Checklist |  |  | 10 | 2027-01-25 | 2027-02-05
53 | LL Storage Shelving |  |  | 3 | 2027-01-25 | 2027-01-27
54 | Final Cleaning |  |  | 2 | 2027-02-08 | 2027-02-09
55 | POST CONSTRUCTION |  |  | 5 | 2027-02-09 | 2027-02-16
56 | CLIENT WALK THROUGH |  |  | 0 | 2027-02-09 | 2027-02-09 | bar: 2027-02-04
57 | Completion Checklist |  |  | 5 | 2027-02-10 | 2027-02-17
58 | OCCUPANCY |  |  | 0 | 2027-02-17 | 2027-02-17 | bar: 2027-02-11
GANTT LEGEND
Light Bar |  |  | Scheduled Work
Progress |  |  | Completed Portion
Gold |  |  | Complete
Orange |  |  | Blocked
Formulas:
Start = MIN([Start, row below]:J9)
Start = MIN([Start, row below],J32,J60)
Finish = IF(OR([Start]="",[Duration]=""),"",IF([Duration]=0,[Start],WORKDAY([Start],[Duration]-1,'Holidays 2026-2027'!$B2:B23)))

## Holidays 2026-2027
Holiday | Observed Date
New Year's Day | 2026-01-01
Martin Luther King Jr. Day | 2026-01-19
Washington's Birthday (Presidents Day) | 2026-02-16
Memorial Day | 2026-05-25
Juneteenth National Independence Day | 2026-06-19
Independence Day (Observed) | 2026-07-03
Labor Day | 2026-09-07
Columbus Day | 2026-10-12
Veterans Day | 2026-11-11
Thanksgiving Day | 2026-11-26
Christmas Day | 2026-12-25
New Year's Day | 2027-01-01
Martin Luther King Jr. Day | 2027-01-18
Washington's Birthday (Presidents Day) | 2027-02-15
Memorial Day | 2027-05-31
Juneteenth (Observed) | 2027-06-18
Independence Day (Observed) | 2027-07-05
Labor Day | 2027-09-06
Columbus Day | 2027-10-11
Veterans Day | 2027-11-11
Thanksgiving Day | 2027-11-25
Christmas Day (Observed) | 2027-12-24