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AGREEMENT REQUEST

	Requester:
	Grady

	To Company:
	BDB

	Vendor #:
	

	Date:
	9/32026

	Job #:
	1-2510

	Agreement Type:
	Subcontract

	Milestones:
	September 8th 2026



Description:  ___ Foundations____

Item Number	Description	Phase Code	Qty	UOM	Unit Price	Totals
1	Foundations	03-300	1	LS	$76,165	$76,165

Total Agreement Amount:  $ _$76,165_
Inclusions:
Item Number	Description
	Review site, site plans, soils report, boring logs as they pertain to this Work before proceeding with any Work. Identify any concerns with the Contractor prior to proceeding with Work.
	Agreement total is based on REV 02 dated 08/31/26 and includes all foundations for the residence, excluding site walls. 
	Verify that existing grades match the plans prior to starting Work. Notify the Contractor of deviations.
	Review staking with the superintendent before proceeding with Work
	Review, verify, and confirm locations of blockouts and embedded items, including, and not limited to, weld plates, anchor bolts, and anchors.
	Provide metals and reinforcing steel within foundations for complete installation, including and not limited to, rebar, weld plates, anchors, stirrups, wall ties, chairs, and tie-wire.
	Provide footings complete, including and limited to excavation, formwork design, formwork, shoring, and placement of concrete.
	Excavation for footings. Place in an approved location as agreed upon by the backfill company and McNeil superintendent. 
	Footings include and are not limited to concrete piers, pilasters, grade beams, trench footings, column pads, and stoop footings.
	Provide complete concrete wall systems, including and limited to formwork design, formwork, shoring, and placement and finish of concrete.
	Provide brick ledge forming. Removal of forming.
	Coordinate sleeves and penetrations through the footings before final placement of the concrete with other trades.
	Provide block-outs for known wall penetrations. Removal of blockouts.
	Remove forms and wall ties.
	Utilize most recent industry standard practices for quality concrete placement, including and not limited to curing compounds, insulation blankets, or poly protection as required.
	Concrete pumping charges. Review site logistic plan for concrete placement prior to the operation with the Contractor.
	Wash out in designated concrete areas only. Provide a washout container as needed.
	Shipping and handling of materials.
	Fees for and scheduling of testing and inspections per city rules and regulations
	Mobilization and demobilization of tools, materials, and equipment necessary to perform Work.
	Schedule utility locates prior to digging as it pertains to this Work. Identify any concerns with the Contractor prior to proceeding with Work.
	Review and sign off of concrete placement areas prior to placing concrete. Placement of concrete is the Subcontractor's acceptance of the conditions.
	Place concrete per the engineer's recommendations, including and not limited to vibrating methods to ensure proper consolidation.
	Cleanup from Work, including and not limited to excess materials & debris.
	Provide equipment to complete the Work, including and not limited to small tools and equipment, grading equipment, and equipment for handling of materials.
	Sales taxes.
	Complete Work per McNeil's safety program specifications and the specifications book, available upon request.
	Maintain a clean and safe site by daily pickup of Subcontractor's materials and tools.


Exclusions:
Item Number	Description
1	Haul off of excess spoils from footing excavation.
2	Cold weather concreting, including and not limited to, concrete mix design adjustments, additional protection of concrete and curing adjustments.
3	Excavation for foundation walls.
4	Waterproofing.
5	Site foundation walls and footings are excluded in the base bid until further design and quantities are finalized. 
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