## MAIN
PROJECT COST SUMMARY |  | EXCLUDING LOWER LEVEL FINISH
PROJECT | CROCKETT | [6 empty] | LOWER LEVEL | 0
PM | Grady | [6 empty] | MAIN LEVEL | 2960
LOCATION | 1702 S 150th Ave.; Omaha, NE 68144 | [6 empty] | UPPER LEVEL | 1661
DATE | 46254 | [6 empty] | TOTAL FINISHED SF | 4621
LOT # | 22 Heartwood Estates | [6 empty] | GARAGE | 1121
ZONING | [7 empty] | LOWER UNFINISHED | 2784
[8 empty] | UPPER UNFINISHED | 577
[8 empty] | COVERED PATIO | 624
[8 empty] | TOTAL SF UNDER ROOF | 9727
PHASE | DESCRIPTION | ALLOW. | LABOR | MATERIAL | OTHER | SUBCONT. | DIVISION | FINISHED COST/SF | UNDER ROOF
1 | GENERAL REQUIREMENTS |  |  |  |  | TOTAL | 192211.66 | 41.5953 | 19.7606
01.120 | Superintendent | 0 | 89775 | 0 | 0 | 0 | 89775 | 19.4276 | 9.2295
01.170 | Travel/Pickup/Deliveries | 0 | 2500 | 0 | 0 | 0 | 2500 | 0.54101 | 0.25702
01.205 | MUD Fees | 0 | 0 | 0 | 4687 | 0 | 4687 | 1.0143 | 0.48185
01.214 | Bldg. Permit | 0 | 0 | 0 | 14170.46 | 0 | 14170.46 | 3.0665 | 1.4568
01.230 | Builders Risk | 0 | 0 | 0 | 4608 | 0 | 4608 | 0.99719 | 0.47373
01.235 | General Liability | 0 | 0 | 0 | 8864 | 0 | 8864 | 1.9182 | 0.91128
01.452 | Testing/Inspections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
01.454 | Mockups | 1500 | 0 | 0 | 0 | 0 | 1500 | 0.32461 | 0.15421
01.501 | Temporary Utilities | 0 | 0 | 0 | 7597.2 | 0 | 7597.2 | 1.6441 | 0.78104
01.538 | Technology / prints | 0 | 0 | 0 | 1500 | 0 | 1500 | 0.32461 | 0.15421
01.540 | Equipment (Forklift/Skid Loader) | 0 | 0 | 0 | 2250 | 0 | 2250 | 0.48691 | 0.23131
01.560 | Temporary Barriers/Enclosures/Protection | 0 | 2400 | 1100 | 0 | 0 | 3500 | 0.75741 | 0.35982
01.578 | Site Maintenance (Snow Removal/Mowing) | 0 | 1250 | 150 | 0 | 0 | 1400 | 0.30296 | 0.14393
01.740 | Cleaning & Waste Management (Dumpsters) | 0 | 12485 | 0 | 7400 | 6725 | 26610 | 5.7585 | 2.7357
01.810 | Warranties | 0 | 0 | 0 | 18000 | 0 | 18000 | 3.8953 | 1.8505
01.830 | Small Tools/Supply/Rentals | 0 | 0 | 0 | 2250 | 0 | 2250 | 0.48691 | 0.23131
01.840 | Punchlist | 0 | 3000 | 0 | 0 | 0 | 3000 | 0.64921 | 0.30842
2 | EXISTING CONDITIONS |  |  |  |  | TOTAL | 0 | 0 | 0
02.010 | Demolition | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CONCRETE |  |  |  |  | TOTAL | 111245 | 24.0738 | 11.4367
03.300 | Footings / Foundations | 0 | 0 | 0 | 0 | 80749 | 80749 | 17.4744 | 8.3015
03.320 | Interior Concrete Flatwork | 0 | 0 | 0 | 1700 | 28796 | 30496 | 6.5994 | 3.1352
4 | MASONRY |  |  |  |  | TOTAL | 116214 | 25.1491 | 11.9476
04.210 | Brick Masonry / Precast Sills & Caps | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
04.220 | Concrete Unit Masonry (Blockwork) | 0 | 0 | 1150 | 0 | 1550 | 2700 | 0.58429 | 0.27758
04.430 | Stone Masonry / Precast Sills & Caps | 0 | 0 | 14691 | 0 | 98823 | 113514 | 24.5648 | 11.67
5 | METAL |  |  |  |  | TOTAL | 18000 | 3.8953 | 1.8505
05.120 | Structural Steel Material | 0 | 0 | 15500 | 0 | 0 | 15500 | 3.3543 | 1.5935
05.528 | Metal Interior Railings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
05.530 | Exterior Railings (stairs) | 0 | 0 | 0 | 0 | 2500 | 2500 | 0.54101 | 0.25702
05.700 | Decorative Metal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | CARPENTRY |  |  |  |  | TOTAL | 614056.97 | 132.884 | 63.1291
06.110 | Wood Framing | 0 | 3640 | 131138.24 | 1500 | 108784 | 245062.24 | 53.0323 | 25.194
06.150 | Composite Decking | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
06.380 | Cabinetry Allowance (Kitchen Hood) | 206405 | 0 | 0 | 8000 | 0 | 214405 | 46.398 | 22.0423
06.442 | Exterior Brackets/Timbers | 0 | 600 | 881 | 0 | 0 | 1481 | 0.32049 | 0.15226
06.460 | Wood Interior Trim & Stair Parts | 0 | 0 | 30806.73 | 0 | 64960 | 95766.73 | 20.7242 | 9.8455
06.612 | Countertop Allowance | 57342 | 0 | 0 | 0 | 0 | 57342 | 12.409 | 5.8951
7 | MOISTURE/THERMAL PROT. |  |  |  |  | TOTAL | 168517 | 36.4676 | 17.3247
07.130 | Waterproofing/Passive Radon/Termite Treatment | 0 | 375 | 150 | 0 | 9839 | 10364 | 2.2428 | 1.0655
07.210 | Insulation | 0 | 0 | 0 | 0 | 27390 | 27390 | 5.9273 | 2.8159
07.250 | Stucco/EIFS System (EIFS chimney) | 0 | 0 | 0 | 6977 | 23370 | 30347 | 6.5672 | 3.1199
07.300 | Roofing | 0 | 0 | 0 | 0 | 64231 | 64231 | 13.8998 | 6.6034
07.455 | Siding | 0 | 0 | 5260 | 0 | 11450 | 16710 | 3.6161 | 1.7179
07.469 | Exterior Carsiding (cedar) | 0 | 0 | 5525 | 0 | w/ siding | 5525 | 1.1956 | 0.56801
07.600 | Flashing/Brick Ledge | 0 | 800 | 1050 | 0 | 0 | 1850 | 0.40035 | 0.19019
07.630 | Gutters/Downspouts | 0 | 0 | 0 | 0 | 6600 | 6600 | 1.4283 | 0.67852
07.920 | Joint Sealants | 0 | 0 | 0 | 0 | 5500 | 5500 | 1.1902 | 0.56544
8 | DOORS & WINDOWS |  |  |  |  | TOTAL | 160973.2547 | 34.8352 | 16.5491
08.140 | Interior Wood Doors | 0 | 0 | 24014.2547 | 0 | 0 | 24014.2547 | 5.1968 | 2.4688
08.164 | Exterior Doors (w/ windows) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
08.178 | Front Door | 14559 | 520 | 0 | 0 | 0 | 15079 | 3.2631 | 1.5502
08.184 | Pet Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
08.385 | Garage Doors | 0 | 0 | 0 | 0 | 7790 | 7790 | 1.6858 | 0.80086
08.500 | Windows (Pella Reserve) | 0 | 0 | 0 | 0 | 100832 | 100832 | 21.8204 | 10.3662
08.600 | Roof Window/Skylights/Sun Tunnel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
08.817 | Mirrors/Glass Inserts/Shower Doors | 13258 | 0 | 0 | 0 | 0 | 13258 | 2.8691 | 1.363
9 | FINISHES |  |  |  |  | TOTAL | 247499 | 53.5596 | 25.4445
09.200 | Drywall | 0 | 0 | 0 | 1000 | 46793 | 47793 | 10.3426 | 4.9134
09.300 | Tile Allowance
| Floor Tile | 29710 | 0 | 0 | 0 | 0 | 29710 | 6.4293 | 3.0544
| Wall Tile/Columns | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tile Backsplash | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Shower/Tub Tile | 35271 | 0 | 0 | 0 | 0 | 35271 | 7.6328 | 3.6261
09.640 | Wood Flooring Allowance | 38124 | 0 | 0 | 0 | 0 | 38124 | 8.2502 | 3.9194
09.657 | Rubber Athletic Flooring Allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
09.672 | Epoxy Flooring | 7352 | 0 | 0 | 0 | 0 | 7352 | 1.591 | 0.75583
09.680 | Carpet Allowance | 19595 | 0 | 0 | 0 | 0 | 19595 | 4.2404 | 2.0145
09.720 | Wall Coverings/Faux Finishing | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
09.910 | Painting (assuming prefinished cabinets) | 0 | 0 | 0 | 0 | 64894 | 64894 | 14.0433 | 6.6715
09.920 | Stone at M Bath | 4760 | 0 | 0 | 0 | 0 | 4760 | 1.0301 | 0.48936
10 | SPECIALTIES |  |  |  |  | TOTAL | 112354 | 24.3138 | 11.5507
10.050 | Finish Hardware Allowance | 15597 | 4000 | 0 | 0 | 0 | 19597 | 4.2409 | 2.0147
10.140 | Address Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.310 | Fireplaces (Great Room and Cap Allowance) | 5000 | 1040 | 0 | 1200 | 9005 | 16245 | 3.5155 | 1.6701
10.311 | Fireplaces (Patio) |  | 520 | 0 | 0 | 4992 | 5512 | 1.1928 | 0.56667
10.314 | Fireplace Facings Allowance | 16627 | 0 | 0 | 0 | 0 | 16627 | 3.5981 | 1.7094
10.552 | Mailbox | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.562 | Storage Shelving | OPTION | 250 | 250 | 0 | 0 | 500 | 0.1082 | 0.051403
10.566 | Wine Cellar Racks/Cooling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.572 | Closet Systems Allowance | 53873 | 0 | 0 | 0 | 0 | 53873 | 11.6583 | 5.5385
10.712 | Exterior Shutters | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | EQUIPMENT |  |  |  |  | TOTAL | 78810.9812 | 17.055 | 8.1023
11.3 | Appliance Allowance (incl. grill/laundry) | 77770.9812 | 1040 | 0 | 0 | 0 | 78810.9812 | 17.055 | 8.1023
11.52 | TV's Allowance | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.660 | Athletic Equipment | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.678 | Game Room Equipment (Golf Simulator) | OPTION | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | FURNISHINGS |  |  |  |  | TOTAL | 0 | 0 | 0
12.170 | Art Glass | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.200 | Window Treatments | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.250 | Motorized Shades | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | SPECIAL CONSTRUCTION |  |  |  |  | TOTAL | 137094 | 29.6676 | 14.0942
13.112 | Swimming Pool (utilities) | 0 | 0 | 0 | 9500 | 119450 | 128950 | 27.9052 | 13.2569
13.174 | Sauna | in LL option | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Hot Tub | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.342 | Screen Porch System (Sun Shade at Patio) | 8144 | 0 | 0 | 0 | 0 | 8144 | 1.7624 | 0.83726
14 | CONVEYING SYSTEMS |  |  |  |  | TOTAL | 0 | 0 | 0
14.050 | Elevator | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22-23 | PLUMBING/HVAC SYSTEMS |  |  |  |  | TOTAL | 181006.0016 | 39.1703 | 18.6086
22.050 | Plumbing | 0 | 0 | 0 | 0 | 57900 | 57900 | 12.5298 | 5.9525
22.322 | Water Filtration System Allowance | 0 | 0 | 0 | 0 | 6067 | 6067 | 1.3129 | 0.62373
22.400 | Plumbing Fixt. Allowance (Air Dryer System) | 40979.2666 | 2000 | 3809.735 | 0 | 0 | 46789.0016 | 10.1253 | 4.8102
23.050 | HVAC | 0 | 0 | 0 | 0 | 67500 | 67500 | 14.6072 | 6.9394
23.400 | Duct Cleaning | 0 | 0 | 0 | 0 | 2750 | 2750 | 0.59511 | 0.28272
26-28 | ELECTRICAL & LOW VOLTAGE |  |  |  |  | TOTAL | 211591 | 45.789 | 21.753
26.050 | Electrical Service & Wiring | 0 | 0 | 0 | 0 | 72595 | 72595 | 15.7098 | 7.4632
26.410 | Lightning Protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26.505 | Light Fixtures Allowance | 43496 | 0 | 0 | 0 | 0 | 43496 | 9.4127 | 4.4717
26.570 | Lighting Control System Allowance | 29500 | 0 | 0 | 0 | 0 | 29500 | 6.3839 | 3.0328
27.410 | AV Systems Pre-Wire/Sound System Allowance | 60000 | 0 | 0 | 0 | 0 | 60000 | 12.9842 | 6.1684
28.070 | Security System/Fire Protect./Video Surv. Allowance | 6000 | 0 | 0 | 0 | 0 | 6000 | 1.2984 | 0.61684
31-32 | EARTHWORK & EXTERIOR IMPROVEMENTS |  |  |  |  | TOTAL | 419485 | 90.778 | 43.1258
31.128 | Site Demolition | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31.230 | Excavation/Fill/Grading/Silt Fence | 0 | 0 | 0 | 0 | 50440 | 50440 | 10.9154 | 5.1856
31.260 | Surveying | 0 | 0 | 0 | 0 | 2000 | 2000 | 0.43281 | 0.20561
32.130 | Exterior Concrete Flatwork | 0 | 0 | 0 | 6750 | 51595 | 58345 | 12.6261 | 5.9983
32.931 | Sitework Allowances
| Landscape - Plantings & Beds | 70000 | 0 | 0 | 0 | 0 | 70000 | 15.1482 | 7.1965
| Paver Allowance | 15000 | 0 | 0 | 0 | 0 | 15000 | 3.2461 | 1.5421
| Retaining Walls Allowance | 153250 | 0 | 0 | 0 | 0 | 153250 | 33.1638 | 15.7551
| Landscape Lighting Allowance | 15000 | 0 | 0 | 0 | 0 | 15000 | 3.2461 | 1.5421
| Irrigation Allowance | 14500 | 0 | 0 | 0 | 0 | 14500 | 3.1378 | 1.4907
| Seeding/Sod Allowance | 12500 | 0 | 0 | 0 | 0 | 12500 | 2.705 | 1.2851
| Underground Buried Drainage Allowance | 15000 | 0 | 0 | 0 | 0 | 15000 | 3.2461 | 1.5421
| Athletic/Recreation Surfacing Allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Artificial Turf Allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fire Pit Allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Exterior Grill/Hood Allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32.310 | Fences/Gates | 13450 | 0 | 0 | 0 | 0 | 13450 | 2.9106 | 1.3827
33 | UTILITIES |  |  |  |  | TOTAL | 8500 | 1.8394 | 0.87386
33.020 | Water/Sewer Utilities | 0 | 0 | 0 | 0 | 8500 | 8500 | 1.8394 | 0.87386
50 | CONTINGENCY |  |  |  |  | TOTAL | 45000 | 9.7382 | 4.6263
50.050 | Contingency | 0 | 0 | 0 | 45000 | 0 | 45000 | 9.7382 | 4.6263
50.070 | Arch/Engr Fees (Separate Agreement) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 1093563.2478 | 126195 | 235475.9597 | 152953.66 | 1214370 | 3245941.5476 | 702.4327 | 333.7043
McNeil Company Builders
PROJECT COST SUMMARY---MARKUP ANALYSIS
Project: | CROCKETT | [5 empty] | LOWER LEVEL | 0
Location: | 1702 S 150th Ave.; Omaha, NE 68144 | [5 empty] | MAIN LEVEL | 2960
Date: | 46254 | [5 empty] | UPPER LEVEL | 1661
Lot: | 22 Heartwood Estates | [5 empty] | TOTAL FINISHED SF | 4621
[7 empty] | GARAGE | 1121
[7 empty] | LOWER UNFINISHED | 2784
[7 empty] | COVERED PATIO | 624
[7 empty] | TOTAL SF UNDER ROOF | 9727
MARKUP ADJUSTMENTS
ACTUAL COST
[6 empty] | Allowances |  | 1093563.2478
[6 empty] | Labor |  | 126195
[6 empty] | Material |  | 235475.9597
[6 empty] | Other |  | 152953.66
[6 empty] | Subcontractor |  | 1214370
[6 empty] | NO MARKUP TOTAL |  | 2822557.8675
[6 empty] | MARKUP PERCENTAGE |  | 0.15
[6 empty] | MARKUP |  | 423383.6801
[6 empty] | BID |  | 3245941.5476

## BASE
PROJECT COST SUMMARY |  | LOWER LEVEL ESTIMATE
PROJECT | CROCKETT | [6 empty] | LOWER LEVEL | 1745
PM | Grady | [6 empty] | MAIN LEVEL | 0
LOCATION | 1702 S 150th Ave.; Omaha, NE 68144 | [6 empty] | UPPER LEVEL | 0
DATE | 46254 | [6 empty] | TOTAL FINISHED SF | 1745
LOT # | 22 | [6 empty] | GARAGE | 0
ZONING | [7 empty] | LOWER UNFINISHED | 0
[8 empty] | UPPER UNFINISHED | 0
[8 empty] | COVERED DECK | 0
[8 empty] | TOTAL SF UNDER ROOF | 1745
PHASE | DESCRIPTION | ALLOW. | LABOR | MATERIAL | OTHER | SUBCONT. | DIVISION | FINISHED COST/SF | UNDER ROOF
1 | GENERAL REQUIREMENTS |  |  |  |  | TOTAL | 18120.5 | 10.3842 | 10.3842
01.120 | Superintendent | 0 | 5845.5 | 0 | 0 | 0 | 5845.5 | 3.3499 | 3.3499
01.170 | Travel/Pickup/Deliveries | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
01.205 | MUD Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
01.214 | Bldg. Permit | 0 | 0 | 0 | 1500 | 0 | 1500 | 0.8596 | 0.8596
01.230 | Builders Risk | 0 | 0 | 0 | 1000 | 0 | 1000 | 0.57307 | 0.57307
01.235 | General Liability | 0 | 0 | 0 | 500 | 0 | 500 | 0.28653 | 0.28653
01.452 | Testing/Inspections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
01.454 | Mockups | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
01.501 | Temporary Utilities | 0 | 0 | 0 | 800 | 0 | 800 | 0.45845 | 0.45845
01.538 | Technology | 0 | 0 | 0 | 250 | 0 | 250 | 0.14327 | 0.14327
01.540 | Equipment (Forklift/Skid Loader) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
01.560 | Temporary Barriers/Enclosures/Protection | 0 | 750 | 300 | 0 | 0 | 1050 | 0.60172 | 0.60172
01.578 | Site Maintenance (Snow Removal/Mowing) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
01.740 | Cleaning & Waste Management (Dumpsters) | 0 | 1500 | 1250 | 0 | 1725 | 4475 | 2.5645 | 2.5645
01.810 | Warranties | 0 | 0 | 0 | 1500 | 0 | 1500 | 0.8596 | 0.8596
01.830 | Small Tools/Supply/Rentals | 0 | 0 | 0 | 450 | 0 | 450 | 0.25788 | 0.25788
01.840 | Punchlist | 0 | 750 | 0 | 0 | 0 | 750 | 0.4298 | 0.4298
2 | EXISTING CONDITIONS |  |  |  |  | TOTAL | 0 | 0 | 0
02.010 | Demolition | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CONCRETE |  |  |  |  | TOTAL | 0 | 0 | 0
03.300 | Footings / Foundations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
03.320 | Interior Concrete Flatwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MASONRY |  |  |  |  | TOTAL | 0 | 0 | 0
04.210 | Brick Masonry / Precast Sills & Caps | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
04.220 | Concrete Unit Masonry (Blockwork) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
04.430 | Stone Masonry / Precast Sills & Caps | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | METAL |  |  |  |  | TOTAL | 0 | 0 | 0
05.120 | Structural Steel Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
05.528 | Metal Interior Railing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
05.530 | Exterior/Deck Railing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
05.700 | Decorative Metal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | CARPENTRY |  |  |  |  | TOTAL | 65107 | 37.3106 | 37.3106
06.110 | Wood Framing | 0 | 520 | 3294 | 0 | 10420 | 14234 | 8.157 | 8.157
06.150 | Composite Decking | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
06.380 | Cabinetry Allowance | 29541 | 0 | 0 | 0 | 0 | 29541 | 16.9289 | 16.9289
06.442 | Exterior Brackets/Timbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
06.460 | Wood Interior Trim & Stair Parts | 0 | 0 | 5034 | 0 | 7840 | 12874 | 7.3777 | 7.3777
06.612 | Countertop Allowance | 8458 | 0 | 0 | 0 | 0 | 8458 | 4.847 | 4.847
7 | MOISTURE/THERMAL PROT. |  |  |  |  | TOTAL | 3470 | 1.9885 | 1.9885
07.130 | Waterproofing/Passive Radon/Termite Treatment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
07.210 | Insulation | 0 | 0 | 0 | 0 | 3470 | 3470 | 1.9885 | 1.9885
07.250 | Stucco/EIFS System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
07.300 | Roofing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
07.455 | Siding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
07.469 | Exterior Carsiding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
07.600 | Flashing/Brick Ledge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
07.630 | Gutters/Downspouts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
07.920 | Joint Sealants | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | DOORS & WINDOWS |  |  |  |  | TOTAL | 8169.26 | 4.6815 | 4.6815
08.140 | Interior Wood Doors | 0 | 0 | 3795.26 | 0 | 0 | 3795.26 | 2.1749 | 2.1749
08.164 | Exterior Doors (w/ windows) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
08.178 | Front Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
08.184 | Pet Door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
08.385 | Garage Doors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
08.500 | Windows | 0 | 0 | included | 0 | 0 | 0 | 0 | 0
08.600 | Roof Window/Skylights/Sun Tunnel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
08.817 | Mirrors/Glass Inserts/Shower Doors | 4374 | 0 | 0 | 0 | 0 | 4374 | 2.5066 | 2.5066
9 | FINISHES |  |  |  |  | TOTAL | 49550.98 | 28.396 | 28.396
09.200 | Drywall | 0 | 0 | 0 | 450 | 12193 | 12643 | 7.2453 | 7.2453
09.300 | Tile Allowance
| Floor Tile | 2090 | 0 | 0 | 0 | 0 | 2090 | 1.1977 | 1.1977
| Wall Tile/Columns | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tile Backsplash | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Shower/Tub Tile | 8450 | 0 | 0 | 0 | 0 | 8450 | 4.8424 | 4.8424
09.640 | LVT Flooring Allowance | 11398.98 | 0 | 0 | 0 | 0 | 11398.98 | 6.5324 | 6.5324
09.657 | Rubber Athletic Flooring Allowance | 2327 | 0 | 0 | 0 | 0 | 2327 | 1.3335 | 1.3335
09.672 | Epoxy Flooring | alternate | 0 | 0 | 0 | 0 | 0 | 0 | 0
09.680 | Carpet Allowance | included | 0 | 0 | 0 | 0 | 0 | 0 | 0
09.720 | Wall Coverings/Faux Finishing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
09.910 | Painting | 0 | 0 | 0 | 750 | 11892 | 12642 | 7.2447 | 7.2447
09.920 | Stone at M Bath
10 | SPECIALTIES |  |  |  |  | TOTAL | 3501 | 2.0063 | 2.0063
10.050 | Finish Hardware Allowance | 2026 | 525 | 0 | 0 | 0 | 2551 | 1.4619 | 1.4619
10.140 | Address Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.310 | Fireplaces (Great Room and Cap Allowance) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.311 | Fireplaces (Patio)
10.314 | Fireplace Facings Allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.552 | Mailbox | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.562 | Storage Shelving | alternate | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.566 | Wine Cellar Racks/Cooling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.572 | Closet Systems Allowance (Linen) | 950 | 0 | 0 | 0 | 0 | 950 | 0.54441 | 0.54441
10.712 | Exterior Shutters | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | EQUIPMENT |  |  |  |  | TOTAL | 4906 | 2.8115 | 2.8115
11.3 | Appliance Allowance | 4656 | 250 | 0 | 0 | 0 | 4906 | 2.8115 | 2.8115
11.52 | TV's Allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.660 | Athletic Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.678 | Game Room Equipment (Golf Simulator) | alternate | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | FURNISHINGS |  |  |  |  | TOTAL | 0 | 0 | 0
12.170 | Art Glass | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.200 | Window Treatments | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.250 | Motorized Shades (exterior only - interior by owner) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | SPECIAL CONSTRUCTION |  |  |  |  | TOTAL | 20159 | 11.5524 | 11.5524
13.112 | Swimming Pool | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.174 | Sauna Allowance | 10159 | included | 0 | 0 | 0 | 10159 | 5.8218 | 5.8218
| Special Textured Wall Allowance | 10000 | 0 | 0 | 0 | 0 | 10000 | 5.7307 | 5.7307
13.342 | Screen Porch System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | CONVEYING SYSTEMS |  |  |  |  | TOTAL | 0 | 0 | 0
14.050 | Elevator | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22-23 | PLUMBING/HVAC SYSTEMS |  |  |  |  | TOTAL | 10273 | 5.8871 | 5.8871
22.050 | Plumbing | 0 | 0 | 0 | 0 | 4000 | 4000 | 2.2923 | 2.2923
22.322 | Water Filtration System Allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22.400 | Plumbing Fixtures Allowance | 4773 | 0 | 0 | 0 | 0 | 4773 | 2.7352 | 2.7352
23.050 | HVAC | 0 | 0 | 0 | 0 | 1500 | 1500 | 0.8596 | 0.8596
23.400 | Duct Cleaning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26-28 | ELECTRICAL & LOW VOLTAGE |  |  |  |  | TOTAL | 32485 | 18.616 | 18.616
26.050 | Electrical Service & Wiring | 0 | 0 | 0 | 0 | 17390 | 17390 | 9.9656 | 9.9656
26.410 | Lightning Protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26.505 | Light Fixtures Allowance | 2595 | 0 | 0 | 0 | 0 | 2595 | 1.4871 | 1.4871
26.570 | Lighting Control System Allowance | alternate | 0 | 0 | 0 | 0 | 0 | 0 | 0
27.410 | AV Systems Pre-Wire/Sound System Allowance | 12500 | 0 | 0 | 0 | 0 | 12500 | 7.1633 | 7.1633
28.070 | Security System/Fire Protect./Video Surv. Allowance | included | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-32 | EARTHWORK & EXTERIOR IMPROVEMENTS |  |  |  |  | TOTAL | 0 | 0 | 0
31.128 | Site Demolition | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31.230 | Excavation/Fill/Grading/Silt Fence | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31.260 | Surveying | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32.130 | Exterior Concrete Flatwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32.931 | Landscaping Allowance
| Plantings & Beds | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Paver Allowance (flagstone path) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retaining Walls Allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Landscape Lighting Allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Irrigation Allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Seeding/Sod Allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Underground Buried Drainage Allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Athletic/Recreation Surfacing Allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Artificial Turf Allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fire Pit Allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Exterior Grill/Hood Allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32.310 | Fences/Gates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | UTILITIES |  |  |  |  | TOTAL | 0 | 0 | 0
33.020 | Water/Sewer Utilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | CONTINGENCY |  |  |  |  | TOTAL | 3750 | 2.149 | 2.149
50.050 | Contingency | 0 | 0 | 0 | 3750 | 0 | 3750 | 2.149 | 2.149
50.070 | Arch/Engr Fees (Separate Agreement) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 114297.98 | 10140.5 | 13673.26 | 10950 | 70430 | 252415.501 | 144.6507 | 144.6507
McNeil Company Builders
PROJECT COST SUMMARY---MARKUP ANALYSIS
Project: | CROCKETT | [5 empty] | LOWER LEVEL | 1745
Location: | 1702 S 150th Ave.; Omaha, NE 68144 | [5 empty] | MAIN LEVEL | 0
Date: | [6 empty] | UPPER LEVEL | 0
Lot: | 22 | [5 empty] | TOTAL FINISHED SF | 1745
[7 empty] | GARAGE | 0
[7 empty] | LOWER UNFINISHED | 0
[7 empty] | COVERED DECK | 0
[7 empty] | TOTAL SF UNDER ROOF | 1745
MARKUP ADJUSTMENTS
ACTUAL COST
[6 empty] | Allowances |  | 114297.98
[6 empty] | Labor |  | 10140.5
[6 empty] | Material |  | 13673.26
[6 empty] | Other |  | 10950
[6 empty] | Subcontractor |  | 70430
[6 empty] | NO MARKUP TOTAL |  | 219491.74
[6 empty] | MARKUP PERCENTAGE |  | 0.15
[6 empty] | MARKUP |  | 32923.761
[6 empty] | BID |  | 252415.501

## Totals
CROCKETT BUDGET ENTRY (both main and basement included) |  |  | MAIN | BASE | TOTAL | MAIN | BASE | TOTAL | MAIN | BASE | TOTAL | MAIN | BASE | TOTAL | MAIN | BASE | TOTAL
PHASE | DESCRIPTION |  | ALLOW. | ALLOW. | ALLOW. | LABOR | LABOR | LABOR | MATERIAL | MATERIAL | MATERIAL | OTHER | OTHER | OTHER | SUBCONT. | SUBCONT. | SUBCONT. | CODE TOTALS
1 | GENERAL REQUIREMENTS
01.120 | Superintendent |  | 0 | 0 | 0 | 89775 | 5845.5 | 95620.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95620.5
01.170 | Travel/Pickup/Deliveries |  | 0 | 0 | 0 | 2500 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500
01.205 | MUD Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4687 | 0 | 4687 | 0 | 0 | 0 | 4687
01.214 | Bldg. Permit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14170.46 | 1500 | 15670.46 | 0 | 0 | 0 | 15670.46
01.230 | Builders Risk |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4608 | 1000 | 5608 | 0 | 0 | 0 | 5608
01.235 | General Liability |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8864 | 500 | 9364 | 0 | 0 | 0 | 9364
01.452 | Testing/Inspections |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
01.454 | Mockups |  | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500
01.501 | Temporary Utilities |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7597.2 | 800 | 8397.2 | 0 | 0 | 0 | 8397.2
01.538 | Technology / prints |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 250 | 1750 | 0 | 0 | 0 | 1750
01.540 | Equipment (Forklift/Skid Loader) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | 0 | 2250 | 0 | 0 | 0 | 2250
01.560 | Temporary Barriers/Enclosures/Protection |  | 0 | 0 | 0 | 2400 | 750 | 3150 | 1100 | 300 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 4550
01.578 | Site Maintenance (Snow Removal/Mowing) |  | 0 | 0 | 0 | 1250 | 0 | 1250 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 1400
01.740 | Cleaning & Waste Management (Dumpsters) |  | 0 | 0 | 0 | 12485 | 1500 | 13985 | 0 | 1250 | 1250 | 7400 | 0 | 7400 | 6725 | 1725 | 8450 | 31085
01.810 | Warranties |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 1500 | 19500 | 0 | 0 | 0 | 19500
01.830 | Small Tools/Supply/Rentals |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | 450 | 2700 | 0 | 0 | 0 | 2700
01.840 | Punchlist |  | 0 | 0 | 0 | 3000 | 750 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3750
2 | EXISTING CONDITIONS
02.010 | Demolition |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CONCRETE
03.300 | Footings / Foundations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80749 | 0 | 80749 | 80749
03.320 | Interior Concrete Flatwork |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1700 | 0 | 1700 | 28796 | 0 | 28796 | 30496
4 | MASONRY
04.210 | Brick Masonry / Precast Sills & Caps |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
04.220 | Concrete Unit Masonry (Blockwork) |  | 0 | 0 | 0 | 0 | 0 | 0 | 1150 | 0 | 1150 | 0 | 0 | 0 | 1550 | 0 | 1550 | 2700
04.430 | Stone Masonry / Precast Sills & Caps |  | 0 | 0 | 0 | 0 | 0 | 0 | 14691 | 0 | 14691 | 0 | 0 | 0 | 98823 | 0 | 98823 | 113514
5 | METAL
05.120 | Structural Steel Material |  | 0 | 0 | 0 | 0 | 0 | 0 | 15500 | 0 | 15500 | 0 | 0 | 0 | 0 | 0 | 0 | 15500
05.528 | Metal Interior Railings |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
05.530 | Exterior Railings (stairs) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 2500 | 2500
05.700 | Decorative Metal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | CARPENTRY
06.110 | Wood Framing |  | 0 | 0 | 0 | 3640 | 520 | 4160 | 131138.24 | 3294 | 134432.24 | 1500 | 0 | 1500 | 108784 | 10420 | 119204 | 259296.24
06.150 | Composite Decking |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
06.380 | Cabinetry Allowance (Kitchen Hood) |  | 206405 | 29541 | 235946 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 8000 | 0 | 0 | 0 | 243946
06.442 | Exterior Brackets/Timbers |  | 0 | 0 | 0 | 600 | 0 | 600 | 881 | 0 | 881 | 0 | 0 | 0 | 0 | 0 | 0 | 1481
06.460 | Wood Interior Trim & Stair Parts |  | 0 | 0 | 0 | 0 | 0 | 0 | 30806.73 | 5034 | 35840.73 | 0 | 0 | 0 | 64960 | 7840 | 72800 | 108640.73
06.612 | Countertop Allowance |  | 57342 | 8458 | 65800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65800
7 | MOISTURE/THERMAL PROT.
07.130 | Waterproofing/Passive Radon/Termite Treatment |  | 0 | 0 | 0 | 375 | 0 | 375 | 150 | 0 | 150 | 0 | 0 | 0 | 9839 | 0 | 9839 | 10364
07.210 | Insulation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27390 | 3470 | 30860 | 30860
07.250 | Stucco/EIFS System (EIFS chimney) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6977 | 0 | 6977 | 23370 | 0 | 23370 | 30347
07.300 | Roofing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64231 | 0 | 64231 | 64231
07.455 | Siding |  | 0 | 0 | 0 | 0 | 0 | 0 | 5260 | 0 | 5260 | 0 | 0 | 0 | 11450 | 0 | 11450 | 16710
07.469 | Exterior Carsiding (cedar) |  | 0 | 0 | 0 | 0 | 0 | 0 | 5525 | 0 | 5525 | 0 | 0 | 0 |  | 0 | 0 | 5525
07.600 | Flashing/Brick Ledge |  | 0 | 0 | 0 | 800 | 0 | 800 | 1050 | 0 | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 1850
07.630 | Gutters/Downspouts |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 0 | 6600 | 6600
07.920 | Joint Sealants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 0 | 5500 | 5500
8 | DOORS & WINDOWS
08.140 | Interior Wood Doors |  | 0 | 0 | 0 | 0 | 0 | 0 | 24014.2547 | 3795.26 | 27809.5147 | 0 | 0 | 0 | 0 | 0 | 0 | 27809.5147
08.164 | Exterior Doors (w/ windows) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
08.178 | Front Door |  | 14559 | 0 | 14559 | 520 | 0 | 520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15079
08.184 | Pet Door |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
08.385 | Garage Doors |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7790 | 0 | 7790 | 7790
08.500 | Windows (Pella Reserve) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 100832 | 0 | 100832 | 100832
08.600 | Roof Window/Skylights/Sun Tunnel |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
08.817 | Mirrors/Glass Inserts/Shower Doors |  | 13258 | 4374 | 17632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17632
9 | FINISHES
09.200 | Drywall |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 450 | 1450 | 46793 | 12193 | 58986 | 60436
09.300 | Tile Allowance |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
| Floor Tile |  | 29710 | 2090 | 31800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31800
| Wall Tile/Columns |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tile Backsplash |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Shower/Tub Tile |  | 35271 | 8450 | 43721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43721
09.640 | Wood Flooring Allowance |  | 38124 | 11398.98 | 49522.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49522.98
09.657 | Rubber Athletic Flooring Allowance |  | 0 | 2327 | 2327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2327
09.672 | Epoxy Flooring |  | 7352 |  | 7352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7352
09.680 | Carpet Allowance |  | 19595 |  | 19595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19595
09.720 | Wall Coverings/Faux Finishing |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
09.910 | Painting (assuming prefinished cabinets) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 750 | 64894 | 11892 | 76786 | 77536
09.920 | Stone at M Bath |  | 4760 |  | 4760 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4760
10 | SPECIALTIES
10.050 | Finish Hardware Allowance |  | 15597 | 2026 | 17623 | 4000 | 525 | 4525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22148
10.140 | Address Numbers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.310 | Fireplaces (Great Room and Cap Allowance) |  | 5000 | 0 | 5000 | 1040 | 0 | 1040 | 0 | 0 | 0 | 1200 | 0 | 1200 | 9005 | 0 | 9005 | 16245
10.311 | Fireplaces (Patio) |  |  |  | 0 | 520 |  | 520 | 0 |  | 0 | 0 |  | 0 | 4992 |  | 4992 | 5512
10.314 | Fireplace Facings Allowance |  | 16627 | 0 | 16627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16627
10.552 | Mailbox |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.562 | Storage Shelving |  |  |  | 0 | 250 | 0 | 250 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 500
10.566 | Wine Cellar Racks/Cooling |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.572 | Closet Systems Allowance |  | 53873 | 950 | 54823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54823
10.712 | Exterior Shutters |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | EQUIPMENT
11.3 | Appliance Allowance (incl. grill/laundry) |  | 77770.9812 | 4656 | 82426.9812 | 1040 | 250 | 1290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83716.9812
11.52 | TV's Allowance |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.660 | Athletic Equipment |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.678 | Game Room Equipment (Golf Simulator) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | FURNISHINGS
12.170 | Art Glass |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.200 | Window Treatments |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.250 | Motorized Shades |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | SPECIAL CONSTRUCTION
13.112 | Swimming Pool (utilities) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9500 | 0 | 9500 | 119450 | 0 | 119450 | 128950
13.174 | Sauna |  |  | 10159 | 10159 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10159
| Hot Tub |  |  | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
13.342 | Screen Porch System (Sun Shade at Patio) |  | 8144 | 0 | 8144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8144
14 | CONVEYING SYSTEMS
14.050 | Elevator |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22-23 | PLUMBING/HVAC SYSTEMS
22.050 | Plumbing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57900 | 4000 | 61900 | 61900
22.322 | Water Filtration System Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6067 | 0 | 6067 | 6067
22.400 | Plumbing Fixt. Allowance (Air Dryer System) |  | 40979.2666 | 4773 | 45752.2666 | 2000 | 0 | 2000 | 3809.735 | 0 | 3809.735 | 0 | 0 | 0 | 0 | 0 | 0 | 51562.0016
23.050 | HVAC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500 | 1500 | 69000 | 69000
23.400 | Duct Cleaning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750 | 0 | 2750 | 2750
26-28 | ELECTRICAL & LOW VOLTAGE
26.050 | Electrical Service & Wiring |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72595 | 17390 | 89985 | 89985
26.410 | Lightning Protection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26.505 | Light Fixtures Allowance |  | 43496 | 2595 | 46091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46091
26.570 | Lighting Control System Allowance |  | 29500 |  | 29500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29500
27.410 | AV Systems Pre-Wire/Sound System Allowance |  | 60000 | 12500 | 72500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72500
28.070 | Security System/Fire Protect./Video Surv. Allowance |  | 6000 |  | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000
31-32 | EARTHWORK & EXTERIOR IMPROVEMENTS
31.128 | Site Demolition |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31.230 | Excavation/Fill/Grading/Silt Fence |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50440 | 0 | 50440 | 50440
31.260 | Surveying |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 2000
32.130 | Exterior Concrete Flatwork |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6750 | 0 | 6750 | 51595 | 0 | 51595 | 58345
32.931 | Sitework Allowances |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
| Landscape - Plantings & Beds |  | 70000 | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
| Paver Allowance |  | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
| Retaining Walls Allowance |  | 153250 | 0 | 153250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153250
| Landscape Lighting Allowance |  | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
| Irrigation Allowance |  | 14500 | 0 | 14500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14500
| Seeding/Sod Allowance |  | 12500 | 0 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500
| Underground Buried Drainage Allowance |  | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
| Athletic/Recreation Surfacing Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Artificial Turf Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fire Pit Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Exterior Grill/Hood Allowance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32.310 | Fences/Gates |  | 13450 | 0 | 13450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13450
33 | UTILITIES
33.020 | Water/Sewer Utilities |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | 0 | 8500 | 8500
50 | CONTINGENCY
50.050 | Contingency |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 3750 | 48750 | 0 | 0 | 0 | 48750
50.070 | Arch/Engr Fees (Separate Agreement) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1093563.2478 | 114297.98 | 1207861.2278 | 126195 | 10140.5 | 136335.5 | 235475.9597 | 13673.26 | 249149.2197 | 152953.66 | 10950 | 163903.66 | 1214370 | 70430 | 1284800 | 3042049.6075
| MARKUP | 15% | 164034.4872 | 17144.697 | 181179.1842 | 18929.25 | 1521.075 | 20450.325 | 35321.394 | 2050.989 | 37372.383 | 22943.049 | 1642.5 | 24585.549 | 182155.5 | 10564.5 | 192720 | 456307.4411
| TOTAL |  | 1257597.735 | 131442.677 | 1389040.412 | 145124.25 | 11661.575 | 156785.825 | 270797.3537 | 15724.249 | 286521.6027 | 175896.709 | 12592.5 | 188489.209 | 1396525.5 | 80994.5 | 1477520 | 3498357.0486