## 1.17.2026
Landscaping Proposal in Comparison to McNeil Allowances
Schachne Residence
2026-01-17
McNeil Site Scope | McNeil Allowance | Indigenous | variance to budget
Landscaping (plants, beds, etc.) | 40000 | 32180 | -7820
Front Yard |  | 14265
Backyard, Along House |  | 5675
Driveway Retaining wall landscape |  | 7370
East Side, Along House |  | 3370
Landscape Design Fee |  | 1500
Pavers | 23000 | 34755 | 11755
Front Stoop |  | 7780
Front Walk Medallion |  | 7315
Covered Patio (Quartziti Tiles) |  | 19660
Retaining Walls | 20000 | 40945 | 7441
Poured Foundation Window Wells Allowance | 13504
Window Wells |  | 9850
Driveway/Backyard |  | 15040
Front Walk |  | 12180
Back Patio Wall (small, off corner of house) |  | 3875
Buried Drainage | 12965 | 32330 | 19365
32330
Landscape Lighting | 12250 | 990 | -11260
990
Irrigation | 4250 | 4090 | -160
4090
Sod/Grading | 10000 | 13405 | 3405
Rough grading |  | 2575
Finish grading and sod install |  | 10830
TOTAL | 135969 | 158695 | 22726
ITEMS TO BE DETERMINED

## 10.24.2025
Landscaping Proposal in Comparison to McNeil Allowances
Schachne Residence
2025-10-24
McNeil Site Scope | McNeil Allowance | Indigenous | variance to budget
Landscaping (plants, beds, etc.) | 40000 | 36115 | -3885
Front Yard |  | 15700
Backyard, Along House |  | 5675
Driveway Retaining wall landscape |  | 9870
East Side, Along House |  | 3370
Landscape Design Fee |  | 1500
Pavers | 23000 | 34755 | 11755
Front Stoop |  | 7780
Front Walk Medallion |  | 7315
Covered Patio (Quartziti Tiles) |  | 19660
Retaining Walls | 20000 | 40945 | 7441
Poured Foundation Window Wells Allowance | 13504
Window Wells |  | 9850
Driveway/Backyard |  | 15040
Front Walk |  | 12180
Back Patio Wall (small, off corner of house) |  | 3875
Buried Drainage | 12965 | 32330 | 19365
32330
Landscape Lighting | 12250 | 5640 | -6610
5640
Irrigation | 4250 | 4090 | -160
4090
Sod/Grading | 10000 | 13405 | 3405
Rough grading |  | 2575
Finish grading and sod install |  | 10830
TOTAL | 135969 | 167280 | 31311
ITEMS TO BE DETERMINED

## 10.6.2025
Landscaping Proposal in Comparison to McNeil Allowances
Schachne Residence
2025-10-06
McNeil Site Scope | McNeil Allowance | Indigenous | variance to budget
Landscaping (plants, beds, etc.) | 40000 | 46620 | 6620
Front Yard |  | 13270
Backyard, Along House |  | 6950
Backyard, West Corner Trees |  | 5215
Driveway Retaining wall landscape |  | 8460
East Side, Along House |  | 3700
Trees Along Rear Fence Line |  | 4550
Boulders Throughout Beds & Small Backyard Wall (Glacier) |  | 2975
Landscape Design Fee |  | 1500
Pavers | 23000 | 34355 | 11355
Front Stoop |  | 7780
Front Walk Medallion |  | 7315
Covered Patio (Quartziti Tiles) |  | 19260
Retaining Walls | 20000 | 37070 | 3566
Poured Foundation Window Wells Allowance | 13504
Window Wells |  | 9850
Driveway/Backyard |  | 15040
Front Stoop |  | 12180
Buried Drainage | 12965 | 26430 | 13465
26430
Landscape Lighting | 12250 | 9410 | -2840
9410
Irrigation | 4250 | 4090 | -160
4090
Sod/Grading | 10000 | 13405 | 3405
Rough grading |  | 2575
Finish grading and sod install |  | 10830
TOTAL | 135969 | 171380 | 35411
ITEMS TO BE DETERMINED
4x4 Natural Stone Landscape Bed Edging |  | 6145 | ADD, plus fee
Boulders - Upgrade to Kodiak |  | 1405 | ADD, plus fee
Backyard - include full landscape bed per plans |  | 11695 | ADD, plus fee
Add (2) trees in rear yard |  | 2550 | ADD, plus fee
Add for landscape lighting at rear elevation and west trees bed |  | 2610 | ADD, plus fee

## 8.29.2025
Landscaping Proposal in Comparison to McNeil Allowances
Schachne Residence
2025-08-29
McNeil Site Scope | McNeil Allowance | Indigenous | variance to budget
Landscaping (plants, beds, etc.) | 40000 | 64105 | 24105
Front Yard |  | 13270
Backyard, Along House |  | 8500
Backyard, West Corner |  | 16910
Driveway Retaining wall landscape |  | 8460
East Side |  | 4030
Trees Along Rear Fence Line |  | 7100
Boulders Throughout Beds & Small Backyard Wall (Glacier) |  | 4335
Landscape Design Fee |  | 1500
Pavers | 23000 | 34355 | 11355
Front Stoop |  | 7780
Front Walk Medallion |  | 7315
Covered Patio (Quartziti Tiles) |  | 19260
Retaining Walls | 20000 | 37070 | 3566
Poured Foundation Window Wells Allowance | 13504
Window Wells |  | 9850
Driveway/Backyard |  | 15040
Front Stoop |  | 12180
Buried Drainage | 12965 | 33885 | 20920
33885
Landscape Lighting | 12250 | 12020 | -230
12020
Irrigation | 4250 | 4090 | -160
4090
Sod/Grading | 10000 | 13405 | 3405
Rough grading |  | 2575
Finish grading and sod install |  | 10830
TOTAL | 135969 | 198930 | 62961
ITEMS TO BE DETERMINED
4x4 Natural Stone Landscape Bed Edging |  | 6145 | ADD
Boulders (Kodiak) | 8760 | 4425 | ADD

## 8.8.2025
Landscaping Proposal in Comparison to McNeil Allowances
Schachne Residence
2025-08-08
McNeil Site Scope | McNeil Allowance | Indigenous | variance to budget
Landscaping (plants, beds, etc.) | 40000 | 43915 | 3915
Front Yard |  | 13985
Backyard |  | 7880
Driveway Retaining wall landscape |  | 9420
East Side |  | 4030
Trees Along Rear Fence Line |  | 7100
Landscape Design Fee |  | 1500
Pavers | 23000 | 34355 | 11355
Front Stoop |  | 7780
Front Walk Medallion |  | 7315
Covered Patio (Quartziti Tiles) |  | 19260
Retaining Walls | 20000 | 47120 | 13616
Poured Foundation Window Wells Allowance | 13504
Window Wells |  | 9850
Driveway/Backyard |  | 25090
Front Stoop |  | 12180
Buried Drainage | 12965 | 30470 | 17505
30470
Landscape Lighting | 12250 | 6145 | -6105
6145
Irrigation | 4250 | 4090 | -160
4090
Sod/Grading | 10000 | 13405 | 3405
Rough grading |  | 2575
Finish grading and sod install |  | 10830
TOTAL | 135969 | 179500 | 43531
ITEMS TO BE DETERMINED
4x4 Natural Stone Landscape Bed Edging |  | 6145 | ADD