## A
CONTRACTOR'S APPLICATION FOR PAYMENT
TO (OWNER): |  | Sydney Schachne | [5 empty] | APPLICATION NO.: | FINAL
PROJECT: |  | Schachne Residence | [5 empty] | APPLICATION DATE: | 2026-07-10
FROM (CONTRACTOR): |  | McNeil & Company Builders, L.L.C. | [5 empty] | PAYMENT DUE BY: | 2026-07-17
CONTRACT FOR: |  | Sydney Schachne
BILLING SCHEDULE
Per the Residential Building Agreement |  |  |  | ORIGINAL SCHEDULED VALUE | TOTAL PREVIOUS COST | TOTAL DUE THIS PERIOD |  | Application is made for Payment, as shown below.
1 | Upon Signed Agreement - Deposit |  |  | 150000 | 150000 |  |  | ORIGINAL CONTRACT SUM |  | 1917756
2 | Upon Completion of Pouring Foundation |  |  | 200000 | 200000 |  |  | NET CHANGE BY CHANGE ORDERS |  | 35882
3 | Upon Completion of Main Level Floor Framing |  |  | 250000 | 250000 |  |  | ALLOWANCE SUMMARY |  | 39536.28
4 | Upon Completion of Window Installation |  |  | 250000 | 250000 |  |  | See Page B for a summary of costs, which will be finalized and applied to the Final Payment.
5 | Upon Beginning of Electrical Rough-in |  |  | 300000 | 300000 |  |  | CONTRACT SUM TO DATE |  | 1993174.28
6 | Upon Beginning of Drywall |  |  | 200000 | 200000 |  |  | TOTAL BILLED TO DATE |  | 1840840.999
7 | Upon Beginning of Cabinetry Installation |  |  | 200000 | 200000
8 | Upon Beginning of Painting |  |  | 200000 | 200000 |  |  | CURRENT PAYMENT DUE |  | 112797
9 | Upon Completion of Driveway Concrete |  |  | 75000 | 75000
10 | Upon Substantial Completion of the Residence |  |  | 92756 |  | 92756 |  | BALANCE TO FINISH, INCLUDING FEE |  | 0
|  |  | TOTAL | 1917756 | 1825000 | 92756
CHANGE ORDER SUMMARY
[5 empty] | APPROVED TOTAL VALUE | PAID PREVIOUS | DUE THIS PERIOD
NUMBER | DESCRIPTION |  |  |  | VALUE | VALUE | VALUE
1 | Final Bid Meeting Changes - Add Powder Bath ($8125), Add double doors at the Den ($4714), Add a Iron-A-Way in the Master Wardrobe ($1773) |  |  |  | 14612 | 10959 | 3653
2 | HVAC - upgrade HVAC equipment to 99% efficiency ($4888), add the PureAir Purification System ($1992), and add a gas heater in the garage $(5693) |  |  |  | 12573 | 9426.75 | 3146.25
3 | Windows - upgrade the window package to Marvin Narrow Frame Series in lieu of Pella Lifestyle Series |  |  |  | 22121 | 22121
4 | Water Treatment - change to a Potassium System in lieu of a Salt System |  |  |  | in Allowance Summary
5 | Interior Doors - door style selection less than budgeted door style |  |  |  | -3082 | -3082
6 | Elevator - delete elevator and turn elevator shaft into (2) finished closet spaces (not including closet systems) |  |  |  | -44693 | -33519.751 | -11173.25
7 | TV's - TV's supplied and installed at Master Bedroom, Dining Room, and Lower Level Family Room (fee not applied) |  |  |  | 4773 |  | 4773
8 | Siding - change siding to a larger size (12") at all areas other than the front accents |  |  |  | 575 | 575
9 | Generator - complete installation of a 14kW generator |  |  |  | 18722 | 9361 | 9361
10 | Fence - Add fence at rear yard, connecting into existing surrounding fences |  |  |  | 11328 |  | 11328
11 | Leaf Gutter Guards - Add leaf guards to gutters |  |  |  | 3841 |  | 3841
12 | HVAC - credit upgrade HVAC equipment to 99% efficiency from Change Order #2 |  |  |  | -4888 |  | -4888
13
14
15
|  |  |  | TOTAL | 35882 | 15840.999 | 20041
[5 empty] | NET CHANGE BY CHANGE ORDERS | 35882

## B
CONTRACTOR'S APPLICATION FOR PAYMENT
TO (OWNER): |  | Sydney Schachne |  |  |  |  | APPLICATION NO.: | FINAL
PROJECT: |  | Schachne Residence |  |  |  |  | APPLICATION DATE: | 2026-07-10
FROM (CONTRACTOR): |  | McNeil & Company Builders, L.L.C. |  |  |  |  | PAYMENT DUE BY: | 2026-07-17
CONTRACT FOR: |  | Sydney Schachne
ALLOWANCES SUMMARY
|  |  |  | ORIGINAL BUDGET | ALLOWANCE CHANGES | ADJUSTED BUDGET | FINAL BUYOUT COST | FINAL VARIANCE | APPROXIMATE BUYOUT COST | VARIANCE
[9 empty] | VALUE | VALUE
| Appliance Allowance |  |  | 32555 |  | 32555 | 31068 | -1487 | 32555 | 0
| Plumbing Fixture & Bath Accessories Allowance |  |  | 31874 |  | 32688 | 38365.12 | 5677.12 | 36770 | 4082
|  |  | Change Guest & Bath 3 shower floors to tile, in lieu of fiberglass pans ($743 each) |  | -1486
|  |  | Add Powder Bath ($1841 PF, $459 Bath) |  | 2300
| Light Fixture Allowance |  |  | 22738 | 0 | 23238 | 6544 | -16694 | 8200 | -15038
|  |  | Add Powder Bath |  | 500
| AV Prewire / Security Allowance |  |  | 14750 |  | 14750 | 25369 | 10619 | 25369 | 10619
| Lighting Control Allowance |  |  | 0 |  | 0 | 29608 | 29608 | 29608 | 29608
| Tile Allowances (Floors, Showers, Backsplash Tile) |  |  | 59434 |  | 40937 | 53379 | 12442 | 53541 | 12604
|  |  | Change Guest & Bath 3 shower floors to tile |  | 1804
|  |  | Backsplash tile changed to countertops materials |  | -2200
|  |  | Kitchen/Dining tile allowance changed to wood floors |  | -15725
|  |  | Primary Wardrobe tile allowance changed to carpet |  | -2376
| Wood Floor Allowance |  |  | 16848 |  | 25587 | 16859 | -8728 | 17762 | -7825
|  |  | Kitchen/Dining tile allowance changed to wood floors |  | 15725
|  |  | Master Bedroom, Stair Landing, Office, Wardrobe 2, & Fitness wood floor allowance changed to carpet |  | -6986
| Countertop & Kitchen Hood Allowance |  |  | 32365 |  | 35027 | 37933 | 2906 | 34357.01 | -669.99
|  |  | Add Powder Bath |  | 462
|  |  | Backsplash tile changed to countertops materials |  | 2200
| Cabinetry Allowance |  |  | 87878 |  | 85906 | 75845.5 | -10060.5 | 76688 | -9218
|  |  | Add Powder Bath/Service Entry Changes |  | -1972
| Carpet Allowance |  |  | 8119 |  | 17481 | 19702 | 2221 | 19481 | 2000
|  |  | Primary Wardrobe tile allowance changed to carpet |  | 2376
|  |  | Master Bedroom, Stair Landing, Office, Wardrobe 2, & Fitness wood floor allowance changed to carpet |  | 6986
| Fireplace Facing Allowance |  |  | 12162 |  | 12162 | 6939.5 | -5222.5 | 7900 | -4262
| Front Entry Door Allowance |  |  | 10283 |  | 10283 | 7884 | -2399
| Finish Hardware Allowance |  |  | 15707 |  | 16500 | 16087.5 | -412.5 | 16330 | -170
|  |  | Add Powder Bath |  | 325
|  |  | Added double doors at Den |  | 468
| Closet Systems Allowance |  |  | 17945 |  | 17160 | 13754 | -3406 | 14500 | -2660
|  |  | Add Powder Bath/Service Entry Changes |  | -785
| Mirrors / Glass / Shower Door Allowance |  |  | 10923 |  | 11498 | 10646.75 | -851.25 | 11242 | -256
575
| Water Treatment Allowance |  |  | 5104 |  | 5104 | 0 | 0 | 0 | -5104
| Paver Allowance |  |  | 23000 |  | 23000 | 33720 | 10720 | 34755 | 11755
| Landscape Lighting Allowance |  |  | 12250 |  | 12250 | 990 | -11260 | 990 | -11260
| Sprinkler System / Sod Allowance |  |  | 14250 |  | 14250 | 19085 | 4835 | 17495 | 3245
| Retaining Wall Allowance |  |  | 20000 |  | 33504 | 46610 | 13106 | 40945 | 7441
|  |  | Changed window wells to retaining wall block in lieu of poured walls (budget from foundation phase) |  | 13504
| Landscaping Allowance (including any buried drainage) |  |  | 52965 |  | 52965 | 55731 | 2766 | 64510 | 11545
| Framing & Structural Steel Allowance |  |  | 85537 |  | 86422 | 86422 | no charge
|  |  | Add Powder Bath/Service Entry Changes |  | 785
|  |  | Add double Office doors |  | 100
[7 empty] | subtotal variance | 34379.37 |  | 36436.01
[7 empty] | fee per agreement | 5156.9055 |  | 5465.4015
[7 empty] | TOTAL ALLOWANCE ADJUSTMENT | 39536.2755 |  | 41901.4115

## SUB-FINAL RECONCILIATION
FINAL RECONCILIATION REPORT
[5 empty] | APPLICATION NUMBER: |  |  |  | SUB-FINAL
[5 empty] | APPLICATION DATE: |  |  |  | 2026-07-10
[5 empty] | PAYMENT DUE DATE: |  |  |  | 2026-07-17
A | B | C | D | MCNEIL | E | MCNEIL TEAM |  |  | F | H
ITEM | DESCRIPTION OF WORK | ORIGINAL | CHANGE | CHANGE | CURRENT | TOTAL | ACCRUAL | ACCRUAL | TOTAL | VARIANCE
NO |  | SCHEDULED | ORDER | ORDER | SCHEDULED | INVOICED | AMOUNT | DESCRIPTION | COMPLETED
|  | VALUE | VALUE | DESCRIPTION | VALUE | TO DATE | TO FINISH |  | TO DATE
01-000 | General Requirements
01-120 | Superintendent | 59500 | 0 |  | 59500 | 41837.45 |  |  | 41837.45 | 17662.55
01-170 | Travel/Pickup/Delivery | 1000 | 0 |  | 1000 | 8806.78 |  |  | 8806.78 | -7806.78
01-205 | MUD Fees | 3537 | 0 |  | 3537 | 5336 |  |  | 5336 | -1799
01-214 | Permits | 3047 | 0 |  | 3047 | 6206.35 |  |  | 6206.35 | -3159.35
01-216 | OPPD Fees | 200 | 0 |  | 200 | 0 |  |  | 0 | 200
01-230 | Builder's Risk | 2448 | 0 |  | 2448 | 3329 |  |  | 3329 | -881
01-235 | General Liability | 4709 | 0 |  | 4709 | 5545 |  |  | 5545 | -836
01-253 | Safety Supplies | 250 | 0 |  | 250 | 0 |  |  | 0 | 250
01-454 | Mockups | 500 | 0 |  | 500 | 1189.33 |  |  | 1189.33 | -689.33
01-501 | Temporary Utilities & Toilets | 6120 | 0 |  | 6120 | 3440.81 |  |  | 3440.81 | 2679.19
01-531 | Technology | 1250 | 0 |  | 1250 | 1250 |  |  | 1250 | 0
01-545 | Forklift/Lull | 0 | 0 |  | 0 | 0 |  |  | 0 | 0
01-547 | Skid Loader | 1500 | 0 |  | 1500 | 0 |  |  | 0 | 1500
01-560 | Temporary Barries/Enclosures | 2200 | 0 |  | 2200 | 822.16 |  |  | 822.16 | 1377.84
01-740 | Cleaning & Waste Management | 23820 | 0 |  | 23820 | 15708.22 |  |  | 15708.22 | 8111.78
01-810 | Warranties | 10200 | 0 |  | 10200 | 10200 |  |  | 10200 | 0
01-830 | Small Tools/Supplies/Rental | 2000 | 0 |  | 2000 | 1582.36 |  |  | 1582.36 | 417.64
01-840 | Punchlist | 1500 | 0 |  | 1500 | 8398.4 |  |  | 8398.4 | -6898.4
02-000 | Existing Conditions
03-000 | Concrete
03-300 | Footings/Foundations | 72000 | -13504 | ICO7 $(13504) | 58496 | 58495.34 |  |  | 58495.34 | 0.66
03-320 | Interior Concrete Flatwork | 22909 | 0 |  | 22909 | 24752.41 |  |  | 24752.41 | -1843.41
03-455 | Precast Sills/Caps | 2500 | -2500 | ICO8 $(2500) | 0 |  |  |  | 0 | 0
04-000 | Masonry
04-220 | Concrete Unit Masonry (CMU) | 600 | 0 |  | 600 | 0 |  |  | 0 | 600
04-430 | Stone Masonry | 77969 | 2500 | ICO8 $2500 | 80469 | 66051.74 |  |  | 66051.74 | 14417.26
05-000 | Metal
05-120 | Structural Steel - Material | 8721 | 0 |  | 8721 | 11267.8 |  |  | 11267.8 | -2546.8
05-528 | Interior Railing | 0 | 0 |  | 0 | 0 |  |  | 0 | 0
05-700 | Decorative Metal | 2430 | 0 |  | 2430 | 0 |  |  | 0 | 2430
06-000 | Carpentry
06-110 | Wood Framing | 138791 | 885 | CO1 $885 | 139676 | 152082.39 |  |  | 152082.39 | -12406.39
06-380 | Architectural Wood Casework | 87878 | -12032.5 | CO1 $(1972) / COA $(10060.50) | 75845.5 | 75002.73 |  |  | 75002.73 | 842.77
06-440 | Exterior Carsiding | 3000 | 0 |  | 3000 | 5576.72 |  |  | 5576.72 | -2576.72
06-460 | Wood Trim | 61585 | 721 | CO1 $721 | 62306 | 40446.47 |  |  | 40446.47 | 21859.53
06-612 | Stone/Quartz Countertops | 32365 | 5568 | CO1 $462 / ICO3 $2200 / COA $2906 | 37933 | 37932.91 |  |  | 37932.91 | 0.09
07-000 | Moisture/Thermal Protection
07-130 | Waterproofing | 9755 | 0 |  | 9755 | 9497.55 |  |  | 9497.55 | 257.45
07-210 | Insulation | 25988 | 0 |  | 25988 | 20864.8 |  |  | 20864.8 | 5123.2
07-250 | EIFS System | 10966 | 0 |  | 10966 | 12119.58 |  |  | 12119.58 | -1153.58
07-455 | Siding | 7696 | 500 | CO8 $500 | 8196 | 9008.85 |  |  | 9008.85 | -812.85
07-554 | Composite Roof | 64377 | 0 |  | 64377 | 64458 |  |  | 64458 | -81
07-600 | Flashing/Brick Ledge | 1150 | 0 |  | 1150 | 550.02 |  |  | 550.02 | 599.98
07-630 | Gutters/Downspouts | 5940 | 3340 | CO11 $3340 | 9280 | 9432.53 |  |  | 9432.53 | -152.53
07-920 | Joint Sealants | 5500 | 0 |  | 5500 | 102.46 | 5000 | accrue final JEM invoice | 5102.46 | 397.54
08-000 | Doors/Windows/Glazing
08-140 | Interior Wood Doors | 18030 | 420 | CO1 $3100 / CO5 $(2680) | 18450 | 12468.37 |  |  | 12468.37 | 5981.63
08-178 | Front Door | 10283 | -2399 | COA $(2399) | 7884 | 7884.03 |  |  | 7884.03 | -0.03
08-385 | Garage Door | 10113 | 0 |  | 10113 | 10760 |  |  | 10760 | -647
08-500 | Windows | 50086 | 19235.68 | CO2 $19235.68 | 69321.68 | 69252.65 |  |  | 69252.65 | 69.03
08-600 | Roof Tunnels/Skylights | 4360 | 0 |  | 4360 | 4348.99 |  |  | 4348.99 | 11.01
08-817 | Mirrors/Glass Inserts/Shower Doors | 10923 | -276.25 | CO1 $575 / COA $(851.25) | 10646.75 | 0 | 10646.75 | accrue for Elite invoice | 10646.75 | 0
09-000 | Finishes
09-200 | Drywall | 39500 | 1425 | CO1 $225 / CO6 $1200 | 40925 | 35457.46 |  |  | 35457.46 | 5467.54
09-360 | Floor Tile | 37719 | 15342 | ICO1 $1486 / ICO2 $19,515 / ICO4 $(15,725) / ICO5 $(2376) / COA $12442 | 53061 | 53379.21 |  |  | 53379.21 | -318.21
09-362 | Tile Backsplash | 2200 | -2200 |  | 0 | 0 |  |  | 0 | 0
09-364 | Wall Tile/Columns | 0 | 0 |  | 0 | 0 |  |  | 0 | 0
09-368 | Shower/Tub Tile | 19515 | -19515 |  | 0 | 0 |  |  | 0 | 0
09-640 | Wood Flooring | 16848 | 11 | ICO4 $15,725 / ICO6 $(6986) / COA $(8728) | 16859 | 16859.17 |  |  | 16859.17 | -0.17
09-672 | Epoxy Flooring | 0 | 0 |  | 0 | 0 |  |  | 0 | 0
09-680 | Carpeting | 8119 | 11583 | ICO5 $2376 / ICO6 $6986 / COA $2221 | 19702 | 12749.45 | 6952.96 | accrue for final IDF invoice | 19702.41 | -0.41
09-910 | Painting | 38250 | 775 | CO1 $775 | 39025 | 19128.54 | 12742.4 | accrue for final Shaver invoice | 31870.94 | 7154.06
10-000 | Specialties
10-050 | Finish Hardware Allowance | 15707 | 380.5 | CO1 $793 / COA $(412.50) | 16087.5 | 10244.74 | 5600 | accrue Greg's final invoice (7/4/2026) | 15844.74 | 242.76
10-140 | Signage (Address) | 450 | 0 |  | 450 | 357.01 |  | missing labor to install | 357.01 | 92.99
10-295 | Iron-A-Way | 0 | 1296 | CO1 $1296 | 1296 | 830.58 |  | missing labor to install | 830.58 | 465.42
10-310 | Fireplaces | 14867 | 0 |  | 14867 | 15058.39 |  |  | 15058.39 | -191.39
10-314 | Fireplace Facings | 12162 | -5222.5 | COA $(5222.50) | 6939.5 | 5979.29 |  |  | 5979.29 | 960.21
10-552 | Mailboxes | 3500 | 0 |  | 3500 | 3246.37 | 370 | accrue for Sandstone invoice 7/7/2026 | 3616.37 | -116.37
10-562 | Storage Shelving | 500 | 0 |  | 500 | 272.42 |  | missing labor to install | 272.42 | 227.58
10-572 | Closet Shelving | 17945 | -4191 | CO1 $(785) / COA $(3406) | 13754 |  | 13275 | accrue for Josh invoice | 13275 | 479
11-000 | Architectural Equipment
11-302 | Residential Appliances | 32555 | -1487 | COA $(1487) | 31068 | 31067.59 |  |  | 31067.59 | 0.41
11-520 | TV's | 0 | 4733 | CO7 $4773 | 4733 | 3454 |  |  | 3454 | 1279
12-000 | Furnishings
13-000 | Special Construction
13-342 | Screen Porch Systems | 4650 | 0 |  | 4650 | 0 | 4650 | accrue final invoice from Omarail | 4650 | 0
14-000 | Conveying Systems
14-050 | Elevator | 40063 | -40063 | CO6 $(40,063) | 0 | 0 |  |  | 0 | 0
18-000 | Miscellaneous
18-050 | Miscellaneous (Labor) | 0 | 0 |  | 0 | 0 |  |  | 0 | 0
22-000 | Plumbing
22-050 | Plumbing | 48450 | 2475 | CO1 $2475 | 50925 | 46548.5 |  |  | 46548.5 | 4376.5
22-322 | Water Filtration System | 5104 | -5104 | COA $(5104) | 0 | 0 |  |  | 0 | 0
22-400 | Plumbing Fixtures & Bath Accessories | 31874 | 6491 | CO1 $1841+$459 / ICO1 $(1486) / COA $5677 | 38365 | 38365.12 |  |  | 38365.12 | -0.12
23-000 | HVAC
23-050 | HVAC | 45975 | 7057 | CO1 $375 / CO2 $10,932 / CO12 $(4250) | 53032 | 45975 | 6682 | accrue for D&K final invoice | 52657 | 375
23-400 | Duct Cleaning | 1204 | 0 |  | 1204 | 749 |  |  | 749 | 455
26-000 | Electrical
26-050 | Electrical | 54965 | 17300 | CO1 $1020 / CO9 $16,280 | 72265 | 75095 |  |  | 75095 | -2830
26-505 | Light Fixtures Allowance | 22738 | -16194 | CO1 $500 / COA $(16694) | 6544 | 6544.2 |  |  | 6544.2 | -0.2
26-570 | Lighting Control System | 0 | 29608 | COA $29608 (includes electrical change order) | 29608 | 22233.18 |  |  | 22233.18 | 7374.82
27-000 | Communications
27-410 | AV Systems | 10000 | 15369 | ICO9 $4750 / COA $10619 | 25369 | 9868.32 | 16464 | accrue final Simplifi invoice, SEI 7208, Simplifi 2356 | 26332.32 | -963.32
28-000 | Electronic Safety & Security
28-070 | Security System Allowance/Video | 4750 | -4750 | ICO9 $(4750) | 0 | 0 | 0 |  | 0 | 0
31-000 | Earthwork
31-230 | Excavation/Grading/Silt Fence/Fill | 16500 | 0 |  | 16500 | 21378.77 |  |  | 21378.77 | -4878.77
31-260 | Surveying | 2000 | 0 |  | 2000 | 1950 |  |  | 1950 | 50
32-000 | Exterior Improvements
32-130 | Exterior Concrete | 26455 | 0 |  | 26455 | 31188.11 |  |  | 31188.11 | -4733.11
32-140 | Paver Allowance | 23000 | 10720 | COA $10720 | 33720 | 33720 |  |  | 33720 | 0
32-300 | Landscape Lighting Allowance | 12250 | -11260 | COA $(11260) | 990 | 990 |  |  | 990 | 0
32-320 | Retaining Walls Allowance | 20000 | 26610 | ICO7 $13504 / COA $13106 | 46610 | 46610 |  |  | 46610 | 0
32-310 | Fences & Gates | 0 | 9850 | CO10 $9850 | 9850 | 9275 |  |  | 9275 | 575
32-803 | Irrigation Allowance | 4250 | -4250 | ICO10 $(4250) | 0 | 0 |  |  | 0 | 0
32-924 | Sod/Fine Grading Allowance | 10000 | 9085 | ICO10 $4250 / COA $4835 | 19085 | 19085 |  |  | 19085 | 0
32-931 | Landscaping Allowance | 40000 | 15731 | ICO11 $12965 / COA$2766 | 55731 | 55730.56 |  |  | 55730.56 | 0.44
33-000 | Utilities
33-100 | Water/Sewer Utilities | 9500 | 0 |  | 9500 | 8000 |  |  | 8000 | 1500
33-460 | Underground Buried Drainage | 12965 | -12965 | ICO $(12965) | 0 | 0 |  |  | 0 | 0
50-050 | Contingency | 35000 | 0 |  | 35000 | 0 |  |  | 0 | 35000
| Contractor's Fee | 241683.9 | 9164.6895 | CO1 $1907 / CO2 $1641 / CO3 $2885.35 / CO5 $(402) / CO6 $(5830) / CO8 $75 / CO9 $2442 / CO10 $1478 / CO11 $501 | 250848.5895 | 224609.727 | 12357.4665 |  | 236967.1935
| TOTALS | 1852909.9 | 70262.6195 |  | 1923172.5195 | 1722007.907 | 94740.5765 | 0 | 1816748.4835 | 92542.64

## SUB-FINAL LABOR
Schachne Residence
Job Number | 12407
JTD Labor | FINAL
Cost Code | Description | JTD Total Labor Hours | Employee | Billable Hours | Billing Rate | Total Billable Cost | Job Cost Report Total | Billing Difference
01-000 | GENERAL REQUIREMENTS
01-117 | Project Engineer Intern | 91.91 |  | 0 | 0 | 0 | 2573.84 | -2573.84
01-120 | Superintendent | 462.52 |  | 462.52 | 85 | 39239.95 | 32166.3 | 7290.93
|  |  | Ron Milhan - 197 | 459.55 | 85 | 39061.75
|  |  | Ron Townsend - 178 | 2.97 | 60 | 178.2
|  |  | Chris Magner | 0 | 90
01-125 | Assistant Superintendent | 51.95 |  | 51.95 | 75 | 2597.5 | 2380.22
|  |  | Ron Townsend - 178 | 0 | 60 | 0
|  |  | Max Fuerstenau - 204 | 0 | 60 | 0
|  |  | Austin Stroh - 242 | 0 | 50 | 0
|  |  | Braden Dall - 239 | 0 | 50 | 0
|  |  | Caleb Fossenbarger - 235 | 0 | 50 | 0
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | Jake Tyler | 51.95 | 50 | 2597.5
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
01-130 | Project Manager | 780.99 |  | 0 | 0 | 0 | 44377.11 | -44377.11
01-140 | Estimator | 111.5 |  | 0 | 0 | 0 | 4519.69 | -4519.69
01-170 | Travel/Pickup/Deliveries | 158.9 |  | 158.9 |  | 8459.2 | 4951.66 | 3507.54
|  |  | Ron Townsend - 178 | 35.67 | 60 | 2140.2
|  |  | Max Fuerstenau - 204 | 15.75 | 60 | 945
|  |  | Austin Stroh - 242 | 27.97 | 50 | 1398.5
|  |  | Braden Dall - 239 | 55.15 | 50 | 2757.5
|  |  | Caleb Fossenbarger - 235 | 8.56 | 50 | 428
|  |  | Nathan Milhan - 233 | 8.33 | 50 | 416.5
|  |  | Jake Tyler | 7.47 | 50 | 373.5
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
01-454 | Mockups | 10.1 |  | 10.1 |  | 529.2 | 264.34 | 264.86
|  |  | Ron Townsend - 178 | 2.42 | 60 | 145.2
|  |  | Max Fuerstenau - 204 | 0 | 60 | 0
|  |  | Austin Stroh - 242 | 3.48 | 50 | 174
|  |  | Braden Dall - 239 | 2.27 | 50 | 113.5
|  |  | Caleb Fossenbarger - 235 | 0 | 50 | 0
|  |  | Nathan Milhan - 233 | 1.93 | 50 | 96.5
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
01-560 | Temp Barriers/Enclosures | 5.37 |  | 5.37 |  | 268.5 | 118.2 | 150.3
|  |  | Ron Townsend - 178 | 0 | 60 | 0
|  |  | Max Fuerstenau - 204 | 0 | 60 | 0
|  |  | Austin Stroh - 242 | 0.83 | 50 | 41.5
|  |  | Braden Dall - 239 | 2.32 | 50 | 116
|  |  | Caleb Fossenbarger - 235 | 2.22 | 50 | 111
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | TJ Ingram | 0 |  | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
01-740 | Cleaning & Waste Management | 84.16 |  | 84.16 |  | 4418.57 | 2246.48 | 2172.09
|  |  | Ron Townsend - 178 | 9.35 | 60 | 561
|  |  | Max Fuerstenau - 204 | 11.56 | 60 | 693.6
|  |  | Austin Stroh - 242 | 10.39 | 50 | 519.5
|  |  | Braden Dall - 239 | 27.49 | 50 | 1374.5
|  |  | Caleb Fossenbarger - 235 | 4.15 | 50 | 207.5
|  |  | Nathan Milhan - 233 | 19.75 | 50 | 987.5
|  |  | Nate Marrinan | 1.47 | 51 | 74.97
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
01-840 | Punchlist | 153.82 |  | 153.82 |  | 8398.4 | 5724.11 | 2674.29
|  |  | Ron Townsend - 178 | 26.57 | 60 | 1594.2
|  |  | Max Fuerstenau - 204 | 44.17 | 60 | 2650.2
|  |  | Austin Stroh - 242 | 60.74 | 50 | 3037
|  |  | Braden Dall - 239 | 22.34 | 50 | 1117
|  |  | Caleb Fossenbarger - 235 | 0 | 50 | 0
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
|  | 1911.22 |  | 874.87 |  | 63911.32 | 99321.95
03-0000 | CONCRETE
03-320 | Concrete Flatwork | 10.45 |  | 10.45 |  | 627 | 433.2 | 193.8
|  |  | Ron Townsend - 178 | 1.05 | 60 | 63
|  |  | Max Fuerstenau - 204 | 9.4 | 60 | 564
|  |  | Austin Stroh - 242 | 0 | 50 | 0
|  |  | Braden Dall - 239 | 0 | 50 | 0
|  |  | Caleb Fossenbarger - 235 | 0 | 50 | 0
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
|  | 10.45 |  | 10.45 |  | 627 | 433.2
04-0000 | MASONRY
04-430 | Stone Masonry | 4.67 |  | 4.67 |  | 250.5 | 121.29 | 129.21
|  |  | Ron Townsend - 178 | 0 | 60 | 0
|  |  | Max Fuerstenau - 204 | 1.7 | 60 | 102
|  |  | Austin Stroh - 242 | 0 | 50 | 0
|  |  | Braden Dall - 239 | 2.97 | 50 | 148.5
|  |  | Caleb Fossenbarger - 235 | 0 | 50 | 0
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
|  | 4.67 |  | 4.67 |  | 250.5 | 121.29
06-0000 | CARPENTRY
06-110 | Wood Framing | 155.06 |  | 155.06 |  | 8368.3 | 5523.98 | 2844.32
|  |  | Ron Milhan - 197 | 2.57 | 85 | 218.45
|  |  | Ron Townsend - 178 | 25.47 | 60 | 1528.2
|  |  | Max Fuerstenau - 204 | 48.91 | 60 | 2934.6
|  |  | Austin Stroh - 242 | 21.95 | 50 | 1097.5
|  |  | Braden Dall - 239 | 20.26 | 50 | 1013
|  |  | Caleb Fossenbarger - 235 | 26.7 | 50 | 1335
|  |  | Nathan Milhan - 233 | 6.55 | 50 | 327.5
|  |  | Jake Tyler | 2.65 | 50 | 132.5
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
06-380 | Cabinetry | 9.85 |  | 9.85 |  | 492.5 | 202.92 | 289.58
|  |  | Ron Townsend - 178 | 0 | 60 | 0
|  |  | Max Fuerstenau - 204 | 0 | 60 | 0
|  |  | Austin Stroh - 242 | 0 | 50 | 0
|  |  | Braden Dall - 239 | 4.82 | 50 | 241
|  |  | Caleb Fossenbarger - 235 | 5.03 | 50 | 251.5
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
06-460 | Wood Trim | 3.42 |  | 3.42 |  | 205.2 | 172.08 | 33.12
|  |  | Ron Townsend - 178 | 3.42 | 60 | 205.2
|  |  | Max Fuerstenau - 204 | 0 | 60 | 0
|  |  | Austin Stroh - 242 | 0 | 50 | 0
|  |  | Braden Dall - 239 | 0 | 50 | 0
|  |  | Caleb Fossenbarger - 235 | 0 | 50 | 0
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
|  | 168.33 |  | 168.33 |  | 9066 | 5898.98
07-0000 | MOISTURE/THERM PROTECTION
07-210 | Insulation | 3.33 |  | 3.33 |  | 199.8 | 138.67 | 61.13
|  |  | Ron Townsend - 178 | 0 | 60 | 0
|  |  | Max Fuerstenau - 204 | 3.33 | 60 | 199.8
|  |  | Austin Stroh - 242 | 0 | 50 | 0
|  |  | Braden Dall - 239 | 0 | 50 | 0
|  |  | Caleb Fossenbarger - 235 | 0 | 50 | 0
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
07-554 | Composite Roofing | 1.62 |  | 1.62 |  | 81 | 27.54 | 53.46
|  |  | Ron Townsend - 178 | 0 | 60 | 0
|  |  | Max Fuerstenau - 204 | 0 | 60 | 0
|  |  | Austin Stroh - 242 | 0 | 50 | 0
|  |  | Braden Dall - 239 | 1.62 | 50 | 81
|  |  | Caleb Fossenbarger - 235 | 0 | 50 | 0
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
07-600 | Flashing | 0.9 |  | 0.9 |  | 45 | 15.3 | 29.7
|  |  | Ron Townsend - 178 | 0 | 60 | 0
|  |  | Max Fuerstenau - 204 | 0 | 60 | 0
|  |  | Austin Stroh - 242 | 0 | 50 | 0
|  |  | Braden Dall - 239 | 0.9 | 50 | 45
|  |  | Caleb Fossenbarger - 235 | 0 | 50 | 0
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
|  | 5.85 |  | 5.85 |  | 325.8 | 181.51
08-0000 | OPENINGS
08-178 | Front Door | 14.94 |  | 14.94 |  | 881.4 | 626.96 | 254.44
|  |  | Ron Townsend - 178 | 3.67 | 60 | 220.2
|  |  | Max Fuerstenau - 204 | 9.77 | 60 | 586.2
|  |  | Austin Stroh - 242 | 0 | 50 | 0
|  |  | Braden Dall - 239 | 0 | 50 | 0
|  |  | Caleb Fossenbarger - 235 | 1.5 | 50 | 75
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
08-600 | Sun Tunnels | 28.58 |  | 28.58 |  | 1591.3 | 1017.75 | 573.55
|  |  | Ron Townsend - 178 | 2.78 | 60 | 166.8
|  |  | Max Fuerstenau - 204 | 13.45 | 60 | 807
|  |  | Austin Stroh - 242 | 0 | 50 | 0
|  |  | Braden Dall - 239 | 7.45 | 50 | 372.5
|  |  | Caleb Fossenbarger - 235 | 2 | 50 | 100
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | Jake Tyler | 2.9 | 50 | 145
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
|  | 43.52 |  | 43.52 |  | 2472.7 | 1644.71
09-0000 | FINISHES
09-200 | Drywall | 2.92 |  | 2.92 |  | 160.2 | 93.97 | 66.23
|  |  | Ron Townsend - 178 | 1.42 | 60 | 85.2
|  |  | Max Fuerstenau - 204 | 0 | 60 | 0
|  |  | Austin Stroh - 242 | 0 | 50 | 0
|  |  | Braden Dall - 239 | 1.5 | 50 | 75
|  |  | Caleb Fossenbarger - 235 | 0 | 50 | 0
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
09-360 | Floor Tile | 3.3 |  | 3.3 |  | 165 | 95.89 | 69.11
|  |  | Ron Townsend - 178 | 0 | 60 | 0
|  |  | Max Fuerstenau - 204 | 0 | 60 | 0
|  |  | Austin Stroh - 242 | 3.3 | 50 | 165
|  |  | Braden Dall - 239 | 0 | 50 | 0
|  |  | Caleb Fossenbarger - 235 | 0 | 50 | 0
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
09-368 | Shower/Tub Tile | 3 |  | 3 |  | 180 | 150.4 | 29.6
|  |  | Ron Townsend - 178 | 3 | 60 | 180
|  |  | Max Fuerstenau - 204 | 0 | 60 | 0
|  |  | Austin Stroh - 242 | 0 | 50 | 0
|  |  | Braden Dall - 239 | 0 | 50 | 0
|  |  | Caleb Fossenbarger - 235 | 0 | 50 | 0
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
09-640 | Wood Flooring | 37.47 |  | 37.47 |  | 2018.5 | 1108.79 | 909.71
|  |  | Ron Townsend - 178 | 6.07 | 60 | 364.2
|  |  | Max Fuerstenau - 204 | 8.43 | 60 | 505.8
|  |  | Austin Stroh - 242 | 6.92 | 50 | 346
|  |  | Braden Dall - 239 | 10.3 | 50 | 515
|  |  | Caleb Fossenbarger - 235 | 5.75 | 50 | 287.5
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
|  | 46.69 |  | 46.69 |  | 2523.7 | 1449.05
10-0000 | SPECIALTIES
10-552 | Mailbox | 11.12 |  | 11.12 |  | 577.8 | 345.98 | 231.82
|  |  | Ron Townsend - 178 | 1 | 60 | 60
|  |  | Max Fuerstenau - 204 | 1.18 | 60 | 70.8
|  |  | Austin Stroh - 242 | 3.57 | 50 | 178.5
|  |  | Braden Dall - 239 | 2.82 | 50 | 141
|  |  | Caleb Fossenbarger - 235 | 2.55 | 50 | 127.5
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
|  | 11.12 |  | 11.12 |  | 577.8 | 345.98
11-0000 | EQUIPMENT
11-302 | Appliances | 1.4 |  | 1.4 |  | 70 | 48.59 | 21.41
|  |  | Ron Townsend - 178 | 0 | 60 | 0
|  |  | Max Fuerstenau - 204 | 0 | 60 | 0
|  |  | Austin Stroh - 242 | 1.4 | 50 | 70
|  |  | Braden Dall - 239 | 0 | 50 | 0
|  |  | Caleb Fossenbarger - 235 | 0 | 50 | 0
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
|  | 1.4 |  | 1.4 |  | 70 | 48.59
17-0000 | DESIGN
17-500 | Construction Admin Nonbillable | 4.75 |  | 0 |  | 0 | 262.38 | -262.38
|  |  | Ron Townsend - 178 | 0 | 60 | 0
|  |  | Max Fuerstenau - 204 | 0 | 60 | 0
|  |  | Austin Stroh - 242 | 0 | 50 | 0
|  |  | Braden Dall - 239 | 0 | 50 | 0
|  |  | Caleb Fossenbarger - 235 | 0 | 50 | 0
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
|  |  |  | 0 |  | 0 | 262.38
17-600 | Construction Admin Billable | 1 |  | 0 |  | 0 | 95.84 | -95.84
|  |  | Ron Townsend - 178 | 0 | 60 | 0
|  |  | Max Fuerstenau - 204 | 0 | 60 | 0
|  |  | Austin Stroh - 242 | 0 | 50 | 0
|  |  | Braden Dall - 239 | 0 | 50 | 0
|  |  | Caleb Fossenbarger - 235 | 0 | 50 | 0
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
|  | 5.75 |  | 0 |  | 0 | 95.84
22-0000 | PLUMBING
22-050 | Plumbing | 0.97 |  | 0.97 |  | 48.5 | 16.49 | 32.01
|  |  | Ron Townsend - 178 | 0 | 60 | 0
|  |  | Max Fuerstenau - 204 | 0 | 60 | 0
|  |  | Austin Stroh - 242 | 0 | 50 | 0
|  |  | Braden Dall - 239 | 0.97 | 50 | 48.5
|  |  | Caleb Fossenbarger - 235 | 0 | 50 | 0
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
|  | 0.97 |  | 0.97 |  | 48.5 | 16.49
31-0000 | EARTHWORK
31-230 | Dirt Work | 53.47 |  | 53.47 |  | 3133.82 | 2387.75 | 746.07
|  |  | Ron Townsend - 178 | 42.78 | 60 | 2566.8
|  |  | Max Fuerstenau - 204 | 3.02 | 60 | 181.2
|  |  | Austin Stroh - 242 | 0 | 50 | 0
|  |  | Braden Dall - 239 | 0.83 | 50 | 41.5
|  |  | Caleb Fossenbarger - 235 | 4.52 | 50 | 226
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | Nate Marrinan | 2.32 | 51 | 118.32
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
|  | 53.47 |  | 53.47 |  | 3133.82 | 2387.75
32-0000 | EXTERIOR IMPROVEMENTS
32-130 | Exterior Concrete | 13.48 |  | 13.48 |  | 726.5 | 393.73 | 332.77
|  |  | Ron Townsend - 178 | 0 | 60 | 0
|  |  | Max Fuerstenau - 204 | 5.25 | 60 | 315
|  |  | Austin Stroh - 242 | 0 | 50 | 0
|  |  | Braden Dall - 239 | 5.93 | 50 | 296.5
|  |  | Caleb Fossenbarger - 235 | 2.3 | 50 | 115
|  |  | Nathan Milhan - 233 | 0 | 50 | 0
|  |  | TJ Ingram | 0 | 75 | 0
|  |  | Jo Nutter - 188 | 0 | 60 | 0
|  | 13.48 |  | 13.48 |  | 726.5 | 393.73
2276.92