## A
CONTRACTOR'S APPLICATION FOR PAYMENT
TO (OWNER): |  | Sydney Schachne | [5 empty] | APPLICATION NO.: | 2
PROJECT: |  | Schachne Residence | [5 empty] | APPLICATION DATE: | 2025-07-28
FROM (CONTRACTOR): |  | McNeil & Company Builders, L.L.C. | [5 empty] | PAYMENT DUE BY: | 2025-08-08
CONTRACT FOR: |  | Sydney Schachne
BILLING SCHEDULE
Per the Residential Building Agreement |  |  |  | ORIGINAL SCHEDULED VALUE | TOTAL PREVIOUS COST | TOTAL DUE THIS PERIOD |  | Application is made for Payment, as shown below.
1 | Upon Signed Agreement - Deposit |  |  | 150000 | 150000 |  |  | ORIGINAL CONTRACT SUM |  | 1917756
2 | Upon Completion of Pouring Foundation |  |  | 200000 | 200000 |  |  | NET CHANGE BY CHANGE ORDERS |  | 1531
3 | Upon Completion of Main Level Floor Framing |  |  | 250000 |  | 250000 |  | ALLOWANCE SUMMARY |  | 0
4 | Upon Completion of Window Installation |  |  | 250000 |  |  |  | See Page B for a summary of costs, which will be finalized and applied to the Final Payment.
5 | Upon Beginning of Electrical Rough-in |  |  | 300000 |  |  |  | CONTRACT SUM TO DATE |  | 1919287
6 | Upon Beginning of Drywall |  |  | 200000 |  |  |  | TOTAL PAID TO DATE |  | 353653
7 | Upon Beginning of Cabinetry Installation |  |  | 200000
8 | Upon Beginning of Painting |  |  | 200000 |  |  |  | CURRENT PAYMENT DUE |  | 250000
9 | Upon Completion of Driveway Concrete |  |  | 75000
10 | Upon Substantial Completion of the Residence |  |  | 92756 |  |  |  | BALANCE TO FINISH, INCLUDING FEE |  | 1315634
|  |  | TOTAL | 1917756 | 350000 | 250000
CHANGE ORDER SUMMARY
[5 empty] | APPROVED TOTAL VALUE | PAID PREVIOUS | DUE THIS PERIOD
NUMBER | DESCRIPTION |  |  |  | VALUE | VALUE | VALUE
1 | Final Bid Meeting Changes - Add Powder Bath ($8125), Add double doors at the Den ($4714), Add a Iron-A-Way in the Master Wardrobe ($1773) |  |  |  | 14612 | 3653
2 | HVAC - upgrade HVAC equipment to 99% efficiency ($4888), add the PureAir Purification System ($1992), and add a gas heater in the garage $(5693) |  |  |  | 12573
3 | Windows - upgrade the window package to Marvin Narrow Frame Series in lieu of Pella Lifestyle Series |  |  |  | 22121
4 | Water Treatment - change to a Potassium System in lieu of a Salt System |  |  |  | pending
5 | Interior Doors - door style selection less than budgeted door style |  |  |  | -3082
6 | Elevator - delete elevator and turn elevator shaft into (2) finished closet spaces (not including closet systems) |  |  |  | -44693
7
8
9
10
11
12
13
14
15
|  |  |  | TOTAL | 1531 | 3653 | 0
[5 empty] | NET CHANGE BY CHANGE ORDERS | 1531

## B
CONTRACTOR'S APPLICATION FOR PAYMENT
TO (OWNER): |  | Sydney Schachne | [5 empty] | APPLICATION NO.: | 2
PROJECT: |  | Schachne Residence | [5 empty] | APPLICATION DATE: | 2025-07-28
FROM (CONTRACTOR): |  | McNeil & Company Builders, L.L.C. | [5 empty] | PAYMENT DUE BY: | 2025-08-08
CONTRACT FOR: |  | Sydney Schachne
ALLOWANCES SUMMARY
|  |  |  | ORIGINAL BUDGET | ALLOWANCE CHANGES | ADJUSTED BUDGET | APPROXIMATE BUYOUT COST | VARIANCE
[7 empty] | VALUE | VALUE
| Appliance Allowance |  |  | 32555 |  |  | 32555 | 0
| Plumbing Fixture & Bath Accessories Allowance |  |  | 31874 |  | 32688 | 32947.02 | 259.02
|  |  | Change Guest & Bath 3 shower floors to tile, in lieu of fiberglass pans |  | -1486
|  |  | Add Powder Bath ($1841 PF, $459 Bath) |  | 2300
| Light Fixture Allowance |  |  | 22738 |  | 23238
|  |  | Add Powder Bath |  | 500
| AV Prewire / Security Allowance |  |  | 14750 |  |  | pending
| Tile Allowances (Floors, Showers, Backsplash Tile) |  |  | 59434 |  | 61238
|  |  | Change Guest & Bath 3 shower floors to tile |  | 1804
| Wood Floor Allowance |  |  | 16848 |  |  | 24166 | 7318
| Countertop & Kitchen Hood Allowance |  |  | 32365 |  | 32827 | 32076 | -751
|  |  | Add Powder Bath |  | 462
| Cabinetry Allowance |  |  | 87878 |  | 85906 | pending
|  |  | Add Powder Bath/Service Entry Changes |  | -1972
| Fireplace Facing Allowance |  |  | 12162
| Front Entry Door Allowance |  |  | 10283
| Finish Hardware Allowance |  |  | 15707 |  | 16032
|  |  | Add Powder Bath |  | 325
| Closet Systems Allowance |  |  | 17945 |  | 17160
|  |  | Add Powder Bath/Service Entry Changes |  | -785
| Mirrors / Glass / Shower Door Allowance |  |  | 10923 |  | 11498
|  |  | Add Powder Bath |  | 575
| Carpet Allowance |  |  | 8119
| Water Treatment Allowance |  |  | 5104
| Paver Allowance |  |  | 23000
| Landscape Lighting Allowance |  |  | 12250
| Sprinkler System / Sod Allowance |  |  | 14250
| Retaining Wall Allowance |  |  | 20000
| Landscaping Allowance (including any buried drainage) |  |  | 52965
| Framing & Structural Steel Allowance |  |  | 85537 |  | 86422
|  |  | Add Powder Bath/Service Entry Changes |  | 785
|  |  | Add double Office doors |  | 100
[7 empty] | subtotal variance | 6826.02
[7 empty] | fee per agreement | 1023.903
[7 empty] | TOTAL ALLOWANCE ADJUSTMENT | 7849.923