## PROJECT SUMMARY
PROJECT COST SUMMARY
PROJECT | Ostronic Residence | [6 empty] | LOWER LEVEL | 1462
PROJECT MANAGER | [7 empty] | MAIN LEVEL | 2435
LOCATION | 1672 S 150th Avenue, Omaha, NE 68144 | [6 empty] | UPPER LEVEL | 1479
DATE | May 2026 | [6 empty] | TOTAL FINISHED SF | 5376
LOT # | Heartwood Lot 8 | [6 empty] | GARAGE | 1028
ZONING | [7 empty] | LOWER UNFINISHED | 438
[8 empty] | COVERED DECK | 245
[8 empty] | COVERED FRONT PORCH | 315
[8 empty] | PARTIAL COVERED DECK | 95
[8 empty] | TOTAL SF UNDER ROOF | 7497
PHASE | DESCRIPTION | ALLOW. | LABOR | MATERIAL | OTHER | SUBCONT. | DIVISION | FINISHED COST/SF | UNDER ROOF
1 | GENERAL REQUIREMENTS |  |  |  |  | TOTAL | 143788.375 | 26.7463 | 19.1795
01.120 | Superintendent | 0 | 61648.375 | 0 | 0 | 0 | 61648.375 | 11.4673 | 8.2231
01.170 | Travel/Pickup/Deliveries | 0 | 1750 | 0 | 0 | 0 | 1750 | 0.32552 | 0.23343
01.205 | MUD Fees | 0 | 0 | 0 | 2150 | 0 | 2150 | 0.39993 | 0.28678
01.214 | Bldg. Permit | 0 | 0 | 0 | 12550 | 0 | 12550 | 2.3344 | 1.674
01.230 | Builders Risk | 0 | 0 | 0 | 3250 | 0 | 3250 | 0.60454 | 0.43351
01.235 | General Liability | 0 | 0 | 0 | 6125 | 0 | 6125 | 1.1393 | 0.81699
01.454 | Mockups | 0 | 550 | 250 | 0 | 0 | 800 | 0.14881 | 0.10671
01.501 | Temporary Utilities | 0 | 0 | 0 | 6500 | 0 | 6500 | 1.2091 | 0.86701
01.538 | Technology | 0 | 0 | 0 | 1750 | 0 | 1750 | 0.32552 | 0.23343
01.540 | Equipment (Forklift/Skid Loader) | 0 | 0 | 0 | 1500 | 0 | 1500 | 0.27902 | 0.20008
01.560 | Temporary Barriers/Enclosures/Protection | 0 | 2250 | 1100 | 0 | 0 | 3350 | 0.62314 | 0.44685
01.578 | Site Maintenance (Snow Removal/Mowing) | 0 | 1500 | 0 | 0 | 0 | 1500 | 0.27902 | 0.20008
01.740 | Cleaning & Waste Management (Dumpsters) | 0 | 10175 | 0 | 8040 | 5750 | 23965 | 4.4578 | 3.1966
01.810 | Warranties | 0 | 0 | 0 | 11700 | 0 | 11700 | 2.1763 | 1.5606
01.830 | Small Tools/Supply/Rentals | 0 | 0 | 2000 | 0 | 0 | 2000 | 0.37202 | 0.26677
01.840 | Punchlist | 0 | 3250 | 0 | 0 | 0 | 3250 | 0.60454 | 0.43351
3 | CONCRETE |  |  |  |  | TOTAL | 94757 | 17.6259 | 12.6393
03.300 | Footings / Foundations | 0 | 0 | 0 | 0 | 67765 | 67765 | 12.6051 | 9.0389
03.320 | Interior Concrete Flatwork | 0 | 0 | 0 | 0 | 26992 | 26992 | 5.0208 | 3.6004
4 | MASONRY |  |  |  |  | TOTAL | 65453 | 12.175 | 8.7306
04.220 | Concrete Unit Masonry (Blockwork) | 0 | 0 | 500 | 0 | 1500 | 2000 | 0.37202 | 0.26677
04.430 | Stone Masonry / Precast Sills & Caps | 0 | 0 | 28300 | 7683 | 27470 | 63453 | 11.803 | 8.4638
5 | METAL |  |  |  |  | TOTAL | 16284 | 3.029 | 2.1721
05.120 | Structural Steel Material | 0 | 0 | 9084 | 0 | 0 | 9084 | 1.6897 | 1.2117
05.530 | Deck Railing (excludes Retaining Wall Steps Railings) | 0 | 0 | 0 | 0 | 7200 | 7200 | 1.3393 | 0.96038
05.700 | Decorative Metal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | CARPENTRY |  |  |  |  | TOTAL | 509946 | 94.856 | 68.02
06.110 | Wood Framing | 0 | 4000 | 122885 | 0 | 122500 | 249385 | 46.3886 | 33.2646
06.150 | Composite Decking (Timbertech Terrain) | 0 | 0 | 13892 | 0 | 7185 | 21077 | 3.9206 | 2.8114
06.380 | Cabinetry Allowance (Signature360 & Classic360) | 127500 | 0 | 0 | 0 | 0 | 127500 | 23.7165 | 17.0068
06.442 | Exterior Brackets/Timbers | 0 | 480 | 1900 | 0 | 0 | 2380 | 0.44271 | 0.31746
06.460 | Wood Interior Trim & Stair Parts | 0 | 0 | 32000 | 0 | 41600 | 73600 | 13.6905 | 9.8173
06.612 | Countertop Allowance | 36004 | 0 | 0 | 0 | 0 | 36004 | 6.6972 | 4.8025
7 | MOISTURE/THERMAL PROT. |  |  |  |  | TOTAL | 129682 | 24.1224 | 17.2979
07.130 | Waterproofing/Passive Radon/Termite Treatment | 0 | 0 | 0 | 850 | 7667 | 8517 | 1.5843 | 1.1361
07.210 | Insulation | 0 | 0 | 0 | 0 | 23545 | 23545 | 4.3797 | 3.1406
07.300 | Roofing (Asphalt) & Metal Chimney Cap | 0 | 0 | 0 | 0 | 48750 | 48750 | 9.0681 | 6.5026
07.455 | Siding | 0 | 0 | 16260 | 0 | 13550 | 29810 | 5.545 | 3.9763
07.469 | Exterior Carsiding | 0 | 0 | 3510 | 0 | 3600 | 7110 | 1.3225 | 0.94838
07.600 | Flashing/Brick Ledge | 0 | 600 | 1100 | 0 | 0 | 1700 | 0.31622 | 0.22676
07.630 | Gutters/Downspouts | 0 | 0 | 0 | 0 | 6250 | 6250 | 1.1626 | 0.83367
07.920 | Joint Sealants | 0 | 0 | 0 | 0 | 4000 | 4000 | 0.74405 | 0.53355
8 | DOORS & WINDOWS |  |  |  |  | TOTAL | 134806 | 25.0755 | 17.9813
08.140 | Interior Wood Doors | 0 | 0 | 18636 | 0 | 0 | 18636 | 3.4665 | 2.4858
| Pantry Door | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Hidden Office Door Allowance | 4000 | 0 | 0 | 0 | 0 | 4000 | 0.74405 | 0.53355
08.178 | Front Door (Iron) | 9370 | 1440 | 0 | 0 | 0 | 10810 | 2.0108 | 1.4419
08.385 | Garage Doors (Gallery Ultra-Grain) | 0 | 0 | 0 | 0 | 8410 | 8410 | 1.5644 | 1.1218
08.500 | Windows (Lifestyle) | 0 | 0 | 0 | 0 | 82750 | 82750 | 15.3925 | 11.0377
08.817 | Mirrors/Shower Doors | 10200 | 0 | 0 | 0 | 0 | 10200 | 1.8973 | 1.3605
9 | FINISHES |  |  |  |  | TOTAL | 212652 | 39.5558 | 28.3649
09.200 | Drywall (level 4 walls) | 0 |  | 0 | 1300 | 41175 | 42475 | 7.9009 | 5.6656
09.300 | Tile Allowance
| Floor Tile | 25890 | 0 | 0 | 0 | 0 | 25890 | 4.8158 | 3.4534
| Tile Backsplash (includes stone at LL Bar) | 6581 | 0 | 0 | 0 | 0 | 6581 | 1.2241 | 0.87782
| Shower/Tub Tile | 16774 | 0 | 0 | 0 | 0 | 16774 | 3.1202 | 2.2374
09.640 | Wood/LVP/LVT Flooring Allowance | 53532 | 0 | 0 | 0 | 0 | 53532 | 9.9576 | 7.1405
09.657 | Rubber Athletic Flooring Allowance (Kinetex) | 1900 | 0 | 0 | 0 | 0 | 1900 | 0.35342 | 0.25343
09.672 | Epoxy Flooring (Garage) | OPTION | 0 | 0 | 0 | 0 | 0 | 0 | 0
09.680 | Carpet Allowance (stairs) | 2500 | 0 | 0 | 0 | 0 | 2500 | 0.46503 | 0.33347
09.720 | Wall Coverings/Faux Finishing | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
09.910 | Painting | 0 | 0 | 0 | 0 | 63000 | 63000 | 11.7188 | 8.4034
10 | SPECIALTIES |  |  |  |  | TOTAL | 51571 | 9.5928 | 6.8789
10.050 | Finish Hardware Allowance | 8575 | 5000 | 0 | 0 | 0 | 13575 | 2.5251 | 1.8107
10.140 | Address Numbers | 0 | 150 | 250 | 0 | 0 | 400 | 0.074405 | 0.053355
10.310 | Fireplaces (arched unit) | 0 | 0 | 0 | 0 | 9096 | 9096 | 1.692 | 1.2133
10.314 | Fireplace Facings Allowance | 8500 | 0 | 0 | 0 | 0 | 8500 | 1.5811 | 1.1338
10.552 | Mailbox - community box | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.562 | Storage Shelving | OPTION | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.572 | Closet Systems Allowance | 20000 | 0 | 0 | 0 | 0 | 20000 | 3.7202 | 2.6677
11 | EQUIPMENT |  |  |  |  | TOTAL | 38550 | 7.1708 | 5.1421
11.3 | Appliance Allowance (Frigidaire option) | 37830 | 720 | 0 | 0 | 0 | 38550 | 7.1708 | 5.1421
11.52 | TV's Allowance | OPTION | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.678 | Golf Simulator | OPTION | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | FURNISHINGS |  |  |  |  | TOTAL | 0 | 0 | 0
12.170 | Art Glass | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.200 | Window Treatments | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.250 | Motorized Shades | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | SPECIAL CONSTRUCTION |  |  |  |  | TOTAL | 0 | 0 | 0
13.342 | Screen Porch System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22-23 | PLUMBING/HVAC SYSTEMS |  |  |  |  | TOTAL | 176340 | 32.8013 | 23.5214
22.050 | Plumbing | 0 | 0 | 0 | 0 | 60900 | 60900 | 11.3281 | 8.1232
22.322 | Water Filtration System Allowance | 5000 | 0 | 0 | 0 | 0 | 5000 | 0.93006 | 0.66693
22.400 | Plumbing Fixtures Allowance | 33615 | 0 | 0 | 0 | 0 | 33615 | 6.2528 | 4.4838
23.050 | HVAC | 0 | 0 | 0 | 0 | 74325 | 74325 | 13.8253 | 9.914
23.400 | Duct Cleaning | 0 | 0 | 0 | 0 | 2500 | 2500 | 0.46503 | 0.33347
26-28 | ELECTRICAL & LOW VOLTAGE |  |  |  |  | TOTAL | 107500 | 19.9963 | 14.3391
26.050 | Electrical Service & Wiring | 0 | 0 | 0 | 0 | 57500 | 57500 | 10.6957 | 7.6697
26.505 | Light Fixtures Allowance | 20000 | 0 | 0 | 0 | 0 | 20000 | 3.7202 | 2.6677
26.570 | Lighting Control System Allowance | OPTION | 0 | 0 | 0 | 0 | 0 | 0 | 0
27.410 | AV Systems Pre-Wire/Sound System Allowance | 20000 | 0 | 0 | 0 | 0 | 20000 | 3.7202 | 2.6677
28.070 | Security System/Fire Protect./Video Surv. Allowance | 10000 | 0 | 0 | 0 | 0 | 10000 | 1.8601 | 1.3339
31-32 | EARTHWORK & EXTERIOR IMPROVEMENTS |  |  |  |  | TOTAL | 66904 | 12.4449 | 8.9241
31.230 | Excavation/Fill/Grading/Silt Fence | 0 | 0 | 0 | 5000 | 25500 | 30500 | 5.6734 | 4.0683
31.260 | Surveying | 0 | 0 | 0 | 0 | 2500 | 2500 | 0.46503 | 0.33347
32.130 | Exterior Concrete Flatwork | 0 | 0 | 0 | 0 | 33904 | 33904 | 6.3065 | 4.5223
32.142 | Paver Allowance | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
32.300 | Landscape Lighting Allowance | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
32.310 | Fences/Gates | OPTION | 0 | 0 | 0 | 0 | 0 | 0 | 0
32.320 | Retaining Walls Allowance | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
32.800 | Irrigation Allowance | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
32.922 | Seeding/Sod Allowance | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
32.931 | Landscaping Allowance | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | UTILITIES |  |  |  |  | TOTAL | 10000 | 1.8601 | 1.3339
33.020 | Water/Sewer Utilities | 0 | 0 | 0 | 0 | 10000 | 10000 | 1.8601 | 1.3339
33.462 | Underground Buried Drainage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | CONTIGENCY |  |  |  |  | TOTAL | 50000 | 9.3006 | 6.6693
50.050 | Contigency & other | 50000 | 0 | 0 | 0 | 0 | 50000 | 9.3006 | 6.6693
50.070 | Arch/Engr Fees (Separate Agreement) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 507771 | 93513.375 | 251667 | 68398 | 886884 | 2079468.3813 | 386.8059 | 277.3734
McNeil Company Builders
PROJECT COST SUMMARY---MARKUP ANALYSIS
Project: | Ostronic Residence | [5 empty] | LOWER LEVEL | 1462
Location: | 1672 S 150th Avenue, Omaha, NE 68144 | [5 empty] | MAIN LEVEL | 2435
Date: | May 2026 | [5 empty] | UPPER LEVEL | 1479
Lot: | Heartwood Lot 8 | [5 empty] | TOTAL FINISHED SF | 5376
[7 empty] | GARAGE | 1028
[7 empty] | LOWER UNFINISHED | 438
[7 empty] | COVERED DECK | 245
[7 empty] | TOTAL SF UNDER ROOF | 7497
MARKUP ADJUSTMENTS
ACTUAL COST
[6 empty] | Allowances |  | 507771
[6 empty] | Labor |  | 93513.375
[6 empty] | Material |  | 251667
[6 empty] | Other |  | 68398
[6 empty] | Subcontractor |  | 886884
[6 empty] | NO MARKUP TOTAL |  | 1808233.375
[6 empty] | MARKUP PERCENTAGE |  | 15%
[6 empty] | MARKUP |  | 271235.0062
[6 empty] | BID |  | 2079468.3813

## DIV 1 GC
01.000 | GENERAL CONDITIONS
1.12 | Superintendent
|  |  | PROJECT DURATION - MONTHS | APPROX. HOURS/DAY | HOURS/WEEK | RATE/HOUR | COST/WEEK | PROJECT DURATION - WEEKS | TOTAL
|  | minimal supervision at start 3 wks | 16.75 | 2 | 10 | 85 | 850 | 72.5275 | 61648.375
1.17 | Travel/Pickup/Deliveries
| Rates updated March 2026 | [6 empty] | TOTAL | 0
|  |  |  | Labor |  | 0 | 60 | HR | 0
1.205 | MUD Fees
| Rates updated March 2026 (based on Schachne) |  |  |  | TOTAL | 0
| 1" Capital Facilities Charge (Impact Fee) |  |  | 0 | 3200 | 0
| 1" Meter Install |  |  | 0 | 500 | 0
| Water Tap |  |  | 0 | 650 | 0
1.214 | Bldg. Permit
| Rates updated March 2026 | [6 empty] | TOTAL | 0
City of Omaha
https://permits.cityofomaha.org/fees
| $1.00-$2,000 |  | 41 |  |  |  | 0 | 41 | 0
| $2,000-$25,000 |  | $41.00 for first $2,000, plus $9.53 for each additional $1,000 |  |  |  | 0 | 41 | 0
[7 empty] | 0 | 9.53 | 0
| $25,001-$50,000 |  | $260.19 for first $25,000, plus $6.44 for each additional $1,000 |  |  |  | 0 | 260.19 | 0
[7 empty] | 0 | 6.44 | 0
| $50,001-$100,000 |  | $421.19 for first $50,000, plus $3.19 for each additional $1,000 |  |  |  | 0 | 421.19 | 0
[7 empty] | 0 | 3.19 | 0
| $100,001-$500,000 |  | $580.69 for first $100,000, plus $2.78 for each additional $1,000 |  |  |  | 0 | 580.69 | 0
[7 empty] | 0 | 2.78 | 0
| $500,001-$1,000,000 |  | $1,692.69 for first $500,000, plus $2.37 for each additional $1,000 |  |  |  | 0 | 1692.69 | 0
[7 empty] | 0 | 2.37 | 0
| $1,000,001 and up |  | $2877.69 for first $1,000,000, plus $1.96 for each additional $1,000 |  |  |  | 0 | 1000000 | 0
[7 empty] | 0 | 1.96 | 0
City of Blair
https://www.blairne.gov/DocumentCenter/View/52/Building-Permit-and-Zoning-Fees-PDF
| Finished SF (not including finished basement) |  |  | 0 | * | 102 | 0
| Finished Basement SF |  |  | 0 | * | 62 | 0
| Unfinished Basement SF |  |  | 0 | * | 32 | 0
| Garage SF |  |  | 0 | * | 30 | 0
0
[6 empty] | Multiply by .006 | 0.006
[6 empty] | Total | 0
1.23 | Builders Risk
[8 empty] | TOTAL | 0
| Builders Risk (0.144/100 cost) |  |  |  |  | 0 | 0.144 |  | 0
| Misc. |  |  |  |  | 0 |  |  | 0
1.235 | General Liability
[8 empty] | TOTAL | 0
| Liability (2.77/1000 cost) |  |  |  |  | 0 | 2.77 |  | 0
| Bond |  |  |  |  | 0 |  |  | 0
| Misc. |  |  |  |  | 0 |  |  | 0
1.452 | Testing/Inspections
[8 empty] | TOTAL | 0
| Soil Testing |  |  |  |  | 0 | 1500 |  | 0
| Call back after excavation for visual inspection |  |  |  |  | 0 | 200 |  | 0
1.454 | Mockups
[8 empty] | TOTAL | 0
|  |  |  | Labor |  | 0 | 60 | HR | 0
|  |  |  | Materials |  | 0 | 350 | EA | 0
1.501 | Temporary Utilities
| Rates updated March 2026 | [6 empty] | TOTAL | 0
| Temp Power Service |  | OPPD |  |  | 0 | 150 | /MONTH | 0
| Temp Gas / Water Service |  | MUD |  |  | 0 | 250 | /MONTH | 0
| Temp Heat for Interior |  | Labor / Material |  |  | 0 | 200 | ALLOWANCE | 0
| Temp Heat for Exterior |  | Labor / Material |  |  | 0 | 200 | ALLOWANCE | 0
| Portable Toilet |  | Eagle Services |  | Monthly Charge (includes tax) | 0 | 128.4 | /MONTH | 0
[5 empty] | Delivery & Pickup (inlcudes tax) | 0 | 21.4 | /MONTH | 0
1.538 | Technology
| Rates updated March 2026 | [6 empty] | TOTAL | 0
[5 empty] | Equipment | 0 | 1200 | /JOB | 0
1.54 | Equipment (Forklift/Skid Loader)
| Rates updated March 2026 | [6 empty] | TOTAL | 0
[5 empty] | Equipment | 0 | 1750 | /JOB | 0
1.56 | Temporary Barries/Enclosures
| Rates updated March 2026 | [6 empty] | TOTAL | 0
|  |  |  | Material |  | 0 | 750 | EA | 0
|  |  |  | Labor | (2 guys at $60/hr) | 0 | 120 | HR | 0
|  |  |  | Subcontract |  | 0 | 4500 | EA | 0
1.578 | Site Maintenance
| Rates updated March 2026 | [6 empty] | TOTAL | 0
| Snow Removal |  |  | Labor |  | 0 | 60 | HR | 0
| Mowing/Spraying/Weedeating |  |  | Labor |  | 0 | 60 | HR | 0
1.74 | Cleaning & Waste Management
| Rates updated March 2026 | [6 empty] | TOTAL | 18215
| assume 17 mo x 4.33weeks/mo |  | 74 weeks |  | 74 | 2.5
|  |  | Interim Clean | Labor | 2.5 hrs/week | 185 | 55 | HR | 10175
|  |  | Final Clean | Labor |  | 0 | 55 | HR | 0
|  |  | Final Clean | Subcontract |  | 0 | 0.9 | EA | 0
|  |  | Window Clean | Subcontract | 2-story | 0 | 1200 | EA | 0
|  |  | Window Clean | Subcontract | Ranch | 0 | 750 | EA | 0
|  |  | Dumpsters | Other | S2 | 24 | 335 | each | 8040
Excludes drywall in phase - new dumpster every 3 weeks approx
1.81 | Warranties
| Warranty Historical |  |  | Own | McNeil | 1950000 | 0.006 | /TOTAL/COST | 11700
1.83 | Small Tools/Supply/Rent
| Rates updated March 2026 | [6 empty] | TOTAL | 0
[5 empty] | Tools/Supplies | 0 | 400 | /JOB | 0
[5 empty] | Floor Sander | 0 | 120 | /JOB | 0
[5 empty] | Other Equipment | 0 | 250 | /JOB | 0
1.84 | Punchlist
| Rates updated March 2026 | [6 empty] | TOTAL | 0
[5 empty] | Labor | 0 | 1200 | /JOB | 0

## DIV 2 EXIST. COND.
02.000 | EXISTING CONDITIONS
2.01 | Demolition
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 3 CONCRETE
03.000 | CONCRETE
3.3 | Footings/Foundations
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
3.32 | Interior Concrete Flatwork
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
Unit Rate Estimate - rates updated March of 2026
Lower Level Slab |  | 0 | sf
Garage Slab |  | 0 | sf
|  | 0 | sf
MATERIAL
Poly (LL & GARAGE SLAB SF x 1.15 = sf) |  |  |  | 0 | 0.075 | SF | 0
Lower Level Slab Granular (LL SF x .33ft x 1.25 / 18 = tons) |  |  |  | 0 | 22 | TON | 0
Garage Slab Granular (GARAGE SF x .33ft x 1.25 / 18 = tons) |  |  |  | 0 | 22 | TON | 0
Additive (Xypex for water impermeable) |  |  |  | 0 | 131.85 | BOX | 0
Expansion Joints at Walls |  |  | ls | 0 | 125 | EA | 0
SUBCONTRACTOR
Lower Level Slab |  |  |  | 0 | 6.75 | SF | 0
Poly install |  |  |  | 0 | 0.35 | SF | 0
Step Down (form charge) |  |  |  | 0 | 10 | LF | 0
Garage Slab |  |  |  | 0 | 6.75 | SF | 0
Saw Cut slabs |  |  |  | 0 | 0.05 | SF | 0
Grading |  |  |  | 0 | 0.25 | SF | 0
Pump charge |  |  |  | 0 | 1700 | EA | 0
Cure & Seal |  |  |  | 0 | 0.12 | SF | 0
[6 empty] | TOTAL | 0

## DIV 4 MASONRY
04.000 | MASONRY
4.21 | Brick / Precast Sills & Caps
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
Unit Rate Estimate - rates updated March of 2026
Brick (Modular) |  | 0 | SF | 7 | 0 | brick ea
Soldiers/Rowblocks |  | 0 | LF | 3.5 | 0 | brick ea
Approx. per 292lf |  |  |  | RAW QTY BRICK | 0 | brick ea
|  |  |  | 12% WASTE FACTOR | 0 | brick ea
|  |  |  | TOTAL | 0 | brick ea
*adjust brick/cube quantity based on brick size |  |  |  | Qty of Full Cubes | 525 | brick/cube
|  |  |  | TOTAL | 0 | total cubes
Per Laura at Watkins:
125 brick/bag of masonry for this product
premix mortar - 35-40 brick/bag on modular / 30-32 brick per bag oversize
MATERIAL
Brick (modular) |  |  |  | 0 | 0.95 | 0
Brick (solids) |  |  |  | 0 | 1.5 | 0
premix mortar (colored) |  |  |  | 0 | 14.45 | 0
premix mortar (standard gray) |  |  |  | 0 | 9.5 | 0
Masonry Cement |  | 7 bags/M |  | 0 | 11 | 0
Portland Cement |  | 1 bag/5 of masonry |  | 0 | 14 | 0
Sand |  | 3 to 1 by weight |  | 0 | 15 | 0
Weep Holes |  | approx. every 3lf |  | 0 | 0.65 | 0
Nervastral |  | 12"x150'/roll |  | 0 | 90 | 0
SureKlean #600 detergent |  | 600sf/gallon |  | 0 | 25 | 0
Ties |  | .10 ties per brick |  | 0 | 0.35 | 0
1" Mortar Net |  |  |  | 0 | 2.4 | 0
Misc. Tools |  |  |  | 0 | 200 | 0
Pallet charge |  |  |  | 0 | 28 | 0
freight/delivery |  |  |  | 0 | 75 | 0
[5 empty] | SUBTOTAL | 0
[5 empty] | 7% TAX | 0
[5 empty] | TOTAL | 0
4.22 | Concrete Masonry Units (Blockwork)
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
4.43 | Stone Masonry / Precast Sills & Caps
|  |  |  | FSP/Watkins - Stone | FSP - Precast | T Docken | Company
Base Bid |  |  |  | 28300 | 7683 | 27470 | 0
|  |  | TOTAL | 28300 | 7683 | 27470 | 0
Unit Rate Estimate - rates updated March of 2026
Thin Stone Flats |  | 1250 | SF | 12% waste factor | 1400 | stone sf
Thin Stone Corners |  | 75 | LF | 12% waste factor | 84 | stone sf
Approx. per 292lf |  |  |  | TOTAL | 1484 | stone sf
Full Bed Depth Stone |  | 327 | SF | 10% waste factor | 359.7 | stone sf
Approx. per 292lf |  |  |  | TOTAL | 359.7 | stone sf
|  |  |  | (Full Bed Depth) Approximate ton qty | 38 | sf/ton
|  |  |  | TOTAL | 9.4658 | tons
per Laura at Watkins:
thin stone mortar coverage - Promix 70lb bag is 15sf/bag for joints; 7sf/bag for scratch coat
full bed depth stone mortar coverage - depends on stone size, but 7-10sf/bag gets close
german schmear style mortar coverage - depends on heaviness of schmear
approximate sf/ton for full bed depth stone - 38-40sf/ton
MATERIAL
Thin Stone Flats |  | $/sf | FSP Rate | 1400 | 8.36 | 11704
Thin Stone Corners |  | $/each | FSP Rate | 84 | 11.41 | 958.44
Full Bed Depth Stone |  | $/ton | allowance | 9 | 600 | 5400
Premix Mortar (colored) - thin |  | 1400/15sf |  | 100 | 14.45 | 1445
Premix Mortar (colored) - full bed |  | 360/7sf |  | 55 | 14.45 | 794.75
Premix Mortar (standard gray) |  |  |  | 0 | 13.8 | 0
Scratch coat mortar |  | 1700/7sf |  | 250 | 13.8 | 3450
Metal Lathe |  | 27"x96", assume 16sf with overlap |  | 100 | 16 | 1600
Felt |  |  |  | 0 | 35 | 0
Lathe Bottom Weep Screed |  | assume 10' |  | 35 | 17 | 595
Rainscreen, Keene |  | 4'x65' |  | 6 | 10 | 60
Masonry Cement |  | 7 bags/M |  | 0 | 11 | 0
Portland Cement |  | 1 bag/5 of masonry |  | 0 | 14 | 0
Sand |  | 3 to 1 by weight |  | 0 | 15 | 0
Weep Holes |  | approx. every 3lf |  | 125 | 0.65 | 81.25
Nervastral |  | 12"x150'/roll |  | 0 | 90 | 0
SureKlean #600 detergent |  | 600sf/gallon |  | 3 | 25 | 75
Ties |  | .10 ties per brick |  | 0 | 0.35 | 0
1" Mortar Net |  |  |  | 0 | 2.4 | 0
Misc. Tools |  |  |  | 1 | 275 | 275
Pallet charge |  | approx. 150-200sf/pallet |  | 3 | 28 | 84
freight/delivery |  |  |  | 3 | 100 | 300
[5 empty] | SUBTOTAL | 26822.44
[5 empty] | 5.5 TAX | 1475.2342
[5 empty] | TOTAL | 28297.6742

## DIV 5 METAL
05.000 | METAL
5.12 | Strucutural Steel - Material
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
5.528 | Metal Interior Railing
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
5.53 | Exterior Deck Railing
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
5.7 | Decorative Metal
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 6 CARPENTRY
06.000 | CARPENTRY
6.11 | Wood Framing
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
6.15 | Wood Decks
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
6.38 | Cabinetry
|  |  |  | Company | Company | Company | Company
Main Level
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
Lower Level
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
Upper Level
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
6.442 | Exterior Brackets/Timbers
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
6.46 | Wood Interior Trim
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
Unit Rate Estimate
| DESCRIPTION |  | SPECIES | QTY | UNIT PRICE | SUBTOTAL | NOTES
BASE AND CASING
| 3" Casing |  |  | 0 | 0 | 0
| 3 1/2" Casing |  |  | 0 | 0 | 0
| 4" Casing |  |  | 0 | 0 | 0
| 3" Base (Mechanical Rooms) |  |  | 0 | 0 | 0
| 4" Base |  |  | 0 | 0 | 0
| 6" Base |  |  | 0 | 0 | 0
| 8" Base |  |  | 0 | 0 | 0
| PVC Base - Azek (Garage) |  |  | 0 | 0 | 0
| Base Shoe |  |  | 0 | 0 | 0
| Window Jamb Extensions |  |  | 0 | 0 | 0
| Tooling/Setup Charge |  |  | 0 | 500 | 0
CASING DETAILS
| 1 1/2" bn |  |  | 0 | 0 | 0
| 1 x 6 S4S (for jamb) |  |  | 0 | 0 | 0
| stop |  |  | 0 | 0 | 0
| glass mullion (to match door profile) |  |  | 0 | 0 | 0
| backband (for front door) |  |  | 0 | 0 | 0
| Mullcenter (double door) |  |  | 0 | 0 | 0
| 1 x 4 S4S window stools |  |  | 0 | 0 | 0
| set up/freight for glass mullions |  |  | 0 | 0 | 0
CROWN MOLDING
| 6" CROWN |  |  | 0 | 0 | 0
| Built-Up Band |  |  | 0 | 0 | 0
| 1 x 4 S4S (backing material) |  |  | 0 | 0 | 0
BEAMS
| Industrial Board (structure) |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
DETAIL
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
DETAIL
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
DETAIL
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
STAIR PARTS
| Newel Posts |  |  | 0 | 0 | 0
| Wood Railing |  |  | 0 | 0 | 0
| Balusters |  |  | 0 | 0 | 0
| 1x12 skirt boards |  |  | 0 | 0 | 0
| 4" casing skirt board cap |  |  | 0 | 0 | 0
| 1/2x12 End Cap Treads |  |  | 0 | 0 | 0
| 1/2x8 End Cap Risers |  |  | 0 | 0 | 0
| Planing Charge |  |  | 0 | 0 | 0
| End Cap & Balcony Nosing |  |  | 0 | 0 | 0
MISC. TRIM DETAILS
| Glue, shims, fasteners, blades |  |  | 0 | 750 | 0
| Delivery |  |  | 0 | 150 | 0
[5 empty] | subtotal | 0
[5 empty] | 7% tax | 0
[5 empty] | TOTAL | 0
6.612 | Countertop Allowance
|  |  |  | Company | Company | Company | Company
Main Level
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
Lower Level
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
Upper Level
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0

## DIV 7 MOISTURE PROTECTION
07.000 | MOISTURE/THERMAL PROTECTION
7.13 | Waterproofing/Passive Radon/Termite Treatment
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.21 | Insulation
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.25 | Stucco System
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.3 | Roofing
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.455 | Siding
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.469 | Exterior Carsiding
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.6 | Flashing/Brickledge
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.63 | Gutters/Downspouts
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.92 | Joint Sealants
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 8 OPENINGS
08.000 | OPENINGS
8.14 | Interior Wood Doors
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.178 | Front Door
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.184 | Pet Door
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.385 | Garage Doors
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.5 | Windows
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.6 | Roof Windows/Skylights/Sun Tunnel
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.817 | Mirrors/Glass Inserts/Shower Doors
|  |  |  | FRAMED ALLOWANCE | Gatsby
Main & Upper Level
| Powder | ALLOWANCE | 24x40 Oval, gold | 375
| Primary Bathroom | ALLOWANCE | 30x48 Oval, black ($400 ea) | 800
| Bath 2 | ALLOWANCE | 24x36 Oval,green scalloped | 650
| Bath 3 | ALLOWANCE | 24x36 Rectangle, white | 375
| Bath 4 | ALLOWANCE | 48x42 Rectangle, black | 800
| Primary Shower Door | ALLOWANCE | Frameless, gold |  | 2193
| Primary Wardrome Mirror | ALLOWANCE | Plate Glass
Lower Level
| LL Bath Mirror | ALLOWANCE | 30x48 Oval, black | 375 | 3574
| LL Bath Shower Door | ALLOWANCE | Semi-Frameless, black
| Fitness Mirrors | ALLOWANCE | Plate Glass
1
2
3
4
5
6
7
8
9 | Install - hang framed mirrors ($75/hr x 4hrs = $300) |  |  | 300
10 | McNeil Company Wood Backer Supply/Install |  |  | NA
|  |  | subtotal | 3675 | 5767
|  |  | tax | 257.25
|  |  | freight | 500
4432.25
|  |  | TOTAL - Mirrors & Shower Doors | 10199.25

## DIV 9 FINISHES
09.000 | FINISHES
9.2 | Drywall
|  |  |  | BC Drywall | Freedom
|  |  |  | 30925 | 44825
1 | Level 4 wall finish throughout |  |  |  | -3558
2 | Level 5 ceiling finish ML only
3 | Finished Lower Level |  |  | 7600
| Base Bid Total |  |  | 38525 | 41267
ALTERNATES
1 | Add for Level 5 wall finish at UL |  |  | 800 | 460
2 | Add for Level 5 wall finishat LL |  |  | 1175 | 300
9.3 | Tile
Floor Tile
[8 empty] | TOTAL | 0
| Location | [7 empty] | 0
|  |  |  | Tile Material | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 75 | EA | 0
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Self Leveling | ALLOWANCE | 0 | 5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Tile Material | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 75 | EA | 0
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Self Leveling | ALLOWANCE | 0 | 5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Tile Material | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 75 | EA | 0
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Self Leveling | ALLOWANCE | 0 | 5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Tile Material | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 75 | EA | 0
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Self Leveling | ALLOWANCE | 0 | 5 | SF | 0
|  |  |  | In-Floor Heat | ALLOWANCE | 0 | 20 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Tile Material | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 75 | EA | 0
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Anti-fracture Membrane | ALLOWANCE | 0 | 2 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Tile Material | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 75 | EA | 0
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Anti-fracture Membrane | ALLOWANCE | 0 | 2 | SF | 0
Tile Backsplash
[8 empty] | TOTAL | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Deco | ALLOWANCE | 0 | 275 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 32 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 50 | EA | 0
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Deco | ALLOWANCE | 0 | 275 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 32 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 50 | EA | 0
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Deco | ALLOWANCE | 0 | 275 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 32 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 50 | EA | 0
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Deco | ALLOWANCE | 0 | 275 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 32 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 50 | EA | 0
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Deco | ALLOWANCE | 0 | 275 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 32 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 50 | EA | 0
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
Wall Tile/Columns
[8 empty] | TOTAL | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 35 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 32 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 50 | EA | 0
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
Shower/Tub Tile
[8 empty] | TOTAL | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 12 | SF | 0
|  |  |  | Deco Tile | ALLOWANCE | 0 | 400 | EA | 0
|  |  |  | Ceiling Tile | ALLOWANCE | 0 | 12 | SF | 0
|  |  |  | Floor Tile | ALLOWANCE | 0 | 20 | SF | 0
|  |  |  | Bullnose | ALLOWANCE | 0 | 15 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Miter Outside Corners - Addt'l Cost | ALLOWANCE | 0 | 300 | EA | 0
|  |  |  | Labor - install seat, shelves, jamb and/or curb | ALLOWANCE | 0 | 1000 | EA | 0
|  |  |  | Labor - floor | ALLOWANCE | 0 | 85 | SF | 0
|  |  |  | Tile Drain | ALLOWANCE | 0 | 150 | EA | 0
|  |  |  | Sealer/Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 100 | EA | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Deco Tile | ALLOWANCE | 0 | 400 | EA | 0
|  |  |  | Ceiling Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Floor Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Bullnose | ALLOWANCE | 0 | 15 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Labor - install shelves, curb | ALLOWANCE | 0 | 1000 | EA | 0
|  |  |  | Labor - floor | ALLOWANCE | 0 | 85 | SF | 0
|  |  |  | Tile Drain | ALLOWANCE | 0 | 150 | EA | 0
|  |  |  | Sealer/Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 100 | EA | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Deco Tile | ALLOWANCE | 0 | 400 | EA | 0
|  |  |  | Ceiling Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Floor Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Bullnose | ALLOWANCE | 0 | 15 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Labor - install shelves, curb | ALLOWANCE | 0 | 1000 | EA | 0
|  |  |  | Labor - floor | ALLOWANCE | 0 | 85 | SF | 0
|  |  |  | Tile Drain | ALLOWANCE | 0 | 150 | EA | 0
|  |  |  | Sealer/Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 100 | EA | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Deco Tile | ALLOWANCE | 0 | 400 | EA | 0
|  |  |  | Ceiling Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Floor Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Bullnose | ALLOWANCE | 0 | 15 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Labor - install shelves, curb | ALLOWANCE | 0 | 1000 | EA | 0
|  |  |  | Labor - floor | ALLOWANCE | 0 | 85 | SF | 0
|  |  |  | Tile Drain | ALLOWANCE | 0 | 150 | EA | 0
|  |  |  | Sealer/Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 100 | EA | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Deco Tile | ALLOWANCE | 0 | 400 | EA | 0
|  |  |  | Ceiling Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Floor Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Bullnose | ALLOWANCE | 0 | 15 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Labor - install shelves, curb | ALLOWANCE | 0 | 1000 | EA | 0
|  |  |  | Labor - floor | ALLOWANCE | 0 | 85 | SF | 0
|  |  |  | Tile Drain | ALLOWANCE | 0 | 150 | EA | 0
|  |  |  | Sealer/Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 100 | EA | 0
9.64 | Wood Flooring / LVP / LVT Allowance
| WOOD FLOOR AREAS | [5 empty] | TOTAL | 53531.73
| Main Level | 1658 | SF
| Subtotal | 1658 | SF
| 7% waste - typical | 116.06 | SF
| Total | 1774.06 | SF
LVP AREAS
| Lower Level - not including Golf | 984 | SF
| Upper Level | 1097 | SF
| Subtotal | 2081 | SF
| 7% waste - typical | 145.67 | SF
| Total | 2226.67 | SF
| Prefin. wood material & install - ML |  |  | Portercraft Rivervail Astoria | 1 | 19840 | SF | 19840
| Wood Vents (Flush Mount) |  |  | ALLOWANCE | 12 | 116.79 | EA | 1401.48
| Miscellanous Underlayment/Floor Prep |  |  | ALLOWANCE | 1774 | 3 | SF | 5322
| LVP / LVT material & labor - UL |  |  | Coretec Parchment Oak | 1 | 11707 | SF | 11707
| Miscellanous Underlayment/Floor Prep - UL |  |  | ALLOWANCE | 1097 | 3.25 | SF | 3565.25
| LVP / LVT material & labor - LL |  |  | Coretec Parchment Oak | 1 | 11446 | SF | 11446
| LVP / LVT Prep / Glue / Transitions |  |  | ALLOWANCE | 1 | 250 | SF | 250
ALTERNATES
| Carpet at Bonus Room in lieu of Coretec Parchment Oak |  |  |  | -1744 | DEDUCT
| Wood flooring at Upper Level in lieu of Coretec Parchment Oak |  |  |  | 1275 | ADD
| Carpet at Bonus Room in lieu of Portercraft |  |  |  | -1889 | DEDUCT
9.657 | Kinetix
| AREAS | [5 empty] | TOTAL | 1871.5569
| Fitness | 212 | SF
| Subtotal | 212 | SF
| 7% waste | 14.84 | SF
| Total | 226.84 | SF
| Conversion to SY (X 1.30 / 9) | 32.7658 | SY
| Carpet Tile/Rubber Flooring Material |  |  | ALLOWANCE | 33 | 36.99 | SF | 1220.67
| Adhesive/Patch/Prep |  |  | ALLOWANCE | 1 | 350 | EA | 350
[7 empty] | subtotal | 1570.67
[7 empty] | tax 5.5% | 86.3869
[7 empty] | subtotal | 1657.0569
| Installation Labor |  |  | ALLOWANCE | 33 | 6.5 | SF | 214.5
[7 empty] | TOTAL | 1871.5569
9.672 | Epoxy Flooring
| AREAS | [5 empty] | TOTAL | 0
| Garage | 0 | SF
| Mechanical/Storage | 0 | SF
| Mechanical/Storage | 0 | SF
| Subtotal | 0 | SF
| 7% waste | 0 | SF
| Total | 0 | SF
| Epoxy Flooring Material / Installation |  |  | ALLOWANCE | 0 | 6 | SF | 0
9.68 | Carpet Allowance
| AREAS |  |  |  |  | TOTAL | 2499
12' Roll Layout | Stairs (x2 for risers) | 234 | SF
| Total SF | 234 | SF
| Conversion to SY (X 1.30 / 9) | 33.8 | SY
ALLOWANCE BREAKDOWN
| Installation Labor |  |  |  | 8 | PER SY
| Carpet Pad (memory foam) |  |  |  | 8 | PER SY
| Material Allowance |  |  |  | 56 | PER SY
| Floor Prep / Tack Strip / Etc. |  |  |  | 1.5 | PER SY
| Carpet Material, Labor, and Pad |  | ALLOWANCE | 34 | 73.5 | SY | 2499
| Additional Labor for Stair |  | ALLOWANCE | 0 | 30 | EA | 0
9.72 | Wall Coverings/Faux Finishing
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
9.91 | Painting
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0

## DIV 10 SPECIALTIES
10.000 | SPECIALTIES
10.05 | Finish Hardware Allowance
Cabinet Hardware
| POWDER BATH |  | DOORS/DRAWERS |  | 0 | 10 | 0
| SERVICE ENTRY |  | DOORS/DRAWERS |  | 0 | 10 | 0
|  |  | HOOKS |  | 0 | 10 | 0
| PRIMARY BATH |  | DOORS/DRAWERS |  | 0 | 10 | 0
| PRIMARY WARDROBE |  | DOORS/DRAWERS |  | 0 | 10 | 0
| GREAT ROOM |  | DOORS/DRAWERS |  | 0 | 10 | 0
| KITCHEN ISLAND |  | DOORS/DRAWERS |  | 0 | 10 | 0
| KITCHEN |  | DOORS/DRAWERS |  | 0 | 10 | 0
|  |  | APPLIANCE PULLS |  | 0 | 350 | 0
| PANTRY |  | DOORS/DRAWERS |  | 0 | 10 | 0
| LAUNDRY |  | DOORS/DRAWERS |  | 0 | 10 | 0
| BATHROOM |  | DOORS/DRAWERS |  | 0 | 10 | 0
| BATHROOM |  | DOORS/DRAWERS |  | 0 | 10 | 0
| BATHROOM |  | DOORS/DRAWERS |  | 0 | 10 | 0
| BAR |  | DOORS/DRAWERS |  | 0 | 10 | 0
| GARAGE |  | DOORS/DRAWERS |  | 0 | 10 | 0
| OUTDOOR |  | DOORS/DRAWERS |  | 0 | 10 | 0
[6 empty] | SUBTOTAL | 0
[6 empty] | FREIGHT | 100
[6 empty] | 7% TAX | 7
[6 empty] | TOTAL | 107
Door Hardware
| LOCATION |  |  |  | QTY | UNIT COST | SUBTOTAL
Lower Level
| DOOR LEVERS (PASSAGE/PRIVACY) |  |  | Schlage Custom | 0 | 95 | 0
| DUMMIES |  |  | Schlage Custom | 0 | 445 | 0
| POCKET DOOR |  |  | Emtek | 0 | 275 | 0
| 3 1/2" HINGES - per pair |  |  |  | 0 | 14 | 0
| 4" HINGES - per pair |  |  |  | 0 | 18 | 0
| HINGE DOOR STOP |  |  |  | 0 | 10 | 0
| BASE DOOR STOP |  |  |  | 0 | 15 | 0
Main Level
| FRONT DOOR HARDWARE |  |  |  | 0 | 600 | 0
| PATIO - MULTIPOINT |  |  | Emtek | 0 | 575 | 0
| DOOR LEVERS (PASSAGE/PRIVACY) |  |  | Emtek | 0 | 187 | 0
| DEADBOLTS (AT GARAGE) |  |  | Emtek | 0 | 100 | 0
| DUMMIES |  |  | Emtek | 0 | 187 | 0
| POCKET DOOR |  |  | Emtek | 0 | 275 | 0
| BARN DOORS |  |  |  | 0 | 325 | 0
| BI-FOLD KNOBS |  |  |  | 0 | 25 | 0
| 3 1/2" HINGES - per pair |  |  |  | 0 | 14 | 0
| 4" HINGES - per pair |  |  |  | 0 | 50 | 0
| SPRING HINGE |  |  |  | 0 | 85.6 | 0
| HINGE DOOR STOP |  |  |  | 0 | 10 | 0
| BASE DOOR STOP |  |  |  | 0 | 15 | 0
| FLOOR STOP |  |  |  | 0 | 50 | 0
Upper Level
| DOOR LEVERS (PASSAGE/PRIVACY) |  |  |  | 0 | 95 | 0
| DUMMIES |  |  | Schlage Custom | 0 | 445 | 0
| POCKET DOOR |  |  | Emtek | 0 | 275 | 0
| 3 1/2" HINGES - per pair |  |  |  | 0 | 14 | 0
| 4" HINGES - per pair |  |  |  | 0 | 18 | 0
| HINGE DOOR STOP |  |  |  | 0 | 10 | 0
| BASE DOOR STOP |  |  |  | 0 | 15 | 0
[6 empty] | SUBTOTAL | 0
[6 empty] | FREIGHT | 100
[6 empty] | 7% TAX | 7
[6 empty] | TOTAL | 107
Bath Accessories
POWDER BATH
|  |  | TOILET PAPER HOLDERS |  | 0 | 75 | 0
|  |  | TOWEL RINGS |  | 0 | 75 | 0
PRIMARY BATH
|  |  | TOILET PAPER HOLDERS |  | 0 | 75 | 0
|  |  | TOWEL BARS |  | 0 | 100 | 0
|  |  | TOWEL RINGS |  | 0 | 75 | 0
|  |  | ROBE HOOKS |  | 0 | 35 | 0
BATHROOM
|  |  | TOILET PAPER HOLDERS |  | 0 | 75 | 0
|  |  | TOWEL BAR |  | 0 | 100 | 0
|  |  | TOWEL RINGS |  | 0 | 75 | 0
|  |  | ROBE HOOKS |  | 0 | 35 | 0
BATHROOM
|  |  | TOILET PAPER HOLDERS |  | 0 | 75 | 0
|  |  | TOWEL BARS |  | 0 | 100 | 0
|  |  | TOWEL RINGS |  | 0 | 75 | 0
|  |  | ROBE HOOKS |  | 0 | 35 | 0
BATHROOM
|  |  | TOILET PAPER HOLDERS |  | 0 | 75 | 0
|  |  | TOWEL BARS |  | 0 | 100 | 0
|  |  | TOWEL RINGS |  | 0 | 75 | 0
|  |  | ROBE HOOKS |  | 0 | 35 | 0
[6 empty] | SUBTOTAL | 0
[6 empty] | FREIGHT | 100
[6 empty] | 7% TAX | 7
[6 empty] | TOTAL | 107
[6 empty] | TOTAL ALL ACCESSORIES | 321
[6 empty] | TOTAL LABOR | 0
10.14 | Address Numbers
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
10.31 | Fireplaces
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
10.314 | Fireplace Facings
[6 empty] | TOTAL | 0
Location | [6 empty] | 0
|  | Field Material | ALLOWANCE | 0 | 0 | SF | 0
|  | Labor/Setting Materials | ALLOWANCE | 0 | 0 | SF | 0
|  | Delivery | ALLOWANCE | 0 | 0 | EA | 0
|  | Sealer | ALLOWANCE | 0 | 0 | SF | 0
|  | Precast Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Metal Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Labor - Surround | ALLOWANCE | 0 | 0 | EA | 0
Location | [6 empty] | 0
|  | Field Material | ALLOWANCE | 0 | 0 | SF | 0
|  | Labor/Setting Materials | ALLOWANCE | 0 | 0 | SF | 0
|  | Delivery | ALLOWANCE | 0 | 0 | EA | 0
|  | Sealer | ALLOWANCE | 0 | 0 | SF | 0
|  | Precast Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Metal Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Labor - Surround | ALLOWANCE | 0 | 0 | EA | 0
Location | [6 empty] | 0
|  | Field Material | ALLOWANCE | 0 | 0 | SF | 0
|  | Labor/Setting Materials | ALLOWANCE | 0 | 0 | SF | 0
|  | Delivery | ALLOWANCE | 0 | 0 | EA | 0
|  | Sealer | ALLOWANCE | 0 | 0 | SF | 0
|  | Precast Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Metal Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Labor - Surround | ALLOWANCE | 0 | 0 | EA | 0
10.562 | Storage Shelving
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
10.566 | Wine Cellar Racks/Cooling
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
10.572 | Closets
|  |  |  | Company | Company | Company | Company
Main Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
Lower Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
Upper Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
10.712 | Exterior Shutters
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0

## DIV 11 EQUIPMENT
11.000 | EQUIPMENT
11.302 | Appliances Allowance
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
11.52 | TV's Allowance
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
11.66 | Athletic Equipment
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
11.678 | Game Room Equipment (Golf Simulator)
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 12 FURNISHINGS
12.000 | FURNISHINGS
12.17 | Art Glass
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
12.2 | Window Treatments
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
12.25 | Motorized Shades
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 13 SPECIAL CONST.
13.000 | SPECIAL CONSTRUCTION
13.112 | Swimming Pool
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
13.174 | Sauna
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
13.26 | Storm Shelter Room(s)
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
13.342 | Screen Porch Systems
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 14 CONVEYING SYSTEMS
14.000 | CONVEYING SYSTEMS
14.05 | Elevators
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 21 FIRE SUPRESSION
21.000 | FIRE SUPPRESSION
21.05 | Fire Suppression
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 22-23 PLUM-HVAC
22.000 | PLUMBING
22.05 | Plumbing
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
22.322 | Water Filtration System
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
22.4 | Plumbing Fixtures Allowance
|  | QUANITITY | UNIT COST | SUBTOTAL
BATHROOM
| SINK SS | 0 | 100 | 0
| FAUCET | 0 | 250 | 0
| TOILET | 0 | 400 | 0
| SEAT/TRIP LEVER | 0 | 115 | 0
| SHOWER VALVE/TRIM | 0 | 450 | 0
| FIBERGLASS SHOWER BASE | 0 | 650 | 0
BAR
| SINK | 0 | 450 | 0
| FAUCET | 0 | 475 | 0
| RO FAUCET | 0 | 400 | 0
| AIR SWITCH | 0 | 125 | 0
| DISPOSAL | 0 | 175 | 0
| BASKET STRAINER | 0 | 70 | 0
KITCHEN
| SINK | 0 | 800 | 0
| FAUCET | 0 | 500 | 0
| RO FAUCET | 0 | 400 | 0
| SOAP DISPENSER | 0 | 150 | 0
| AIR SWITCH | 0 | 125 | 0
| DISPOSAL | 0 | 300 | 0
| BASKET STRAINER | 0 | 70 | 0
| POT FILLER | 0 | 700 | 0
POWDER BATH
| SINK | 0 | 175 | 0
| FAUCET | 0 | 400 | 0
| TOILET | 0 | 400 | 0
| SEAT/TRIP LEVER | 0 | 115 | 0
LAUNDRY
| SINK | 0 | 225 | 0
| FAUCET | 0 | 200 | 0
| BASKET STRAINER | 0 | 70 | 0
PRIMARY BATH
| SINK | 0 | 150 | 0
| FAUCETS | 0 | 400 | 0
| TOILET | 0 | 400 | 0
| SEAT/TRIP LEVER | 0 | 115 | 0
| BIDET SEAT | 0 | 1000 | 0
| SHOWER VALVE/TRIM | 0 | 1250 | 0
| WHIRLPOOL TUB | 0 | 4750 | 0
| TUB VALVE/FAUCET | 0 | 1000 | 0
GUEST BATH
| SINK | 0 | 100 | 0
| FAUCET | 0 | 250 | 0
| TOILET | 0 | 400 | 0
| SEAT/TRIP LEVER | 0 | 115 | 0
| SHOWER VALVE/TRIM | 0 | 450 | 0
| FIBERGLASS SHOWER BASE | 0 | 650 | 0
|  |  | SUBTOTAL | 0
|  |  | FREIGHT | 0
|  |  | 7% TAX | 0
|  |  | TOTAL | 0
23.000 | HVAC
23.05 | HVAC
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
23.4 | Duct Cleaning
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 26-28 ELEC. - LV
26.000 | ELECTRICAL
26.05 | Electrical Service & Wiring
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
26.41 | Lightning Protection
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
26.505 | Light Fixtures Allowance
*ALLOWANCE UNIT COSTS INCLUDE ALL BULBS
| LOCATION | TYPE |  | QTY | UNIT PRICE | SUBTOTAL
Main Level
| FOYER | CEILING MOUNT |  | 0 | 500 | 0
| DINING | CEILING MOUNT |  | 0 | 1000 | 0
| POWDER BATH | WALL MOUNT |  | 0 | 150 | 0
| KITCHEN | PENDANTS |  | 0 | 250 | 0
| GREAT ROOM | CEILING FAN |  | 0 | 400 | 0
| LAUNDRY ROOM | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| PRIMARY BEDROOM | CEILING FAN |  | 0 | 250 | 0
| PRIMARY BATHROOM | WALL MOUNT |  | 0 | 150 | 0
| PRIMARY WARDROBE | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| GUEST BEDROOM | CEILING FAN |  | 0 | 250 | 0
| GUEST BATHROOM VANITY | WALL MOUNT |  | 0 | 150 | 0
| SERVICE ENTRY | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| GARAGE | LED - by elect. |  | 0 | 0 | 0
Upper Level
| BEDROOM | CEILING FAN |  | 0 | 225 | 0
| BEDROOM | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| WARDROBE | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| BATHROOM VANITY | WALL MOUNT |  | 0 | 125 | 0
Lower Level
| BATHROOM VANITY | WALL MOUNT |  | 0 | 125 | 0
| BEDROOM | CEILING FAN |  | 0 | 225 | 0
| BEDROOM | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| WARDROBE | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| FITNESS ROOM | CEILING FAN |  | 0 | 225 | 0
| FITNESS WARDROBE | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| MECHANICAL/STORAGE | LED - by elect. |  | 0 | 0 | 0
EXTERIOR LIGHTING
| FRONT ENTRY | WALL MOUNT |  | 0 | 550 | 0
| GARAGE DOOR PIERS | WALL MOUNT |  | 0 | 300 | 0
| COVERED PATIO | CEILING FAN |  | 0 | 400 | 0
| COVERED PATIO | WALL MOUNT |  | 0 | 400 | 0
| LOWER PATIO | WALL MOUNT |  | 0 | 400 | 0
| FLOODS | WALL MOUNT - by elect. |  | 0 | 0 | 0
[5 empty] | SUBTOTAL | 0
[5 empty] | FREIGHT | 0
[5 empty] | 7% TAX | 0
[5 empty] | TOTAL (INCLUDING BULBS) | 0
26.57 | Lighting Control System Allowance
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
27.000 | COMMUNICATIONS
27.41 | Audio-Visual Systems/Structured Wire/Sound System Allowance
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
28.000 | ELECTRONIC SAFETY & SECURITY
28.07 | Security System/Fire Protection/Video Surveillance Allowance
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 31-32 EARTH-SITE
31.000 | EARTHWORK
31.218 | Site Demolition
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
31.23 | Excavation/Fill/Grading/Silt Fence
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
31.26 | Surveying
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.000 | EXTERIOR IMPROVEMENTS
32.13 | Exterior Concrete Flatwork
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
Unit Rate Estimate
Driveway |  | 0 | SF
Front Stoop |  | 0 | SF
Front Walk |  | 0 | SF
City Sidewalks |  | 0 | SF
AC Pads |  | 0 | SF
Pool Deck |  | 0 | SF
Rear Patio |  | 0 | SF
|  | 0 | SF
MATERIAL
sleeve materials (pvc for under slabs) |  |  | 0 | 75 | EA | 0
Granular (SF x .25ft x 1.25 / 18 = X tons) |  |  | 0 | 16 | TON | 0
Additive (Xypex for water impermeable) |  |  | 0 | 131.85 | BOX | 0
expansion joints at walls |  |  | 0 | 150 | EA | 0
SUBCONTRACTOR
Driveway (5" with rebar) |  |  | 0 | 0 | SF | 0
Driveway Curb |  |  | 0 | 0 | LF | 0
Street Curb Cut |  |  | 0 | 0 | SF | 0
Front Walks (4") |  |  | 0 | 0 | SF | 0
City Sidewalks (4") |  |  | 0 | 0 | SF | 0
Front Stoop |  |  | 0 | 800 | EA | 0
Concrete Steps |  |  | 0 | 0 | LF | 0
AC Pads (4") |  |  | 0 | 0 | SF | 0
Rear Patio (4") |  |  | 0 | 0 | SF | 0
Pool Deck (4") |  |  | 0 | 0 | SF | 0
Trench Drain |  |  | 0 | 0 | LF | 0
Paver inset areas |  |  | 0 | 0 | LF | 0
Additional Concrete Material for 5" thick |  |  | 0 | 82.5 | CY | 0
Pump Charge for elevated balconies |  |  | 0 | 1500 | EA | 0
Grading |  |  | 0 | 0.4 | SF | 0
Cure & Seal |  |  | 0 | 0.05 | SF | 0
Sealer (Application of Stifle) |  |  | 0 | 0.45 | SF | 0
[5 empty] | TOTAL | 0
32.142 | Pavers Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
Unit Rate Estimate
Driveway | 0 | SF
Front Walk | 0 | SF
Front Stoop | 0 | SF
Rear Patio | 0 | SF
Pool Deck | 0 | SF
| 0 | SF
| 0 | 8% waste
| 0 | total SFpavers
STEPPING STONES |  | 0 | EA
NOTE: verify full pallet quantities or sf count
Paver Material (incl tax) |  |  | ALLOWANCE | 0 | 6.25 | SF | 0
Bullnose Edging (lakeside nosing) |  |  | ALLOWANCE | 0 | 12 | LF | 0
Front Stoop (brick and mortar) |  |  | ALLOWANCE | 0 | 7.25 | SF | 0
Front Stoop |  |  | ALLOWANCE | 0 | 15.75 | SF | 0
Aluminum Edging |  |  | ALLOWANCE | 0 | 3.25 | LF | 0
Subcontractor Installation |  |  | ALLOWANCE | 0 | 6.75 | SF | 0
Palmeric Sand |  |  | ALLOWANCE | 0 | 1 |  | 0
additional for asphalt set |  |  | ALLOWANCE | 0 | 1.75 | SF | 0
Stepping Stones |  |  | ALLOWANCE | 0 | 100 | EA | 0
[6 empty] | TOTAL | 0
OPTION
Sealer / Enhancer |  |  | ALLOWANCE | 0 | 1.5 | SF | 0
32.18 | Athletic/Recreational Surfacing
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.181 | Artificial Turf
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.3 | Landscape Lighting Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.31 | Fences/Gates
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.32 | Retaining Walls Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.392 | Fire Pit Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.394 | Exterior Grill/Hood
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.8 | Irrigation Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.922 | Seeding/Sod Allowance
| Sod - Raw Area | 0 | SF | 0.33 | 0 | 0
| (less beds) |  |  |  | 7% TAX | 0
[5 empty] | TOTAL | 0
32.931 | Landscaping Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0

## DIV 33 UTILITES
33.000 | UTILITIES
33.02 | Sewer / Water Utilities
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
33.462 | Underground Buried Drainage
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0