## PROJECT SUMMARY
PROJECT COST SUMMARY
PROJECT | Ostronic Residence | [6 empty] | LOWER LEVEL | 1451
PROJECT MANAGER | [7 empty] | MAIN LEVEL | 2566
LOCATION | 1672 S 150th Avenue, Omaha, NE 68144 | [6 empty] | UPPER LEVEL | 1562
DATE | May 2026 | [6 empty] | TOTAL FINISHED SF | 5579
LOT # | Heartwood Lot 8 | [6 empty] | GARAGE | 1170
ZONING | [7 empty] | LOWER UNFINISHED | 1002
[8 empty] | COVERED DECK | 0
[8 empty] | TOTAL SF UNDER ROOF | 7751
PHASE | DESCRIPTION | ALLOW. | LABOR | MATERIAL | OTHER | SUBCONT. | DIVISION | FINISHED COST/SF | UNDER ROOF
1 | GENERAL REQUIREMENTS |  |  |  |  | TOTAL | 143788.375 | 25.7731 | 18.5509
01.120 | Superintendent | 0 | 61648.375 | 0 | 0 | 0 | 61648.375 | 11.0501 | 7.9536 | 61648
01.170 | Travel/Pickup/Deliveries | 0 | 1750 | 0 | 0 | 0 | 1750 | 0.31368 | 0.22578 | 1750
01.205 | MUD Fees | 0 | 0 | 0 | 2150 | 0 | 2150 | 0.38537 | 0.27738 | 2150
01.214 | Bldg. Permit | 0 | 0 | 0 | 12550 | 0 | 12550 | 2.2495 | 1.6191 | 14835
01.230 | Builders Risk | 0 | 0 | 0 | 3250 | 0 | 3250 | 0.58254 | 0.4193 | 3250
01.235 | General Liability | 0 | 0 | 0 | 6125 | 0 | 6125 | 1.0979 | 0.79022 | 6125
01.454 | Mockups | 0 | 550 | 250 | 0 | 0 | 800 | 0.14339 | 0.10321 | 800
01.501 | Temporary Utilities | 0 | 0 | 0 | 6500 | 0 | 6500 | 1.1651 | 0.8386 | 6500
01.538 | Technology | 0 | 0 | 0 | 1750 | 0 | 1750 | 0.31368 | 0.22578 | 1750
01.540 | Equipment (Forklift/Skid Loader) | 0 | 0 | 0 | 1500 | 0 | 1500 | 0.26887 | 0.19352 | 1500
01.560 | Temporary Barriers/Enclosures/Protection | 0 | 2250 | 1100 | 0 | 0 | 3350 | 0.60047 | 0.4322 | 3350
01.578 | Site Maintenance (Snow Removal/Mowing) | 0 | 1500 | 0 | 0 | 0 | 1500 | 0.26887 | 0.19352 | 1500
01.740 | Cleaning & Waste Management (Dumpsters) | 0 | 10175 | 0 | 8040 | 5750 | 23965 | 4.2956 | 3.0919 | 23965
01.810 | Warranties | 0 | 0 | 0 | 11700 | 0 | 11700 | 2.0972 | 1.5095 | 11700
01.830 | Small Tools/Supply/Rentals | 0 | 0 | 2000 | 0 | 0 | 2000 | 0.35849 | 0.25803 | 2000
01.840 | Punchlist | 0 | 3250 | 0 | 0 | 0 | 3250 | 0.58254 | 0.4193 | 3250
3 | CONCRETE |  |  |  |  | TOTAL | 91241 | 16.3544 | 11.7715
03.300 | Footings / Foundations | 0 | 0 | 0 | 0 | 62500 | 62500 | 11.2027 | 8.0635 | 65000
03.320 | Interior Concrete Flatwork | 0 | 0 | 0 | 0 | 28741 | 28741 | 5.1516 | 3.708 | 28741
4 | MASONRY |  |  |  |  | TOTAL | 70045 | 12.5551 | 9.0369
04.220 | Concrete Unit Masonry (Blockwork) | 0 | 0 | 800 | 0 | 3200 | 4000 | 0.71697 | 0.51606 | 4000
04.430 | Stone Masonry / Precast Sills & Caps | 0 | 0 | included | 0 | 66045 | 66045 | 11.8381 | 8.5208 | 73500
5 | METAL |  |  |  |  | TOTAL | 17264 | 3.0945 | 2.2273
05.120 | Structural Steel Material | 0 | 0 | 12500 | 0 | 0 | 12500 | 2.2405 | 1.6127 | 6000
05.530 | Exterior/Deck Railing | 0 | 0 | 0 | 0 | 4764 | 4764 | 0.85392 | 0.61463 | 6195
05.700 | Decorative Metal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | CARPENTRY |  |  |  |  | TOTAL | 509486 | 91.3221 | 65.7316
06.110 | Wood Framing | 0 | 4000 | 122885 | 0 | 122500 | 249385 | 44.7007 | 32.1746 | 236885
06.150 | Composite Decking (Timbertech Terrain) | 0 | 0 | 13892 | 0 | 6725 | 20617 | 3.6955 | 2.6599 | 20617
06.380 | Cabinetry Allowance (Signature360 & Classic360) | 127500 | 0 | 0 | 0 | 0 | 127500 | 22.8536 | 16.4495 | 166843
06.442 | Exterior Brackets/Timbers | 0 | 480 | 1900 | 0 | 0 | 2380 | 0.4266 | 0.30706 | 2380
06.460 | Wood Interior Trim & Stair Parts | 0 | 0 | 32000 | 0 | 41600 | 73600 | 13.1923 | 9.4955 | 73600
06.612 | Countertop Allowance | 36004 | 0 | 0 | 0 | 0 | 36004 | 6.4535 | 4.6451 | 48000
7 | MOISTURE/THERMAL PROT. |  |  |  |  | TOTAL | 127640 | 22.8787 | 16.4676
07.130 | Waterproofing/Passive Radon/Termite Treatment | 0 | 0 | 0 | 0 | 8600 | 8600 | 1.5415 | 1.1095 | 8600
07.210 | Insulation | 0 | 0 | 0 | 0 | 23545 | 23545 | 4.2203 | 3.0377 | 23545
07.300 | Roofing (Asphalt) & Metal Chimney Cap | 0 | 0 | 0 | 0 | 49375 | 49375 | 8.8502 | 6.3701 | 49375
07.455 | Siding | 0 | 0 | 16260 | 0 | 13550 | 29810 | 5.3433 | 3.846 | 29810
07.469 | Exterior Carsiding | 0 | 0 | 3510 | 0 | 3600 | 7110 | 1.2744 | 0.9173 | 7110
07.600 | Flashing/Brick Ledge | 0 | 600 | 1100 | 0 | 0 | 1700 | 0.30471 | 0.21933 | 1700
07.630 | Gutters/Downspouts | 0 | 0 | 0 | 0 | 3500 | 3500 | 0.62735 | 0.45155 | 6232
07.920 | Joint Sealants | 0 | 0 | 0 | 0 | 4000 | 4000 | 0.71697 | 0.51606 | 4000
8 | DOORS & WINDOWS |  |  |  |  | TOTAL | 144213 | 25.8493 | 18.6057
08.140 | Interior Wood Doors | 0 | 0 | 18636 | 0 | 0 | 18636 | 3.3404 | 2.4043 | 18636
08.141 | Hidden Office Door Allowance | 4000 | 0 | 0 | 0 | 0 | 4000 | 0.71697 | 0.51606 | 4000
08.178 | Front Door | 5500 | 960 | 0 | 0 | 0 | 6460 | 1.1579 | 0.83344 | 9500
08.385 | Garage Doors (Coachman) | 0 | 0 | 0 | 0 | 15500 | 15500 | 2.7783 | 1.9997 | 8500
08.500 | Windows (Lifestyle) | 0 | 0 | 0 | 0 | 82750 | 82750 | 14.8324 | 10.676 | 82750
08.817 | Mirrors/Pantry Door Glass/Shower Doors | 16867 | 0 | 0 | 0 | 0 | 16867 | 3.0233 | 2.1761 | 16867
9 | FINISHES |  |  |  |  | TOTAL | 202040 | 36.2144 | 26.0663
09.200 | Drywall (level 4 walls) | 0 |  | 0 | 1300 | 41225 | 42525 | 7.6223 | 5.4864 | 44500
09.300 | Tile Allowance
| Floor Tile | 25890 | 0 | 0 | 0 | 0 | 25890 | 4.6406 | 3.3402 | 25890
| Tile Backsplash (includes stone at LL Bar) | 6581 | 0 | 0 | 0 | 0 | 6581 | 1.1796 | 0.84905 | 6581
| Shower/Tub Tile | 16774 | 0 | 0 | 0 | 0 | 16774 | 3.0066 | 2.1641 | 16774
09.640 | Wood/LVP/LVT Flooring Allowance | 42536 | 0 | 0 | 0 | 0 | 42536 | 7.6243 | 5.4878 | 42536
09.657 | Rubber Athletic Flooring Allowance (Kinetex) | 2234 | 0 | 0 | 0 | 0 | 2234 | 0.40043 | 0.28822 | 2234
09.672 | Epoxy Flooring | OPTION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
09.680 | Carpet Allowance (stairs) | 2500 | 0 | 0 | 0 | 0 | 2500 | 0.44811 | 0.32254 | 2500
09.720 | Wall Coverings/Faux Finishing | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
09.910 | Painting | 0 | 0 | 0 | 0 | 63000 | 63000 | 11.2923 | 8.128 | 75000
10 | SPECIALTIES |  |  |  |  | TOTAL | 51571 | 9.2438 | 6.6535
10.050 | Finish Hardware Allowance | 8575 | 5000 | 0 | 0 | 0 | 13575 | 2.4332 | 1.7514 | 13575
10.140 | Address Numbers | 0 | 150 | 250 | 0 | 0 | 400 | 0.071697 | 0.051606 | 400
10.310 | Fireplaces (arched unit) | 0 | 0 | 0 | 0 | 9096 | 9096 | 1.6304 | 1.1735 | 7500
10.314 | Fireplace Facings Allowance | 8500 | 0 | 0 | 0 | 0 | 8500 | 1.5236 | 1.0966 | 8500
10.552 | Mailbox - community box | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.562 | Storage Shelving | OPTION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300
10.572 | Closet Systems Allowance | 20000 | 0 | 0 | 0 | 0 | 20000 | 3.5849 | 2.5803 | 25000
11 | EQUIPMENT |  |  |  |  | TOTAL | 39152.24 | 7.0178 | 5.0513
11.3 | Appliance Allowance (Frigidaire option) | 38432.24 | 720 | 0 | 0 | 0 | 39152.24 | 7.0178 | 5.0513 | 39152
11.52 | TV's Allowance | OPTION | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.678 | Game Room Equipment (Golf Simulator) | OPTION | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | FURNISHINGS |  |  |  |  | TOTAL | 0 | 0 | 0
12.170 | Art Glass | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.200 | Window Treatments | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.250 | Motorized Shades | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | SPECIAL CONSTRUCTION |  |  |  |  | TOTAL | 0 | 0 | 0
13.342 | Screen Porch System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22-23 | PLUMBING/HVAC SYSTEMS |  |  |  |  | TOTAL | 176340 | 31.6078 | 22.7506
22.050 | Plumbing | 0 | 0 | 0 | 0 | 60900 | 60900 | 10.9159 | 7.8571 | 62500
22.322 | Water Filtration System Allowance | 5000 | 0 | 0 | 0 | 0 | 5000 | 0.89622 | 0.64508 | 5000
22.400 | Plumbing Fixtures Allowance | 33615 | 0 | 0 | 0 | 0 | 33615 | 6.0253 | 4.3369 | 40150
23.050 | HVAC | 0 | 0 | 0 | 0 | 74325 | 74325 | 13.3223 | 9.5891 | 75800
23.400 | Duct Cleaning | 0 | 0 | 0 | 0 | 2500 | 2500 | 0.44811 | 0.32254 | 2500
26-28 | ELECTRICAL & LOW VOLTAGE |  |  |  |  | TOTAL | 107500 | 19.2687 | 13.8692
26.050 | Electrical Service & Wiring | 0 | 0 | 0 | 0 | 57500 | 57500 | 10.3065 | 7.4184 | 66100
26.505 | Light Fixtures Allowance | 20000 | 0 | 0 | 0 | 0 | 20000 | 3.5849 | 2.5803 | 22500
26.570 | Lighting Control System Allowance | OPTION | 0 | 0 | 0 | 0 | 0 | 0 | 0
27.410 | AV Systems Pre-Wire/Sound System Allowance | 20000 | 0 | 0 | 0 | 0 | 20000 | 3.5849 | 2.5803 | 20000
28.070 | Security System/Fire Protect./Video Surv. Allowance | 10000 | 0 | 0 | 0 | 0 | 10000 | 1.7924 | 1.2902 | 3500
31-32 | EARTHWORK & EXTERIOR IMPROVEMENTS |  |  |  |  | TOTAL | 66904 | 11.9921 | 8.6317
31.230 | Excavation/Fill/Grading/Silt Fence | 0 | 0 | 0 | 5000 | 25500 | 30500 | 5.4669 | 3.935 | 30500
31.260 | Surveying | 0 | 0 | 0 | 0 | 2500 | 2500 | 0.44811 | 0.32254 | 2500
32.130 | Exterior Concrete Flatwork | 0 | 0 | 0 | 0 | 33904 | 33904 | 6.0771 | 4.3741 | 33904
32.142 | Paver Allowance | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
32.300 | Landscape Lighting Allowance | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
32.310 | Fences/Gates | OPTION | 0 | 0 | 0 | 0 | 0 | 0 | 0
32.320 | Retaining Walls Allowance | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
32.800 | Irrigation Allowance | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
32.922 | Seeding/Sod Allowance | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
32.931 | Landscaping Allowance | by owner | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | UTILITIES |  |  |  |  | TOTAL | 10000 | 1.7924 | 1.2902
33.020 | Water/Sewer Utilities | 0 | 0 | 0 | 0 | 10000 | 10000 | 1.7924 | 1.2902 | 10000
33.462 | Underground Buried Drainage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | CONTIGENCY |  |  |  |  | TOTAL | 50000 | 8.9622 | 6.4508
50.050 | Contigency & other | 50000 | 0 | 0 | 0 | 0 | 50000 | 8.9622 | 6.4508 | 50000
50.070 | Arch/Engr Fees (Separate Agreement) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 500508.24 | 93033.375 | 227083 | 59865 | 926695 | 2078262.3073 | 372.5152 | 268.1283 | 2169883.25
91620.9427
McNeil Company Builders
PROJECT COST SUMMARY---MARKUP ANALYSIS
Project: | Ostronic Residence | [5 empty] | LOWER LEVEL | 1451
Location: | 1672 S 150th Avenue, Omaha, NE 68144 | [5 empty] | MAIN LEVEL | 2566
Date: | May 2026 | [5 empty] | UPPER LEVEL | 1562
Lot: | Heartwood Lot 8 | [5 empty] | TOTAL FINISHED SF | 5579
[7 empty] | GARAGE | 1170
[7 empty] | LOWER UNFINISHED | 1002
[7 empty] | COVERED DECK | 0
[7 empty] | TOTAL SF UNDER ROOF | 7751
MARKUP ADJUSTMENTS
ACTUAL COST
[6 empty] | Allowances |  | 500508.24
[6 empty] | Labor |  | 93033.375
[6 empty] | Material |  | 227083
[6 empty] | Other |  | 59865
[6 empty] | Subcontractor |  | 926695
[6 empty] | NO MARKUP TOTAL |  | 1807184.615
[6 empty] | MARKUP PERCENTAGE |  | 15%
[6 empty] | MARKUP |  | 271077.6922
[6 empty] | BID |  | 2078262.3073

## DIV 1 GC
01.000 | GENERAL CONDITIONS
1.12 | Superintendent
|  |  | PROJECT DURATION - MONTHS | APPROX. HOURS/DAY | HOURS/WEEK | RATE/HOUR | COST/WEEK | PROJECT DURATION - WEEKS | TOTAL
|  | minimal supervision at start 3 wks | 16.75 | 2 | 10 | 85 | 850 | 72.5275 | 61648.375
1.17 | Travel/Pickup/Deliveries
| Rates updated March 2026 | [6 empty] | TOTAL | 0
|  |  |  | Labor |  | 0 | 60 | HR | 0
1.205 | MUD Fees
| Rates updated March 2026 (based on Schachne) |  |  |  | TOTAL | 0
| 1" Capital Facilities Charge (Impact Fee) |  |  | 0 | 3200 | 0
| 1" Meter Install |  |  | 0 | 500 | 0
| Water Tap |  |  | 0 | 650 | 0
1.214 | Bldg. Permit
| Rates updated March 2026 | [6 empty] | TOTAL | 0
City of Omaha
https://permits.cityofomaha.org/fees
| $1.00-$2,000 |  | 41 |  |  |  | 0 | 41 | 0
| $2,000-$25,000 |  | $41.00 for first $2,000, plus $9.53 for each additional $1,000 |  |  |  | 0 | 41 | 0
[7 empty] | 0 | 9.53 | 0
| $25,001-$50,000 |  | $260.19 for first $25,000, plus $6.44 for each additional $1,000 |  |  |  | 0 | 260.19 | 0
[7 empty] | 0 | 6.44 | 0
| $50,001-$100,000 |  | $421.19 for first $50,000, plus $3.19 for each additional $1,000 |  |  |  | 0 | 421.19 | 0
[7 empty] | 0 | 3.19 | 0
| $100,001-$500,000 |  | $580.69 for first $100,000, plus $2.78 for each additional $1,000 |  |  |  | 0 | 580.69 | 0
[7 empty] | 0 | 2.78 | 0
| $500,001-$1,000,000 |  | $1,692.69 for first $500,000, plus $2.37 for each additional $1,000 |  |  |  | 0 | 1692.69 | 0
[7 empty] | 0 | 2.37 | 0
| $1,000,001 and up |  | $2877.69 for first $1,000,000, plus $1.96 for each additional $1,000 |  |  |  | 0 | 1000000 | 0
[7 empty] | 0 | 1.96 | 0
City of Blair
https://www.blairne.gov/DocumentCenter/View/52/Building-Permit-and-Zoning-Fees-PDF
| Finished SF (not including finished basement) |  |  | 0 | * | 102 | 0
| Finished Basement SF |  |  | 0 | * | 62 | 0
| Unfinished Basement SF |  |  | 0 | * | 32 | 0
| Garage SF |  |  | 0 | * | 30 | 0
0
[6 empty] | Multiply by .006 | 0.006
[6 empty] | Total | 0
1.23 | Builders Risk
[8 empty] | TOTAL | 0
| Builders Risk (0.144/100 cost) |  |  |  |  | 0 | 0.144 |  | 0
| Misc. |  |  |  |  | 0 |  |  | 0
1.235 | General Liability
[8 empty] | TOTAL | 0
| Liability (2.77/1000 cost) |  |  |  |  | 0 | 2.77 |  | 0
| Bond |  |  |  |  | 0 |  |  | 0
| Misc. |  |  |  |  | 0 |  |  | 0
1.452 | Testing/Inspections
[8 empty] | TOTAL | 0
| Soil Testing |  |  |  |  | 0 | 1500 |  | 0
| Call back after excavation for visual inspection |  |  |  |  | 0 | 200 |  | 0
1.454 | Mockups
[8 empty] | TOTAL | 0
|  |  |  | Labor |  | 0 | 60 | HR | 0
|  |  |  | Materials |  | 0 | 350 | EA | 0
1.501 | Temporary Utilities
| Rates updated March 2026 | [6 empty] | TOTAL | 0
| Temp Power Service |  | OPPD |  |  | 0 | 150 | /MONTH | 0
| Temp Gas / Water Service |  | MUD |  |  | 0 | 250 | /MONTH | 0
| Temp Heat for Interior |  | Labor / Material |  |  | 0 | 200 | ALLOWANCE | 0
| Temp Heat for Exterior |  | Labor / Material |  |  | 0 | 200 | ALLOWANCE | 0
| Portable Toilet |  | Eagle Services |  | Monthly Charge (includes tax) | 0 | 128.4 | /MONTH | 0
[5 empty] | Delivery & Pickup (inlcudes tax) | 0 | 21.4 | /MONTH | 0
1.538 | Technology
| Rates updated March 2026 | [6 empty] | TOTAL | 0
[5 empty] | Equipment | 0 | 1200 | /JOB | 0
1.54 | Equipment (Forklift/Skid Loader)
| Rates updated March 2026 | [6 empty] | TOTAL | 0
[5 empty] | Equipment | 0 | 1750 | /JOB | 0
1.56 | Temporary Barries/Enclosures
| Rates updated March 2026 | [6 empty] | TOTAL | 0
|  |  |  | Material |  | 0 | 750 | EA | 0
|  |  |  | Labor | (2 guys at $60/hr) | 0 | 120 | HR | 0
|  |  |  | Subcontract |  | 0 | 4500 | EA | 0
1.578 | Site Maintenance
| Rates updated March 2026 | [6 empty] | TOTAL | 0
| Snow Removal |  |  | Labor |  | 0 | 60 | HR | 0
| Mowing/Spraying/Weedeating |  |  | Labor |  | 0 | 60 | HR | 0
1.74 | Cleaning & Waste Management
| Rates updated March 2026 | [6 empty] | TOTAL | 18215
| assume 17 mo x 4.33weeks/mo |  | 74 weeks |  | 74 | 2.5
|  |  | Interim Clean | Labor | 2.5 hrs/week | 185 | 55 | HR | 10175
|  |  | Final Clean | Labor |  | 0 | 55 | HR | 0
|  |  | Final Clean | Subcontract |  | 0 | 0.9 | EA | 0
|  |  | Window Clean | Subcontract | 2-story | 0 | 1200 | EA | 0
|  |  | Window Clean | Subcontract | Ranch | 0 | 750 | EA | 0
|  |  | Dumpsters | Other | S2 | 24 | 335 | each | 8040
Excludes drywall in phase - new dumpster every 3 weeks approx
1.81 | Warranties
| Warranty Historical |  |  | Own | McNeil | 1950000 | 0.006 | /TOTAL/COST | 11700
1.83 | Small Tools/Supply/Rent
| Rates updated March 2026 | [6 empty] | TOTAL | 0
[5 empty] | Tools/Supplies | 0 | 400 | /JOB | 0
[5 empty] | Floor Sander | 0 | 120 | /JOB | 0
[5 empty] | Other Equipment | 0 | 250 | /JOB | 0
1.84 | Punchlist
| Rates updated March 2026 | [6 empty] | TOTAL | 0
[5 empty] | Labor | 0 | 1200 | /JOB | 0

## DIV 2 EXIST. COND.
02.000 | EXISTING CONDITIONS
2.01 | Demolition
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 3 CONCRETE
03.000 | CONCRETE
3.3 | Footings/Foundations
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
3.32 | Interior Concrete Flatwork
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
Unit Rate Estimate - rates updated March of 2026
Lower Level Slab |  | 0 | sf
Garage Slab |  | 0 | sf
|  | 0 | sf
MATERIAL
Poly (LL & GARAGE SLAB SF x 1.15 = sf) |  |  |  | 0 | 0.075 | SF | 0
Lower Level Slab Granular (LL SF x .33ft x 1.25 / 18 = tons) |  |  |  | 0 | 22 | TON | 0
Garage Slab Granular (GARAGE SF x .33ft x 1.25 / 18 = tons) |  |  |  | 0 | 22 | TON | 0
Additive (Xypex for water impermeable) |  |  |  | 0 | 131.85 | BOX | 0
Expansion Joints at Walls |  |  | ls | 0 | 125 | EA | 0
SUBCONTRACTOR
Lower Level Slab |  |  |  | 0 | 6.75 | SF | 0
Poly install |  |  |  | 0 | 0.35 | SF | 0
Step Down (form charge) |  |  |  | 0 | 10 | LF | 0
Garage Slab |  |  |  | 0 | 6.75 | SF | 0
Saw Cut slabs |  |  |  | 0 | 0.05 | SF | 0
Grading |  |  |  | 0 | 0.25 | SF | 0
Pump charge |  |  |  | 0 | 1700 | EA | 0
Cure & Seal |  |  |  | 0 | 0.12 | SF | 0
[6 empty] | TOTAL | 0

## DIV 4 MASONRY
04.000 | MASONRY
4.21 | Brick / Precast Sills & Caps
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
Unit Rate Estimate - rates updated March of 2026
Brick (Modular) |  | 0 | SF | 7 | 0 | brick ea
Soldiers/Rowblocks |  | 0 | LF | 3.5 | 0 | brick ea
Approx. per 292lf |  |  |  | RAW QTY BRICK | 0 | brick ea
|  |  |  | 12% WASTE FACTOR | 0 | brick ea
|  |  |  | TOTAL | 0 | brick ea
*adjust brick/cube quantity based on brick size |  |  |  | Qty of Full Cubes | 525 | brick/cube
|  |  |  | TOTAL | 0 | total cubes
Per Laura at Watkins:
125 brick/bag of masonry for this product
premix mortar - 35-40 brick/bag on modular / 30-32 brick per bag oversize
MATERIAL
Brick (modular) |  |  |  | 0 | 0.95 | 0
Brick (solids) |  |  |  | 0 | 1.5 | 0
premix mortar (colored) |  |  |  | 0 | 14.45 | 0
premix mortar (standard gray) |  |  |  | 0 | 9.5 | 0
Masonry Cement |  | 7 bags/M |  | 0 | 11 | 0
Portland Cement |  | 1 bag/5 of masonry |  | 0 | 14 | 0
Sand |  | 3 to 1 by weight |  | 0 | 15 | 0
Weep Holes |  | approx. every 3lf |  | 0 | 0.65 | 0
Nervastral |  | 12"x150'/roll |  | 0 | 90 | 0
SureKlean #600 detergent |  | 600sf/gallon |  | 0 | 25 | 0
Ties |  | .10 ties per brick |  | 0 | 0.35 | 0
1" Mortar Net |  |  |  | 0 | 2.4 | 0
Misc. Tools |  |  |  | 0 | 200 | 0
Pallet charge |  |  |  | 0 | 28 | 0
freight/delivery |  |  |  | 0 | 75 | 0
[5 empty] | SUBTOTAL | 0
[5 empty] | 7% TAX | 0
[5 empty] | TOTAL | 0
4.22 | Concrete Masonry Units (Blockwork)
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
4.43 | Stone Masonry / Precast Sills & Caps
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
Unit Rate Estimate - rates updated March of 2026
Thin Stone Flats |  | 0 | SF | 12% waste factor | 0 | stone sf
Thin Stone Corners |  | 0 | LF | 12% waste factor | 0 | stone sf
Approx. per 292lf |  |  |  | TOTAL | 0 | stone sf
Full Bed Depth Stone |  | 0 | SF | 12% waste factor | 0 | stone sf
Approx. per 292lf |  |  |  | TOTAL | 0 | stone sf
|  |  |  | Approximate ton qty | 38 | sf/ton
|  |  |  | TOTAL | 0 | tons
per Laura at Watkins:
thin stone mortar coverage - Promix 70lb bag is 15sf/bag for joints; 7sf/bag for scratch coat
full bed depth stone mortar coverage - depends on stone size, but 7-10sf/bag gets close
german schmear style mortar coverage - depends on heaviness of schmear
approximate sf/ton for full bed depth stone - 38-40sf/ton
MATERIAL
Thin Stone Flats |  | $/sf |  | 0 | 12 | 0
Thin Stone Corners |  | $/each |  | 0 | 18 | 0
Full Bed Depth Stone |  | $/ton |  | 0 | 500 | 0
Premix Mortar (colored) |  |  |  | 0 | 14.45 | 0
Premix Mortar (standard gray) |  |  |  | 0 | 13.8 | 0
Scratch coat mortar |  |  |  | 0 | 13.8 | 0
Metal Lathe |  | 27"x96", assume 16sf with overlap |  | 0 | 14.1 | 0
Felt |  | 200sf/roll |  | 0 | 35 | 0
Lathe Bottom Weep Screed |  | assume 10' |  | 0 | 17 | 0
Rainscreen, Keene |  | 4'x65' |  | 0 | 10 | 0
Masonry Cement |  | 7 bags/M |  | 0 | 11 | 0
Portland Cement |  | 1 bag/5 of masonry |  | 0 | 14 | 0
Sand |  | 3 to 1 by weight |  | 0 | 15 | 0
Weep Holes |  | approx. every 3lf |  | 0 | 0.65 | 0
Nervastral |  | 12"x150'/roll |  | 0 | 90 | 0
SureKlean #600 detergent |  | 600sf/gallon |  | 0 | 25 | 0
Ties |  | .10 ties per brick |  | 0 | 0.35 | 0
1" Mortar Net |  |  |  | 0 | 2.4 | 0
Misc. Tools |  |  |  | 0 | 200 | 0
Pallet charge |  | approx. 150-200sf/pallet |  | 0 | 28 | 0
freight/delivery |  |  |  | 0 | 75 | 0
[5 empty] | SUBTOTAL | 0
[5 empty] | 7% TAX | 0
[5 empty] | TOTAL | 0

## DIV 5 METAL
05.000 | METAL
5.12 | Strucutural Steel - Material
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
5.528 | Metal Interior Railing
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
5.53 | Exterior Deck Railing
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
5.7 | Decorative Metal
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 6 CARPENTRY
06.000 | CARPENTRY
6.11 | Wood Framing
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
6.15 | Wood Decks
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
6.38 | Cabinetry
|  |  |  | Company | Company | Company | Company
Main Level
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
Lower Level
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
Upper Level
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
6.442 | Exterior Brackets/Timbers
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
6.46 | Wood Interior Trim
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
Unit Rate Estimate
| DESCRIPTION |  | SPECIES | QTY | UNIT PRICE | SUBTOTAL | NOTES
BASE AND CASING
| 3" Casing |  |  | 0 | 0 | 0
| 3 1/2" Casing |  |  | 0 | 0 | 0
| 4" Casing |  |  | 0 | 0 | 0
| 3" Base (Mechanical Rooms) |  |  | 0 | 0 | 0
| 4" Base |  |  | 0 | 0 | 0
| 6" Base |  |  | 0 | 0 | 0
| 8" Base |  |  | 0 | 0 | 0
| PVC Base - Azek (Garage) |  |  | 0 | 0 | 0
| Base Shoe |  |  | 0 | 0 | 0
| Window Jamb Extensions |  |  | 0 | 0 | 0
| Tooling/Setup Charge |  |  | 0 | 500 | 0
CASING DETAILS
| 1 1/2" bn |  |  | 0 | 0 | 0
| 1 x 6 S4S (for jamb) |  |  | 0 | 0 | 0
| stop |  |  | 0 | 0 | 0
| glass mullion (to match door profile) |  |  | 0 | 0 | 0
| backband (for front door) |  |  | 0 | 0 | 0
| Mullcenter (double door) |  |  | 0 | 0 | 0
| 1 x 4 S4S window stools |  |  | 0 | 0 | 0
| set up/freight for glass mullions |  |  | 0 | 0 | 0
CROWN MOLDING
| 6" CROWN |  |  | 0 | 0 | 0
| Built-Up Band |  |  | 0 | 0 | 0
| 1 x 4 S4S (backing material) |  |  | 0 | 0 | 0
BEAMS
| Industrial Board (structure) |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
DETAIL
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
DETAIL
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
DETAIL
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
STAIR PARTS
| Newel Posts |  |  | 0 | 0 | 0
| Wood Railing |  |  | 0 | 0 | 0
| Balusters |  |  | 0 | 0 | 0
| 1x12 skirt boards |  |  | 0 | 0 | 0
| 4" casing skirt board cap |  |  | 0 | 0 | 0
| 1/2x12 End Cap Treads |  |  | 0 | 0 | 0
| 1/2x8 End Cap Risers |  |  | 0 | 0 | 0
| Planing Charge |  |  | 0 | 0 | 0
| End Cap & Balcony Nosing |  |  | 0 | 0 | 0
MISC. TRIM DETAILS
| Glue, shims, fasteners, blades |  |  | 0 | 750 | 0
| Delivery |  |  | 0 | 150 | 0
[5 empty] | subtotal | 0
[5 empty] | 7% tax | 0
[5 empty] | TOTAL | 0
6.612 | Countertop Allowance
|  |  |  | Company | Company | Company | Company
Main Level
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
Lower Level
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
Upper Level
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
| Location | ALLOWANCE | *MATERIAL
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0

## DIV 7 MOISTURE PROTECTION
07.000 | MOISTURE/THERMAL PROTECTION
7.13 | Waterproofing/Passive Radon/Termite Treatment
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.21 | Insulation
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.25 | Stucco System
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.3 | Roofing
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.455 | Siding
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.469 | Exterior Carsiding
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.6 | Flashing/Brickledge
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.63 | Gutters/Downspouts
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
7.92 | Joint Sealants
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 8 OPENINGS
08.000 | OPENINGS
8.14 | Interior Wood Doors
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.178 | Front Door
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.184 | Pet Door
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.385 | Garage Doors
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.5 | Windows
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.6 | Roof Windows/Skylights/Sun Tunnel
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
8.817 | Mirrors/Glass Inserts/Shower Doors
|  |  |  | Company | Company | Company | Company
Main Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
Lower Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
Upper Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
1
2
3
4
5
6
7
8
9 | Install
10 | McNeil Company Wood Backer Supply/Install
|  |  | TOTAL | 0 | 0 | 0 | 0

## DIV 9 FINISHES
09.000 | FINISHES
9.2 | Drywall
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
9.3 | Tile
Floor Tile
[8 empty] | TOTAL | 0
| Location | [7 empty] | 0
|  |  |  | Tile Material | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 75 | EA | 0
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Self Leveling | ALLOWANCE | 0 | 5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Tile Material | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 75 | EA | 0
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Self Leveling | ALLOWANCE | 0 | 5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Tile Material | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 75 | EA | 0
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Self Leveling | ALLOWANCE | 0 | 5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Tile Material | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 75 | EA | 0
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Self Leveling | ALLOWANCE | 0 | 5 | SF | 0
|  |  |  | In-Floor Heat | ALLOWANCE | 0 | 20 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Tile Material | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 75 | EA | 0
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Anti-fracture Membrane | ALLOWANCE | 0 | 2 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Tile Material | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 75 | EA | 0
|  |  |  | Sealer | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Anti-fracture Membrane | ALLOWANCE | 0 | 2 | SF | 0
Tile Backsplash
[8 empty] | TOTAL | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Deco | ALLOWANCE | 0 | 275 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 32 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 50 | EA | 0
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Deco | ALLOWANCE | 0 | 275 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 32 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 50 | EA | 0
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Deco | ALLOWANCE | 0 | 275 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 32 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 50 | EA | 0
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Deco | ALLOWANCE | 0 | 275 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 32 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 50 | EA | 0
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Deco | ALLOWANCE | 0 | 275 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 32 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 50 | EA | 0
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
Wall Tile/Columns
[8 empty] | TOTAL | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 35 | SF | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 32 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 50 | EA | 0
|  |  |  | Sealer / Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
Shower/Tub Tile
[8 empty] | TOTAL | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 12 | SF | 0
|  |  |  | Deco Tile | ALLOWANCE | 0 | 400 | EA | 0
|  |  |  | Ceiling Tile | ALLOWANCE | 0 | 12 | SF | 0
|  |  |  | Floor Tile | ALLOWANCE | 0 | 20 | SF | 0
|  |  |  | Bullnose | ALLOWANCE | 0 | 15 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Miter Outside Corners - Addt'l Cost | ALLOWANCE | 0 | 300 | EA | 0
|  |  |  | Labor - install seat, shelves, jamb and/or curb | ALLOWANCE | 0 | 1000 | EA | 0
|  |  |  | Labor - floor | ALLOWANCE | 0 | 85 | SF | 0
|  |  |  | Tile Drain | ALLOWANCE | 0 | 150 | EA | 0
|  |  |  | Sealer/Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 100 | EA | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Deco Tile | ALLOWANCE | 0 | 400 | EA | 0
|  |  |  | Ceiling Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Floor Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Bullnose | ALLOWANCE | 0 | 15 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Labor - install shelves, curb | ALLOWANCE | 0 | 1000 | EA | 0
|  |  |  | Labor - floor | ALLOWANCE | 0 | 85 | SF | 0
|  |  |  | Tile Drain | ALLOWANCE | 0 | 150 | EA | 0
|  |  |  | Sealer/Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 100 | EA | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Deco Tile | ALLOWANCE | 0 | 400 | EA | 0
|  |  |  | Ceiling Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Floor Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Bullnose | ALLOWANCE | 0 | 15 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Labor - install shelves, curb | ALLOWANCE | 0 | 1000 | EA | 0
|  |  |  | Labor - floor | ALLOWANCE | 0 | 85 | SF | 0
|  |  |  | Tile Drain | ALLOWANCE | 0 | 150 | EA | 0
|  |  |  | Sealer/Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 100 | EA | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Deco Tile | ALLOWANCE | 0 | 400 | EA | 0
|  |  |  | Ceiling Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Floor Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Bullnose | ALLOWANCE | 0 | 15 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Labor - install shelves, curb | ALLOWANCE | 0 | 1000 | EA | 0
|  |  |  | Labor - floor | ALLOWANCE | 0 | 85 | SF | 0
|  |  |  | Tile Drain | ALLOWANCE | 0 | 150 | EA | 0
|  |  |  | Sealer/Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 100 | EA | 0
| Location | [7 empty] | 0
|  |  |  | Field Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Deco Tile | ALLOWANCE | 0 | 400 | EA | 0
|  |  |  | Ceiling Tile | ALLOWANCE | 0 | 8 | SF | 0
|  |  |  | Floor Tile | ALLOWANCE | 0 | 15 | SF | 0
|  |  |  | Bullnose | ALLOWANCE | 0 | 15 | EA | 0
|  |  |  | Labor/Setting Materials | ALLOWANCE | 0 | 21 | SF | 0
|  |  |  | Labor - install shelves, curb | ALLOWANCE | 0 | 1000 | EA | 0
|  |  |  | Labor - floor | ALLOWANCE | 0 | 85 | SF | 0
|  |  |  | Tile Drain | ALLOWANCE | 0 | 150 | EA | 0
|  |  |  | Sealer/Caulk | ALLOWANCE | 0 | 1.5 | SF | 0
|  |  |  | Delivery | ALLOWANCE | 0 | 100 | EA | 0
9.64 | Wood Flooring / LVP / LVT Allowance
| WOOD FLOOR / LVP / LVT AREAS | [5 empty] | TOTAL | 0
| Main Level | 0 | SF
| Lower Level | 0 | SF
| Upper Level | 0 | SF
| Subtotal | 0 | SF
| 7% waste - typical | 0 | SF
| 15% waste - diagonal/herringbone | 0 | SF
| Total | 0 | SF
| Prefin. wood materials (range from $5.50-$12) |  |  | ALLOWANCE | 0 | 0 | SF | 0
| Wood Installation Labor |  |  | ALLOWANCE | 0 | 0 | SF | 0
| Wood Stair Labor |  |  | ALLOWANCE | 0 | 25 | EA | 0
| Wood Vents (Flush Mount) |  |  | ALLOWANCE | 0 | 122 | EA | 0
| Miscellanous Underlayment/Floor Prep |  |  | ALLOWANCE | 0 | 3 | SF | 0
| LVP / LVT materials |  |  | ALLOWANCE | 0 | 0 | SF | 0
| LVP / LVT Installation Labor |  |  | ALLOWANCE | 0 | 0 | SF | 0
| LVP / LVT Prep / Glue / Transitions |  |  | ALLOWANCE | 0 | 0 | SF | 0
NOTES:
per Timberland - use $10/sf allowance for prefinished wood
9.657 | Rubber Athletic Flooring Allowance
| AREAS | [5 empty] | TOTAL | 0
| Main Level | 0 | SF
| Lower Level | 0 | SF
| Upper Level | 0 | SF
| Subtotal | 0 | SF
| 7% waste | 0 | SF
| Total | 0 | SF
| Carpet Tile/Rubber Flooring Material |  |  | ALLOWANCE | 0 | 0 | SF | 0
| Installation Labor |  |  | ALLOWANCE | 0 | 0 | SF | 0
9.672 | Epoxy Flooring
| AREAS | [5 empty] | TOTAL | 0
| Garage | 0 | SF
| Mechanical/Storage | 0 | SF
| Mechanical/Storage | 0 | SF
| Subtotal | 0 | SF
| 7% waste | 0 | SF
| Total | 0 | SF
| Epoxy Flooring Material / Installation |  |  | ALLOWANCE | 0 | 6 | SF | 0
9.68 | Carpet Allowance
| AREAS |  |  |  |  | TOTAL | 0
| Main Level | 0 | SF
| Lower Level | 0 | SF
| Upper Level | 0 | SF
| Stairs (x2 for risers) | 0 | SF
| Total SF | 0 | SF
| Conversion to SY (X 1.30 / 9) | 0 | SY
| 12' Roll Layout - Actual | 0 | SY
ALLOWANCE BREAKDOWN
| Installation Labor |  |  |  | 8 | PER SY
| Carpet Pad (memory foam) |  |  |  | 8 | PER SY
| Material Allowance |  |  |  | 40 | PER SY
| Floor Prep / Tack Strip / Etc. |  |  |  | 1.5 | PER SY
| Carpet Material, Labor, and Pad |  | ALLOWANCE | 0 | 57.5 | SY | 0
| Walk Off Carpet |  | ALLOWANCE | 0 | 50 | SY | 0
| VCT (furnace room) |  | ALLOWANCE | 0 | 3 | SF | 0
| Additional Labor for Stair |  | ALLOWANCE | 0 | 30 | EA | 0
9.72 | Wall Coverings/Faux Finishing
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
9.91 | Painting
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0

## DIV 10 SPECIALTIES
10.000 | SPECIALTIES
10.05 | Finish Hardware Allowance
Cabinet Hardware
| POWDER BATH |  | DOORS/DRAWERS |  | 0 | 10 | 0
| SERVICE ENTRY |  | DOORS/DRAWERS |  | 0 | 10 | 0
|  |  | HOOKS |  | 0 | 10 | 0
| PRIMARY BATH |  | DOORS/DRAWERS |  | 0 | 10 | 0
| PRIMARY WARDROBE |  | DOORS/DRAWERS |  | 0 | 10 | 0
| GREAT ROOM |  | DOORS/DRAWERS |  | 0 | 10 | 0
| KITCHEN ISLAND |  | DOORS/DRAWERS |  | 0 | 10 | 0
| KITCHEN |  | DOORS/DRAWERS |  | 0 | 10 | 0
|  |  | APPLIANCE PULLS |  | 0 | 350 | 0
| PANTRY |  | DOORS/DRAWERS |  | 0 | 10 | 0
| LAUNDRY |  | DOORS/DRAWERS |  | 0 | 10 | 0
| BATHROOM |  | DOORS/DRAWERS |  | 0 | 10 | 0
| BATHROOM |  | DOORS/DRAWERS |  | 0 | 10 | 0
| BATHROOM |  | DOORS/DRAWERS |  | 0 | 10 | 0
| BAR |  | DOORS/DRAWERS |  | 0 | 10 | 0
| GARAGE |  | DOORS/DRAWERS |  | 0 | 10 | 0
| OUTDOOR |  | DOORS/DRAWERS |  | 0 | 10 | 0
[6 empty] | SUBTOTAL | 0
[6 empty] | FREIGHT | 100
[6 empty] | 7% TAX | 7
[6 empty] | TOTAL | 107
Door Hardware
| LOCATION |  |  |  | QTY | UNIT COST | SUBTOTAL
Lower Level
| DOOR LEVERS (PASSAGE/PRIVACY) |  |  | Schlage Custom | 0 | 95 | 0
| DUMMIES |  |  | Schlage Custom | 0 | 445 | 0
| POCKET DOOR |  |  | Emtek | 0 | 275 | 0
| 3 1/2" HINGES - per pair |  |  |  | 0 | 14 | 0
| 4" HINGES - per pair |  |  |  | 0 | 18 | 0
| HINGE DOOR STOP |  |  |  | 0 | 10 | 0
| BASE DOOR STOP |  |  |  | 0 | 15 | 0
Main Level
| FRONT DOOR HARDWARE |  |  |  | 0 | 600 | 0
| PATIO - MULTIPOINT |  |  | Emtek | 0 | 575 | 0
| DOOR LEVERS (PASSAGE/PRIVACY) |  |  | Emtek | 0 | 187 | 0
| DEADBOLTS (AT GARAGE) |  |  | Emtek | 0 | 100 | 0
| DUMMIES |  |  | Emtek | 0 | 187 | 0
| POCKET DOOR |  |  | Emtek | 0 | 275 | 0
| BARN DOORS |  |  |  | 0 | 325 | 0
| BI-FOLD KNOBS |  |  |  | 0 | 25 | 0
| 3 1/2" HINGES - per pair |  |  |  | 0 | 14 | 0
| 4" HINGES - per pair |  |  |  | 0 | 50 | 0
| SPRING HINGE |  |  |  | 0 | 85.6 | 0
| HINGE DOOR STOP |  |  |  | 0 | 10 | 0
| BASE DOOR STOP |  |  |  | 0 | 15 | 0
| FLOOR STOP |  |  |  | 0 | 50 | 0
Upper Level
| DOOR LEVERS (PASSAGE/PRIVACY) |  |  |  | 0 | 95 | 0
| DUMMIES |  |  | Schlage Custom | 0 | 445 | 0
| POCKET DOOR |  |  | Emtek | 0 | 275 | 0
| 3 1/2" HINGES - per pair |  |  |  | 0 | 14 | 0
| 4" HINGES - per pair |  |  |  | 0 | 18 | 0
| HINGE DOOR STOP |  |  |  | 0 | 10 | 0
| BASE DOOR STOP |  |  |  | 0 | 15 | 0
[6 empty] | SUBTOTAL | 0
[6 empty] | FREIGHT | 100
[6 empty] | 7% TAX | 7
[6 empty] | TOTAL | 107
Bath Accessories
POWDER BATH
|  |  | TOILET PAPER HOLDERS |  | 0 | 75 | 0
|  |  | TOWEL RINGS |  | 0 | 75 | 0
PRIMARY BATH
|  |  | TOILET PAPER HOLDERS |  | 0 | 75 | 0
|  |  | TOWEL BARS |  | 0 | 100 | 0
|  |  | TOWEL RINGS |  | 0 | 75 | 0
|  |  | ROBE HOOKS |  | 0 | 35 | 0
BATHROOM
|  |  | TOILET PAPER HOLDERS |  | 0 | 75 | 0
|  |  | TOWEL BAR |  | 0 | 100 | 0
|  |  | TOWEL RINGS |  | 0 | 75 | 0
|  |  | ROBE HOOKS |  | 0 | 35 | 0
BATHROOM
|  |  | TOILET PAPER HOLDERS |  | 0 | 75 | 0
|  |  | TOWEL BARS |  | 0 | 100 | 0
|  |  | TOWEL RINGS |  | 0 | 75 | 0
|  |  | ROBE HOOKS |  | 0 | 35 | 0
BATHROOM
|  |  | TOILET PAPER HOLDERS |  | 0 | 75 | 0
|  |  | TOWEL BARS |  | 0 | 100 | 0
|  |  | TOWEL RINGS |  | 0 | 75 | 0
|  |  | ROBE HOOKS |  | 0 | 35 | 0
[6 empty] | SUBTOTAL | 0
[6 empty] | FREIGHT | 100
[6 empty] | 7% TAX | 7
[6 empty] | TOTAL | 107
[6 empty] | TOTAL ALL ACCESSORIES | 321
[6 empty] | TOTAL LABOR | 0
10.14 | Address Numbers
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
10.31 | Fireplaces
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
10.314 | Fireplace Facings
[6 empty] | TOTAL | 0
Location | [6 empty] | 0
|  | Field Material | ALLOWANCE | 0 | 0 | SF | 0
|  | Labor/Setting Materials | ALLOWANCE | 0 | 0 | SF | 0
|  | Delivery | ALLOWANCE | 0 | 0 | EA | 0
|  | Sealer | ALLOWANCE | 0 | 0 | SF | 0
|  | Precast Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Metal Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Labor - Surround | ALLOWANCE | 0 | 0 | EA | 0
Location | [6 empty] | 0
|  | Field Material | ALLOWANCE | 0 | 0 | SF | 0
|  | Labor/Setting Materials | ALLOWANCE | 0 | 0 | SF | 0
|  | Delivery | ALLOWANCE | 0 | 0 | EA | 0
|  | Sealer | ALLOWANCE | 0 | 0 | SF | 0
|  | Precast Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Metal Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Labor - Surround | ALLOWANCE | 0 | 0 | EA | 0
Location | [6 empty] | 0
|  | Field Material | ALLOWANCE | 0 | 0 | SF | 0
|  | Labor/Setting Materials | ALLOWANCE | 0 | 0 | SF | 0
|  | Delivery | ALLOWANCE | 0 | 0 | EA | 0
|  | Sealer | ALLOWANCE | 0 | 0 | SF | 0
|  | Precast Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Metal Surround | ALLOWANCE | 0 | 0 | EA | 0
|  | Labor - Surround | ALLOWANCE | 0 | 0 | EA | 0
10.562 | Storage Shelving
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
10.566 | Wine Cellar Racks/Cooling
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
10.572 | Closets
|  |  |  | Company | Company | Company | Company
Main Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
Lower Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
Upper Level
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
| Location | ALLOWANCE | TYPE
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
10.712 | Exterior Shutters
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0

## DIV 11 EQUIPMENT
11.000 | EQUIPMENT
11.302 | Appliances Allowance
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
11.52 | TV's Allowance
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
11.66 | Athletic Equipment
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
11.678 | Game Room Equipment (Golf Simulator)
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 12 FURNISHINGS
12.000 | FURNISHINGS
12.17 | Art Glass
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
12.2 | Window Treatments
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
12.25 | Motorized Shades
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 13 SPECIAL CONST.
13.000 | SPECIAL CONSTRUCTION
13.112 | Swimming Pool
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
13.174 | Sauna
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
13.26 | Storm Shelter Room(s)
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
13.342 | Screen Porch Systems
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 14 CONVEYING SYSTEMS
14.000 | CONVEYING SYSTEMS
14.05 | Elevators
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 21 FIRE SUPRESSION
21.000 | FIRE SUPPRESSION
21.05 | Fire Suppression
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 22-23 PLUM-HVAC
22.000 | PLUMBING
22.05 | Plumbing
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
22.322 | Water Filtration System
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
22.4 | Plumbing Fixtures Allowance
|  | QUANITITY | UNIT COST | SUBTOTAL
BATHROOM
| SINK SS | 0 | 100 | 0
| FAUCET | 0 | 250 | 0
| TOILET | 0 | 400 | 0
| SEAT/TRIP LEVER | 0 | 115 | 0
| SHOWER VALVE/TRIM | 0 | 450 | 0
| FIBERGLASS SHOWER BASE | 0 | 650 | 0
BAR
| SINK | 0 | 450 | 0
| FAUCET | 0 | 475 | 0
| RO FAUCET | 0 | 400 | 0
| AIR SWITCH | 0 | 125 | 0
| DISPOSAL | 0 | 175 | 0
| BASKET STRAINER | 0 | 70 | 0
KITCHEN
| SINK | 0 | 800 | 0
| FAUCET | 0 | 500 | 0
| RO FAUCET | 0 | 400 | 0
| SOAP DISPENSER | 0 | 150 | 0
| AIR SWITCH | 0 | 125 | 0
| DISPOSAL | 0 | 300 | 0
| BASKET STRAINER | 0 | 70 | 0
| POT FILLER | 0 | 700 | 0
POWDER BATH
| SINK | 0 | 175 | 0
| FAUCET | 0 | 400 | 0
| TOILET | 0 | 400 | 0
| SEAT/TRIP LEVER | 0 | 115 | 0
LAUNDRY
| SINK | 0 | 225 | 0
| FAUCET | 0 | 200 | 0
| BASKET STRAINER | 0 | 70 | 0
PRIMARY BATH
| SINK | 0 | 150 | 0
| FAUCETS | 0 | 400 | 0
| TOILET | 0 | 400 | 0
| SEAT/TRIP LEVER | 0 | 115 | 0
| BIDET SEAT | 0 | 1000 | 0
| SHOWER VALVE/TRIM | 0 | 1250 | 0
| WHIRLPOOL TUB | 0 | 4750 | 0
| TUB VALVE/FAUCET | 0 | 1000 | 0
GUEST BATH
| SINK | 0 | 100 | 0
| FAUCET | 0 | 250 | 0
| TOILET | 0 | 400 | 0
| SEAT/TRIP LEVER | 0 | 115 | 0
| SHOWER VALVE/TRIM | 0 | 450 | 0
| FIBERGLASS SHOWER BASE | 0 | 650 | 0
|  |  | SUBTOTAL | 0
|  |  | FREIGHT | 0
|  |  | 7% TAX | 0
|  |  | TOTAL | 0
23.000 | HVAC
23.05 | HVAC
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
23.4 | Duct Cleaning
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 26-28 ELEC. - LV
26.000 | ELECTRICAL
26.05 | Electrical Service & Wiring
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
26.41 | Lightning Protection
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
26.505 | Light Fixtures Allowance
*ALLOWANCE UNIT COSTS INCLUDE ALL BULBS
| LOCATION | TYPE |  | QTY | UNIT PRICE | SUBTOTAL
Main Level
| FOYER | CEILING MOUNT |  | 0 | 500 | 0
| DINING | CEILING MOUNT |  | 0 | 1000 | 0
| POWDER BATH | WALL MOUNT |  | 0 | 150 | 0
| KITCHEN | PENDANTS |  | 0 | 250 | 0
| GREAT ROOM | CEILING FAN |  | 0 | 400 | 0
| LAUNDRY ROOM | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| PRIMARY BEDROOM | CEILING FAN |  | 0 | 250 | 0
| PRIMARY BATHROOM | WALL MOUNT |  | 0 | 150 | 0
| PRIMARY WARDROBE | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| GUEST BEDROOM | CEILING FAN |  | 0 | 250 | 0
| GUEST BATHROOM VANITY | WALL MOUNT |  | 0 | 150 | 0
| SERVICE ENTRY | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| GARAGE | LED - by elect. |  | 0 | 0 | 0
Upper Level
| BEDROOM | CEILING FAN |  | 0 | 225 | 0
| BEDROOM | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| WARDROBE | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| BATHROOM VANITY | WALL MOUNT |  | 0 | 125 | 0
Lower Level
| BATHROOM VANITY | WALL MOUNT |  | 0 | 125 | 0
| BEDROOM | CEILING FAN |  | 0 | 225 | 0
| BEDROOM | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| WARDROBE | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| FITNESS ROOM | CEILING FAN |  | 0 | 225 | 0
| FITNESS WARDROBE | FLUSH MOUNT - by elect. |  | 0 | 0 | 0
| MECHANICAL/STORAGE | LED - by elect. |  | 0 | 0 | 0
EXTERIOR LIGHTING
| FRONT ENTRY | WALL MOUNT |  | 0 | 550 | 0
| GARAGE DOOR PIERS | WALL MOUNT |  | 0 | 300 | 0
| COVERED PATIO | CEILING FAN |  | 0 | 400 | 0
| COVERED PATIO | WALL MOUNT |  | 0 | 400 | 0
| LOWER PATIO | WALL MOUNT |  | 0 | 400 | 0
| FLOODS | WALL MOUNT - by elect. |  | 0 | 0 | 0
[5 empty] | SUBTOTAL | 0
[5 empty] | FREIGHT | 0
[5 empty] | 7% TAX | 0
[5 empty] | TOTAL (INCLUDING BULBS) | 0
26.57 | Lighting Control System Allowance
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
27.000 | COMMUNICATIONS
27.41 | Audio-Visual Systems/Structured Wire/Sound System Allowance
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
28.000 | ELECTRONIC SAFETY & SECURITY
28.07 | Security System/Fire Protection/Video Surveillance Allowance
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0

## DIV 31-32 EARTH-SITE
31.000 | EARTHWORK
31.218 | Site Demolition
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
31.23 | Excavation/Fill/Grading/Silt Fence
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
31.26 | Surveying
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.000 | EXTERIOR IMPROVEMENTS
32.13 | Exterior Concrete Flatwork
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
Unit Rate Estimate
Driveway |  | 0 | SF
Front Stoop |  | 0 | SF
Front Walk |  | 0 | SF
City Sidewalks |  | 0 | SF
AC Pads |  | 0 | SF
Pool Deck |  | 0 | SF
Rear Patio |  | 0 | SF
|  | 0 | SF
MATERIAL
sleeve materials (pvc for under slabs) |  |  | 0 | 75 | EA | 0
Granular (SF x .25ft x 1.25 / 18 = X tons) |  |  | 0 | 16 | TON | 0
Additive (Xypex for water impermeable) |  |  | 0 | 131.85 | BOX | 0
expansion joints at walls |  |  | 0 | 150 | EA | 0
SUBCONTRACTOR
Driveway (5" with rebar) |  |  | 0 | 0 | SF | 0
Driveway Curb |  |  | 0 | 0 | LF | 0
Street Curb Cut |  |  | 0 | 0 | SF | 0
Front Walks (4") |  |  | 0 | 0 | SF | 0
City Sidewalks (4") |  |  | 0 | 0 | SF | 0
Front Stoop |  |  | 0 | 800 | EA | 0
Concrete Steps |  |  | 0 | 0 | LF | 0
AC Pads (4") |  |  | 0 | 0 | SF | 0
Rear Patio (4") |  |  | 0 | 0 | SF | 0
Pool Deck (4") |  |  | 0 | 0 | SF | 0
Trench Drain |  |  | 0 | 0 | LF | 0
Paver inset areas |  |  | 0 | 0 | LF | 0
Additional Concrete Material for 5" thick |  |  | 0 | 82.5 | CY | 0
Pump Charge for elevated balconies |  |  | 0 | 1500 | EA | 0
Grading |  |  | 0 | 0.4 | SF | 0
Cure & Seal |  |  | 0 | 0.05 | SF | 0
Sealer (Application of Stifle) |  |  | 0 | 0.45 | SF | 0
[5 empty] | TOTAL | 0
32.142 | Pavers Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
Unit Rate Estimate
Driveway | 0 | SF
Front Walk | 0 | SF
Front Stoop | 0 | SF
Rear Patio | 0 | SF
Pool Deck | 0 | SF
| 0 | SF
| 0 | 8% waste
| 0 | total SFpavers
STEPPING STONES |  | 0 | EA
NOTE: verify full pallet quantities or sf count
Paver Material (incl tax) |  |  | ALLOWANCE | 0 | 6.25 | SF | 0
Bullnose Edging (lakeside nosing) |  |  | ALLOWANCE | 0 | 12 | LF | 0
Front Stoop (brick and mortar) |  |  | ALLOWANCE | 0 | 7.25 | SF | 0
Front Stoop |  |  | ALLOWANCE | 0 | 15.75 | SF | 0
Aluminum Edging |  |  | ALLOWANCE | 0 | 3.25 | LF | 0
Subcontractor Installation |  |  | ALLOWANCE | 0 | 6.75 | SF | 0
Palmeric Sand |  |  | ALLOWANCE | 0 | 1 |  | 0
additional for asphalt set |  |  | ALLOWANCE | 0 | 1.75 | SF | 0
Stepping Stones |  |  | ALLOWANCE | 0 | 100 | EA | 0
[6 empty] | TOTAL | 0
OPTION
Sealer / Enhancer |  |  | ALLOWANCE | 0 | 1.5 | SF | 0
32.18 | Athletic/Recreational Surfacing
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.181 | Artificial Turf
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.3 | Landscape Lighting Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.31 | Fences/Gates
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.32 | Retaining Walls Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.392 | Fire Pit Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.394 | Exterior Grill/Hood
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.8 | Irrigation Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0
32.922 | Seeding/Sod Allowance
| Sod - Raw Area | 0 | SF | 0.33 | 0 | 0
| (less beds) |  |  |  | 7% TAX | 0
[5 empty] | TOTAL | 0
32.931 | Landscaping Allowance
|  |  |  | Company | Company | Company | Company
Base Bid |  |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  |  | TOTAL | 0 | 0 | 0 | 0

## DIV 33 UTILITES
33.000 | UTILITIES
33.02 | Sewer / Water Utilities
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0
33.462 | Underground Buried Drainage
|  |  | Company | Company | Company | Company
Base Bid |  |  | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
|  | TOTAL | 0 | 0 | 0 | 0